## Slide 1
PI-4 Implementation Plan — Phase Timeline
Appendix to slide 6 · bar colour = objective, as slide 6 · three phase bands per feature · diamond marks the AP00288 gate, triangle the OCM sign-off · requirements runway shown left of the PI where it falls in PI-3 IP
PPL CMDB-CSDM | PI-4 Implementation Plan | SOW AP00288 | Oct 14, 2026
Feature
PI-3 IP
Oct 14–27
4.1
Oct 28 – Nov 10
4.2
Nov 11 – Nov 24
4.3
Nov 25 – Dec 8
4.4
Dec 9 – Dec 22
4.5
Dec 23 – Jan 5
4.6
Jan 6 – Jan 19
4.7 IP
Jan 20 – Feb 2
D3 15 Maps (1 of 3) 1646517
D8 CMDB Correctness 1639335
D4 15 Maps (2 of 3) 1642237
D9 Non-Discoverable CI Interface 1640795
D7 Adoption Campaign 1639308
D6 Stakeholder Notifications 1642240
D10 Server Build Flow 1640805
D2 Cisco Catalyst 1639225
D11 Server Decommission Flow 1640819
D5 15 Maps (3 of 3) 1642332
D12 Service Map Update Item 1640844
TBC Qualys 1639239
Phase:
Requirements / Spike
Build & Test
Validate & Release
gate on track
tight (<10 days)
no validation margin
Phase dates derived from the ADO sprint spans on slide 3 — requirements = one sprint ending where build starts; validate & release = one sprint after build ends. Sprint 4.5 treated as unavailable. D7 and Qualys have no validate-and-release window at all; D11, D5 and D12 finish on their gate date. Tripwire has no ADO item and cannot be scheduled. December change-freeze dates unconfirmed.