PPL CMDB-CSDM — PI-2 Objectives & Features

PI-2: May 13 – Aug 4, 2026   |   Active

PI-2 Objectives Summary

| # | Objective | BV | Priority |
| --- | --- | --- | --- |
| 1 | Automate Discovery Coverage for Network Gear CI Classes (>=90% quality by Aug 4) | 10 | Highest |
| 2 | Establish CI Data Certification Program (framework + pilot for Business Apps) | 8 | High |
| 3 | Expand Service Mapping Foundation (10 business-critical platforms/month) | 9 | High |
| 4 | Prepare CMDB for Regulatory and Security Integrations (NERC CIP + Qualys) | 8 | High |
| 5 | Embed NowAssist AI Across CMDB and ITSM Workflows | 7 | Medium |
| 6 | Enable Governed VMware-to-Azure Migration via CMDB-Driven Intelligence | 10 | Highest |

Objective 1 — Automate Network Gear Discovery

BV: 10  |  Priority: Highest  |  Op Priority: 1  |  ADO Obj: 1366657

| ADO Feature ID | Feature | Status |
| --- | --- | --- |
| 1383523 | Unplanned Backlog - CMDB Workstream | Active |
| 1356646 | Network Device Coverage Reconciliation - Group 1 | Active |
| 1356826 | SCCM Server Class Precedence Updates | Active |
| 1354797 | Server Class Data & Form Updates | Active |
| 1411480 | CMDB PI2.26 Enhancements | Active |
| 1354794 | Computer Class Data & Form Improvements | Active |
| 1355888 | Update Operational Monitoring Activities P2 | Active |
| 1355890 | Support ServiceNow Upgrade Analysis | Active |

Blockers: DB and SNMP credentials in progress (Tony); CI Ownership for servers pending OCM review; HCM needed for computer location (Sonika).

Objective 2 — Establish CI Data Certification Program

BV: 8  |  Priority: High  |  Op Priority: 1  |  ADO Obj: 1420082

| ADO Feature ID | Feature | Status |
| --- | --- | --- |
| 1247179 | Data Certification Pilot - Functionality | Active |
| 1371672 | Governance Model for Requesting New Business Applications | Active |
| 1382404 | Data Certification Rollout | Active |
| 1402958 | Data Certification Pilot - Implementation Planning | Active |
| 1402979 | Data Certification Pilot - Implementation Support | Active |

Objective 3 — Expand Service Mapping Foundation

BV: 9  |  Priority: High  |  Op Priority: 2  |  ADO Obj: 1366660

| ADO Feature ID | Feature | Status |
| --- | --- | --- |
| 1355866 | Service Mapping PI2 Wave 17 & 18 | Active |
| 1355868 | Service Mapping PI2 Wave 19 & 20 | Active |
| 1355871 | Service Mapping PI2 Wave 20 & 21 | Active |

Blockers: Missing server credentials for automated scanning (Sonika support needed); DNS issue ongoing.

Objective 4 — Prepare CMDB for Regulatory and Security Integrations

BV: 8  |  Priority: High  |  ADO Features: 1250905 (Qualys), 1370224 (NERC-CIP)

Stream A — Governance  (Op Priority: 2)

Formalizing CCB ceremony cadence and compliance process. Next steps: formalize CCB cadence, engage Jason Dubriel, document CMP.

Stream B — NERC-CIP Security Requirements  (Op Priority: 4)

ESS 02 scope. Early engagement phase. Next steps: locate docs (Alex), engage Sonika/Cyber compliance, engage Jason Dubriel.

Stream C — Qualys Integration  (Op Priority: 5)

| ADO ID | Story | Owner | PI Scope |
| --- | --- | --- | --- |
| US 1428703 | Install x_qual5_itam_nwapp plugin on dev, test and Prod (Part 1) | Stan | PI2 |
| US 1428704 | Configure Qualys integration for CMDB to Qualys (Part 2) | Stan | PI2 |
| Spike 1234585 | Define and Configure Data Scope and Import Views in Qualys | Stan | PI2 |

Phase 1 (PI2): Read-only integration. Phase 2 (PI3): Two-way integration if needed.

Objective 5 — Embed NowAssist AI Across CMDB and ITSM Workflows

BV: 7  |  Priority: Medium  |  Op Priority: 3  |  ADO Obj: 1408764

NOTE: ADO feature IDs still missing — Anu to confirm upon return. Stories created by Alex Phan on 2026-06-08.

| ADO Story ID | Story | Owner | Size | Sprint |
| --- | --- | --- | --- | --- |
| 1436576 | NowAssist: Confirm Platform Prerequisites for NowAssist Activation (Part 1) | Karen | 1 pt | 2.3 |
| 1436579 | NowAssist: Activate Now Assist for CMDB Plugin | Karen | 1 pt | 2.3 |
| 1436593 | NowAssist: Activate Contextual CI Form Help Skill | Karen | 1 pt | 2.3 |
| 1436592 | NowAssist: Activate CI Summarization Skill | Karen | 1 pt | 2.3 |

PI-2 scope: OOB capability assessment only (not full deployment). Full NowAssist rollout deferred to PI-3.

Objective 6 — Enable Governed VMware-to-Azure Migration

BV: 10  |  Priority: Highest  |  Op Priority: 0 (most urgent)  |  ADO Obj: 1420079

| ADO Feature ID | Feature | Status |
| --- | --- | --- |
| 1420613 | CMDB Support for Air Lift | Active |

Stories under Feature 1420613:

US 1418610 — Airlift to Azure Pre-Migration

US 1418618 — Airlift to Azure During Migration

US 1418621 — Airlift to Azure Post-Migration

US 1416384 — Auto Populate CI Owner / Support Group / Technical Owner for Server Class

Backlog Gap Check

| Objective | ADO Features | Stories | Status |
| --- | --- | --- | --- |
| Obj 1 - Network Gear Discovery | 8 confirmed | Spike 1421790 + others | Covered |
| Obj 2 - Data Certification | 5 confirmed | US 1402727 + others TBD | Covered |
| Obj 3 - Service Mapping | 3 confirmed | Multiple confirmed | Covered |
| Obj 4 - Governance (Stream A) | 1250905, 1370224 | None yet | Light |
| Obj 4 - NERC-CIP (Stream B) | 1250905, 1370224 | None yet | Light |
| Obj 4 - Qualys (Stream C) | 1250905, 1370224 | 3 stories/spikes (Stan) | Covered |
| Obj 5 - NowAssist | None - Joe to create | 4 stories (Karen) | Feature gap |
| Obj 6 - Azure Migration | 1420613 confirmed | 4 stories confirmed | Covered |