## Slide 1
PI-2 Scope & Delivery Focus
CMDB Team Working Session
PI-2 · Iteration 2.3 (Jun 10 - 23)
May 13 - Aug 4, 2026
Manuel Vazquez - Scrum Master, CMDB-CSDM

## Slide 2
Why This Deck
Clarity on what we committed to, what we added, and where to focus
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
This deck aligns what we are building to what the engagement committed to. It establishes the original contracted scope, the scope added during PI-2, and where to focus our effort and solution decisions for the rest of the increment.
1. Initial scope
What the engagement was contracted to deliver - 4 workstreams.
2. Added in PI-2
What PI-2 layered on top - 6 objectives, 3 of them new.
3. Direction
Our ranked goals, live work, capacity, risks, and the calls we own.
Audience: the CMDB team doing the work and making solution decisions.

## Slide 3
Initial Scope - Contracted
The contracted CMDB scope: 4 workstreams (WS #1-3 = CO#5 · WS #4 = prior CO)
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
# | Workstream | What it covers | Effort
WS #1 | Governance | Data dictionary / class attributes (Servers, Computers, Business Apps, Databases); SOX / ESS-02; CCB facilitation | 27 pts
WS #2 | Automated Data Ingestion | SCCM / Discovery precedence; 90% coverage validation (Computers & Servers); Oracle / MS-SQL discovery; Life Cycle bulk updates | 33 pts
WS #3 | Other Enhancements | Evaluate ONE integration - Tanium OR Qualys; asset / service-mapping data only (no vulnerability ingestion) | 7 pts
WS #4 | Service Mapping | Dev 4 fully dedicated; 5 maps / sprint x 6 sprints = 30 service maps | 48 pts
115 pts total (67 general pool + 48 Dev 4 dedicated)
Dev 4 is walled off for Service Mapping and does not draw on the shared (general) pool.
Contract term: CO#5 runs through June 30, 2026
All CO#5 deliverables are due June 30, with a $533,775 holdback released on acceptance. An extension covering July / August (Sprints 5-6) is expected but NOT yet signed.

## Slide 4
PI-2 Scope vs Signed Contract (CO#5)
Basis: signed CO#5 (Mar 31 - Jun 30, 2026) · 2 contracted · 1 partial · 2 added · 1 to verify
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
# | PI-2 Objective | Alignment | Note
6 | VMware -> Azure Migration | ADDED | Not in CO#5 - added, critical. Needs a change order. 100% VMs discovered & mapped pre-migration.
1 | Network Gear Discovery | VERIFY | Believed contracted (prior CO) - NOT named in CO#5. Confirm against CO#1-4. >=90% network-gear quality.
2 | CI Data Certification | CONTRACTED | CO#5 Deliverable 1.2 (named). Process, intake, Business App pilot, KB docs.
3 | Service Mapping Expansion | CONTRACTED | Contracted (prior CO). 30 maps target - exact commitment shape TBD.
4 | NERC-CIP & Qualys | PARTIAL | CO#5 buys Qualys REQUIREMENTS only; team is building (verify build CO). NERC-CIP explicitly EXCLUDED.
5 | NowAssist AI Embedding | ADDED | Not in CO#5 - added. ~17 pts. Needs a change order.
Two original commitments need a home:
WS #2 Auto Data Ingestion (CO#5 Deliverable 2) - contracted and delivered at task level, but has no PI-2 objective of its own. Give it a tracked goal.
SOX / ESS-02 (CO#5 Deliverable 1) - contracted, but not explicitly called out as its own PI-2 objective.

## Slide 5
Our Goals, Ranked
By operational priority · #1 split into added network gear vs. contracted ingestion
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
P0
BV 10
VMware -> Azure Migration
100% in-scope VMs discovered, classified & relationship-mapped pre-migration
At risk
Added in PI-2
P1
BV 10
Network Gear Discovery
>=90% of network-gear CIs meet data-quality standard by Aug 4
At risk
Contracted? verify
P1
Core
Server / Computer Data Ingestion
SCCM precedence + 90% Computer/Server coverage + class data & form updates
On track
Original WS #2
P1
BV 8
CI Data Certification
Framework defined + Business App pilot + repeatable cadence
On track
Original WS #1
P2
BV 9
Service Mapping Expansion
30 maps (10/month) of business-critical apps, by criticality
On track
Original WS #4
P2
BV 8
NERC-CIP & Qualys Foundation
100% foundational data model + integration approach defined
Blocked
Partial WS #3
P3
BV 7
NowAssist AI Embedding
Embed in key CMDB/ITSM touchpoints; measurable quality gain
At risk
Added - defer candidate

## Slide 6
Live Work - P0 / P1
What we are actually working - live ADO status (6/17 snapshot)
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
P0
VMware -> Azure Migration
3 Validation · 2 Active · Feat 1420613
- Airlift Pre/During/Post (1418610/18/21) - Validation; CI auto-populate 1416384 - Active
- Live driver: Ray's 450-server app-instance request (82/450 covered) - Risk #13
P1
Network Gear Discovery
2 Validation · 1 Active · 2 New · Feat 1356646
- Spikes 1402555 (Active) / 1402559 (New); credentials 1444864 (Validation, 6 tasks still in 2.2)
- Dep #1 network-gear stakeholder requirements (1383487) still New
P1
Server / Computer Data Ingestion (WS #2 - contracted)
6 Validation · 4 Active
- SCCM precedence 1403759 / 1403760 / 1403762 / 1403763 - all Validation
- Class data: 1454371, 1355167, 1455858 Active; 1407572, 1421790, 1387236 Validation
P1
CI Data Certification
1 UAT · 1 Validation · 3 empty features
- Dashboard 1402727 - UAT signed, PROD 6/23; Pilot changes 1435307 - Validation
- Watch: Feats 1371672 / 1382404 / 1402958 are shells, no stories yet

## Slide 7
Live Work - P2 / P3
What we are actually working - live ADO status (6/17 snapshot)
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
P2
Service Mapping Expansion
4 maps active · 2 spikes · Dev 4 dedicated
- WATT / Vault Inspection / MV90 / RIE active; spikes 1326754, 1420634
- Watch: ~36 carryover map tasks stranded in 2.1/2.2; Wave 20 & 21 empty
P2
NERC-CIP & Qualys Foundation
2 Blocked · 1 Active · NERC = dep only
- Qualys 1428703 / 1428704 BLOCKED - Issue 1465952 (vendor plugin approval)
- ESS-02 1420244 Active; NERC-CIP = dependency 1383515 only, no build stories
P3
NowAssist AI Embedding
1 Closed · 1 Resolved · 2 Active · Feat 1436574
- 1436576 Closed, 1436579 Resolved, 1436592 / 1470837 Active; 1436593 / 1436581 Ready
- Watch: ~17-pt admin / platform-setup prerequisite not yet storied
Not mapped to any objective - capacity leaking off-board
OCM 1428659 (Active, Nora Lizenberg) - no objective home · orphan stories 1472365 & 1399787 - no parent / no feature

## Slide 8
Capacity Reality
The added scope fits on paper - but the back half has no margin
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
Original scope (contracted)
115 pts
67 general pool + 48 Dev 4 dedicated
PI-2 additions (general pool)
~55 pts
Network Gear + NowAssist + VMware - absorbed into the buffer
General-pool demand
122 / 144
Buffer ~22 pts - but front/back-loaded
S1
May 13-23
10 / 24
Under
S2
May 27-Jun 6
19 / 24
Under
S3
Jun 10-20
23 / 24
Near
S4
Jun 24-Jul 4
24 / 24
At capacity
S5
Jul 8-18
24 / 24
At capacity
S6
Jul 22-Aug 1
22 / 24
Under
S4-S5 run at 100% (zero buffer). Dev code freeze Jun 27 - Jul 18 covers most of S4 + all of S5; Test code freeze Jul 18 - Aug 15 covers all of S6. The back half is the crunch. Note: CO#5 term ends Jun 30 (mid-S4) - S5/S6 sit beyond the signed term, pending a not-yet-signed extension.

## Slide 9
Roadmap - Plan vs. Reality
The plan is sound; several near-term gates are slipping
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
Plan phases: Initiation (S1) -> Foundation Build (S2-S3) -> Core Delivery (S4-S5) -> Finalization & Close (S6). Contract reality: CO#5 ends Jun 30 (mid-S4) - everything in S5/S6 sits beyond the signed term, pending an extension.
Where plan and live status diverge:
Plan: NowAssist admin 'complete by S2 (Jun 6)'
Reality: Not started - and it gates S5 workflow embedding.
Plan: Network Gear 'CI class defined by S3 (Jun 20)'
Reality: Dep #1 still New; unlikely by Jun 20 (we are in S3 now).
Plan: Service Mapping '15 maps by S3'
Reality: Only 4 maps active; ~36 tasks stranded in carryover.
Plan: VMware (P0, critical) parked entirely in S6
Reality: S6 is the IP iteration AND inside the test code freeze (Jul 18 - Aug 15).

## Slide 10
Risks & Escalations
9 risks total · only 2 need leadership action - and both are overdue
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
Risk | Type | Status | Action
#1 Missing / delayed HR / location data (physical computers) | Program | TO ESCALATE | Escalate now - 'before S3' deadline is today. Blocks Dep #7 + computer-location ingestion (WS #2).
#2 Undefined NERC-CIP requirements | Program | TO ESCALATE | Escalate now - overdue. Blocks Dep #2 and all PI-2 #4 NERC build work.
#4 Competing priorities / unplanned Airlift | Team | ACCEPTED | S4 + S5 at 100%. Reconsider: deferring NowAssist (P3) is a clean mitigation lever.
#5 ServiceNow upgrade / code-freeze windows | Team | ACCEPTED | Dates are known (dev Jun 27-Jul 18, test Jul 18-Aug 15) = S4-S6. 'Adjust sprint plan' action still outstanding.
#9 Airlift / Azure - credential, IP, firewall | Team | MITIGATED | Marked 'IP-only changes'. Pressure-test vs Ray's 450-server reality before trusting 'Mitigated'.
Also open: #3 key-member dependency (Owned), #6 Service Mapping PoC, #7 Qualys field mapping, #8 Business Owners (all Mitigated).

## Slide 11
Solution Decisions We Own
The calls the team and PO need to make - this is the direction
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
1
Track Server/Computer Ingestion (WS #2) as its own goal - it is contracted and mature, but invisible at the objective level today.
2
Set the NowAssist (P3) defer trigger now - it is the first thing to drop if S4/S5 tightens.
3
Hold the line in S4/S5 - no new scope; route every new ask through the PO trade-off.
4
Escalate Risks #1 and #2 this week - both are overdue and block contracted + added work.
5
NERC-CIP needs requirements before any build - it is dependency-only today; do not commit build stories yet.
6
Qualys is blocked on the vendor plugin (Issue 1465952) - monitor; do not burn capacity waiting on it.
7
Re-plan VMware out of the frozen S6 where possible - sequence Airlift discovery earlier.
8
Decide Service Mapping carryover (~36 tasks) - re-sprint or de-scope at iteration review.
9
Clean up off-board work - OCM 1428659 and orphans 1472365 / 1399787 need an objective home or closure.

## Slide 12
Focus & Next Steps
Protect committed goals; make the open calls
PPL CMDB-CSDM | PI-2 | Scope & Delivery Focus - Jun 18, 2026
Focus discipline
S4-S5 at 100% capacity + freezes Jun 27 - Aug 15. Protect P0/P1; NowAssist (P3) is the first defer candidate.
Immediate next steps:
Confirm the WS #2 goal split on the board and in ADO.
PO trade-off session: NowAssist defer trigger + S4/S5 capacity protection.
Escalate Risks #1 (location data) and #2 (NERC requirements) - this week.
Iteration-review decision on the Service Mapping carryover backlog.
Full traceability: PI-2/pi2-objectives-features-stories.md