## Slide 1
CMDB-CSDM Delivery Status
Weekly Leadership Report
PI-2 · Iteration 2.3 (Jun 10 - 23)
Week of June 11, 2026
Manuel Vazquez - Scrum Master, CMDB-CSDM

## Slide 2
How to Read This Report
Baseline edition - week-over-week deltas begin next week.
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
Three progress lenses, refreshed every week:
PI over PI
Are we delivering more value each Program Increment?
Iteration over Iteration
Is each 2-week sprint building on the last?
Week over Week
What concretely moved since the last report?
Status legend:
GREEN
On track
AMBER
Progressing, with watch items
RED
Blocked / needs intervention

## Slide 3
Executive Summary
Iteration 2.3 (Jun 10 - 23)
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
ON TRACK - WITH WATCH ITEMS
Delivery is progressing across all 6 objectives. Three items need leadership attention: NowAssist resourcing, an SCCM approval gate, and the DNS dependency.
Wins this period
+ Data Certification UAT signed off by Sonika (6/10) - clear path to PROD on Jun 23.
+ Service Mapping discovery breakthrough - credentials working; Linux servers, Oracle DBs, and listeners now visible.
+ Airlift dev admin access resolved (6/9) - migration stories unblocked.
+ Scrum Master transition complete - Manuel now leading CMDB ceremonies & delivery tracking.
Needs leadership attention
! NowAssist resourcing - Confirm replacement owner / approve reassignment.
! SCCM approval gate - Expedite approval to keep the story in-sprint.
! Service Mapping DNS - Leadership support on the DNS / infra dependency.

## Slide 4
PI-2 Objectives Scorecard
Status explains itself · Stories = moving / in-scope (provisional)
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
P0 Governed VMware-to-Azure Migration (Airlift)
4
stories in scope
4 moving · 0 stuck
On track - dev access resolved; 4 stories active
P1 Automate Discovery Coverage for Network Gear
6
stories in scope
3 moving · 3 stuck
At risk - 1 approval gate + 1 on-hold; ~6 stories not yet ID'd
P1 Establish CI Data Certification Program
1
stories in scope
1 moving · 0 stuck
On track - in UAT, signed off; PROD Jun 23
P2 Expand Service Mapping Foundation
6
stories in scope
6 moving · 0 stuck
On track - discovery scaling; DNS dependency still open
P2 Regulatory & Security Integrations (Qualys/NERC/CCB)
3
stories in scope
3 moving · 0 stuck
Progressing - Qualys active; CCB/NERC-CIP not yet storied
P3 Embed NowAssist AI Across CMDB & ITSM
4
stories in scope
0 moving · 4 stuck
Blocked - 4 stories await owner reassignment
Story counts derived from team notes - PROVISIONAL, not ADO-validated. 'Completed' tracking begins at first PROD deploy (Jun 23).

## Slide 5
Progress: PI over PI
Are we delivering more value each Program Increment?
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
PI-2 ACTIVE
May 13 - Aug 4, 2026
Iteration 2.3 of 6
6 objectives in flight; foundation laid + first PROD deployment
PI-3 PLANNING
Aug 5 - Oct 27, 2026
Planning Jul 22 - Aug 4
NowAssist 5-phase rollout, Qualys Phase 2, CI Cert extended scope
Note: Only PI-2 has live data today. PI-over-PI comparison populates once PI-3 begins (planning during the PI-2 IP iteration).

## Slide 6
Progress: Iteration over Iteration
Is each 2-week sprint building on the last?
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
Sprint 2.1
May 13 - 26 · COMPLETED
Foundation & refinement
- Airlift + CI auto-population stories shaped
- OOTB-first & customization governance established
- Retro theme: credential blockers dominated the sprint
Sprint 2.2
May 27 - Jun 9 · COMPLETED
SCCM precedence & unblocking
- SCCM locked as authoritative for 6 hardware attributes
- Service Mapping credentials resolved (6/9)
- Airlift dev admin access resolved (6/9)
- NowAssist activation stories created & assigned
Sprint 2.3
Jun 10 - 23 · ACTIVE
Deploy & scale
- Data Certification -> PROD (Jun 23)
- Service Mapping subnet scans expanding
- Qualys read-only integration active
- NowAssist activation pending owner reassignment
Metric note: Quantitative velocity (committed vs. accepted points) is not yet captured in sprint ceremonies. Establishing this metric is an active process-improvement item.

## Slide 7
Progress: Week over Week
What concretely moved since the last report?
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
Changes this period
Data Certification UAT signed off by Sonika (6/10) - clear path to PROD on Jun 23.
Service Mapping discovery breakthrough - credentials working; Linux servers, Oracle DBs, and listeners now visible.
Airlift dev admin access resolved (6/9) - migration stories unblocked.
Scrum Master transition complete - Manuel now leading CMDB ceremonies & delivery tracking.
Note: First edition = baseline. From next week this slide shows what moved vs. the prior report.

## Slide 8
Highest-Priority Objectives (P0 - P1)
Status and detail by objective
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
GREEN
Airlift (P0)
Pre/During/Post-Migration + CI auto-populate stories active. Dev access resolved 6/9.
GREEN
Data Certification (P1)
Dashboard in UAT, signed off 6/10. PROD deployment Jun 23; Todd validates Jun 24-25.
AMBER
Discovery / SCCM (P1)
Hardware-attribute precedence approved. Timestamp story blocked on approval; gap analysis in progress.

## Slide 9
Supporting Objectives (P2 - P3)
Status and detail by objective
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
AMBER
Service Mapping (P2)
Credentials resolved - discovery now finding infrastructure previously invisible. DNS dependency still open.
AMBER
Regulatory / Qualys (P2)
Qualys read-only integration active (3 stories). CCB Jun 16, Audit Sync Jun 18. NERC-CIP in early engagement.
AMBER
NowAssist AI (P3)
4 OOB activation stories ready but assigned to a departing team member - reassignment needed.

## Slide 10
Key Milestones & Upcoming Dates
Iteration 2.3 critical path
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
Jun 15
Data Certification UAT gate
Jun 16
CMDB CCB Meeting
Jun 17
Backlog Refinement 2.3
Jun 18
CMDB Audit Sync
Jun 19
PROD Change Request - Data Certification
Jun 23
Sprint 2.3 end + Data Certification PROD deployment
Jun 24-25
Todd validates Data Certification in PROD

## Slide 11
Risks & Leadership Asks
Where we need help to stay on track
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
Risk | Severity | Detail | Ask of Leadership
NowAssist resourcing | HIGH | 4 activation stories assigned to a team member rolling off the project. | Confirm replacement owner / approve reassignment.
SCCM approval gate | HIGH | Timestamp-alignment story blocked pending customization approval. | Expedite approval to keep the story in-sprint.
Service Mapping DNS | HIGH | Reverse-DNS issue limits full discovery coverage. | Leadership support on the DNS / infra dependency.
Code-freeze windows | HIGH | Dev freeze Jun 27 - Jul 18; Test freeze Jul 18 - Aug 15 compresses PI-2 completion. | Awareness; sequence deployments around freezes.

## Slide 12
What's Next
Looking ahead to PI-3 and the IP iteration
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
PI-3 Planning during the IP iteration (Jul 22 - Aug 4).
NowAssist Phase 1+: Duplicate CI Elimination, NL CMDB Search.
Qualys Phase 2: two-way integration for data completeness.
CI Certification: extend program beyond Business Apps.
Plan delivery around code freezes (Dev Jun 27-Jul 18, Test Jul 18-Aug 15).

## Slide 13
Appendix
Story-level detail
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026
Full traceability is maintained in the team's working notes:
- Objectives -> Features -> Stories: PI-2/pi2-objectives-features-stories.md
- Activity by Iteration (2.1 / 2.2 / 2.3): PI-2/pi2-iteration-activity.md
- Program Backlog Review notes: PI-2/Program-Backlog-Review/
This deck is regenerated weekly from build_status_deck.py.