## Slide 1
CMDB-CSDM Delivery Status
Weekly Leadership Report
PI-2 · Iteration 2.3 (Jun 10 - 23)
Week of June 11, 2026 (updated June 12, 12:00pm EST)
Manuel Vazquez - Scrum Master, CMDB-CSDM

## Slide 2
How to Read This Report
Updated 6/12 12:00pm EST - first week-over-week deltas vs the 6/11 baseline.
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
Three progress lenses, refreshed every week:
PI over PI
Are we delivering more value each Program Increment?
Iteration over Iteration
Is each 2-week sprint building on the last?
Week over Week
What concretely moved since the last report?
Status legend:
GREEN
On track
AMBER
Progressing, with watch items
RED
Blocked / needs intervention

## Slide 3
Executive Summary
Iteration 2.3 (Jun 10 - 23)
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
ON TRACK - WITH WATCH ITEMS
Delivery is progressing across all 6 objectives. Two items resolved since the 6/11 baseline (NowAssist resourcing, SCCM approval gate). New watch item: Qualys integration blocked pending a vendor plugin approval. DNS dependency and code-freeze windows remain.
Wins this period
+ NowAssist resourcing resolved - 4 OOB stories reassigned to Kiran Dhobale; prerequisites story now active, others ready.
+ SCCM approval gate cleared - timestamp-alignment story unblocked; all SCCM precedence stories now in validation.
+ Airlift migration stories advanced to validation.
+ Data Certification pilot changes in validation; dashboard PROD deploy on track for Jun 23.
Needs leadership attention
! Qualys vendor approval - Support / expedite vendor approval to unblock the read-only integration.
! Service Mapping DNS - Leadership support on the DNS / infra dependency.
! Code-freeze windows - Awareness; sequence deployments around freezes.

## Slide 4
PI-2 Objectives Scorecard
Status explains itself · Stories = moving / in-scope (provisional)
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
P0 Governed VMware-to-Azure Migration (Airlift)
4
stories in scope
4 moving · 0 stuck
On track - 3 airlift stories in validation; CI auto-populate active
P1 Automate Discovery Coverage for Network Gear
6
stories in scope
6 moving · 0 stuck
Improving - SCCM gate cleared; precedence stories in validation; ~6 not yet ID'd
P1 Establish CI Data Certification Program
2
stories in scope
2 moving · 0 stuck
On track - dashboard signed off (PROD Jun 23); pilot changes in validation
P2 Expand Service Mapping Foundation
6
stories in scope
6 moving · 0 stuck
On track - discovery scaling; DNS dependency still open
P2 Regulatory & Security Integrations (Qualys/NERC/CCB)
3
stories in scope
1 moving · 2 stuck
Watch - Qualys plugin BLOCKED on vendor approval; CCB Jun 16 / Audit Jun 18
P3 Embed NowAssist AI Across CMDB & ITSM
5
stories in scope
5 moving · 0 stuck
Unblocked - 4 stories reassigned to Kiran; 1 active, 3 ready + baseline spike
Story counts derived from team notes - PROVISIONAL, not ADO-validated. 'Completed' tracking begins at first PROD deploy (Jun 23).

## Slide 5
Progress: PI over PI
Are we delivering more value each Program Increment?
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
PI-2 ACTIVE
May 13 - Aug 4, 2026
Iteration 2.3 of 6
6 objectives in flight; foundation laid + first PROD deployment
PI-3 PLANNING
Aug 5 - Oct 27, 2026
Planning Jul 22 - Aug 4
NowAssist 5-phase rollout, Qualys Phase 2, CI Cert extended scope
PENDING DATA
PI-over-PI comparison metric
Comparison basis (objectives completed / business value delivered / stories accepted per PI) to be fixed before PI-3 begins. Only PI-2 has live data today - not yet ready for relevant data.
Note: Only PI-2 has live data today. PI-over-PI comparison populates once PI-3 begins (planning during the PI-2 IP iteration).

## Slide 6
Progress: Iteration over Iteration
Is each 2-week sprint building on the last?
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
Sprint 2.1
May 13 - 26 · COMPLETED
Foundation & refinement
- Airlift + CI auto-population stories shaped
- OOTB-first & customization governance established
- Retro theme: credential blockers dominated the sprint
Sprint 2.2
May 27 - Jun 9 · COMPLETED
SCCM precedence & unblocking
- SCCM locked as authoritative for 6 hardware attributes
- Service Mapping credentials resolved (6/9)
- Airlift dev admin access resolved (6/9)
- NowAssist activation stories created & assigned
Sprint 2.3
Jun 10 - 23 · ACTIVE
Deploy & scale
- Data Certification -> PROD (Jun 23)
- SCCM precedence stories advanced to validation; approval gate cleared
- Service Mapping subnet scans expanding
- Qualys read-only integration blocked on vendor plugin approval
- NowAssist activation reassigned to Kiran Dhobale - in progress
PENDING DATA
Iteration velocity - committed vs. accepted stories
Per-sprint committed -> accepted counts will quantify whether each iteration builds on the last. Quantitative velocity (committed vs. accepted points) is not yet captured in sprint ceremonies. Establishing this metric is an active process-improvement item. Not yet ready for relevant data.

## Slide 7
Progress: Week over Week
What changed in status since the last report?
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
Objective | Last week | This week | Δ stories | Trend
Governed VMware-to-Azure Migration (Airlift) | On track | On track | +0 mv / +0 stk | → No change
Automate Discovery Coverage for Network Gear | Watch | Watch | +3 mv / -3 stk | → No change
Establish CI Data Certification Program | On track | On track | +1 mv / +0 stk | → No change
Expand Service Mapping Foundation | Watch | Watch | +0 mv / +0 stk | → No change
Regulatory & Security Integrations (Qualys/NERC/CCB) | Watch | Watch | -2 mv / +2 stk | → No change
Embed NowAssist AI Across CMDB & ITSM | Watch | On track | +5 mv / -4 stk | ▲ Improved
Newly unblocked: none
Newly blocked: none
PENDING DATA
Completed / delivered this period
Delivery tracking (completed & accepted stories) begins at first PROD deploy (Jun 23). Current 'moving' counts reflect activity in flight, not completion. Not yet ready for relevant data.

## Slide 8
Highest-Priority Objectives (P0 - P1)
Status and detail by objective
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
GREEN
Airlift (P0)
Pre/During/Post-Migration stories in validation; CI auto-populate active. Dev access resolved 6/9.
GREEN
Data Certification (P1)
Dashboard signed off 6/10; PROD Jun 23, Todd validates Jun 24-25. Pilot changes in validation.
AMBER
Discovery / SCCM (P1)
SCCM approval gate cleared - timestamp story unblocked; precedence stories in validation. ~6 stories still need ADO IDs.

## Slide 9
Supporting Objectives (P2 - P3)
Status and detail by objective
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
AMBER
Service Mapping (P2)
Discovery scaling - infrastructure previously invisible now found. DNS dependency still open.
AMBER
Regulatory / Qualys (P2)
Qualys read-only stories BLOCKED - vendor plugin replacement pending approval. CCB Jun 16, Audit Sync Jun 18. NERC-CIP early engagement.
GREEN
NowAssist AI (P3)
Resourcing resolved - 4 OOB stories reassigned to Kiran Dhobale; 1 active, 3 ready + health-baseline spike. Feature 1436574 confirmed.

## Slide 10
Key Milestones & Upcoming Dates
Iteration 2.3 critical path
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
Jun 15
Data Certification UAT gate
Jun 16
CMDB CCB Meeting
Jun 17
Backlog Refinement 2.3
Jun 18
CMDB Audit Sync
Jun 19
PROD Change Request - Data Certification
Jun 23
Sprint 2.3 end + Data Certification PROD deployment
Jun 24-25
Todd validates Data Certification in PROD

## Slide 11
Risks & Leadership Asks
Where we need help to stay on track
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
Risk | Severity | Detail | Ask of Leadership
Qualys vendor approval | HIGH | Qualys replaced its plugin version; previous uninstalled, new one requested. Stories 1428703/1428704 blocked. | Support / expedite vendor approval to unblock the read-only integration.
Service Mapping DNS | HIGH | Reverse-DNS issue limits full discovery coverage. | Leadership support on the DNS / infra dependency.
Code-freeze windows | HIGH | Dev freeze Jun 27 - Jul 18; Test freeze Jul 18 - Aug 15 compresses PI-2 completion. | Awareness; sequence deployments around freezes.

## Slide 12
What's Next
Looking ahead to PI-3 and the IP iteration
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
PI-3 Planning during the IP iteration (Jul 22 - Aug 4).
NowAssist Phase 1+: Duplicate CI Elimination, NL CMDB Search.
Qualys Phase 2: two-way integration for data completeness.
CI Certification: extend program beyond Business Apps.
Plan delivery around code freezes (Dev Jun 27-Jul 18, Test Jul 18-Aug 15).

## Slide 13
Appendix
Story-level detail
PPL CMDB-CSDM | PI-2 | Week of June 11, 2026 (updated June 12, 12:00pm EST)
Full traceability is maintained in the team's working notes:
- Objectives -> Features -> Stories: PI-2/pi2-objectives-features-stories.md
- Activity by Iteration (2.1 / 2.2 / 2.3): PI-2/pi2-iteration-activity.md
- Program Backlog Review notes: PI-2/Program-Backlog-Review/
This deck is regenerated weekly from build_status_deck.py.