## Slide 1
Feature Structure
Every feature decomposes into the same three buckets · use it to create the spikes and stories under a feature in ADO
PPL CMDB-CSDM | Feature Structure | Oct 15, 2026
Spike / requirements
what must be answered before anyone builds
Access, data and dependencies understood
Technical approach agreed with the team
Build stories listed and sized
Configuration vs. customization determined
Exit — build stories pass DoR gates 1–4
Build & test
the stories that do the work
One story per increment of work
Each story fits one iteration
Testing inside the story
Staging deploy + PO demo
Exit — Definition of Done met
Promote to prod
getting it released and accepted
OCM comms and training where needed
Change request and PROD deploy
Evidence packaged
Acceptance received
Exit — gate evidenced
How to use it
Hold this next to a feature in ADO and create the items listed. Create every item with the “+” link from the Feature — never standalone. The bucket weights differ by feature type — see the two templates that follow.

## Slide 2
Template A — Network Inventory Integration
Applies to 1639206 SolarWinds · 1639225 Cisco Catalyst · 1639239 Qualys · Tripwire (no ADO item yet)
PPL CMDB-CSDM | Template A — Network Inventory Integration | Oct 15, 2026
Spike / requirements
3 items · fat
A-S1 Source access and authentication
A-S2 Data profile and field mapping
A-S3 Reconciliation and precedence
Build & test
5 items
A-B1 Configure data source connection
A-B2 Field mapping and transforms
A-B3 Identification and reconciliation rules
A-B4 Scheduled sync and error handling
A-B5 Validate against a sample set
Promote to prod
1 item · thin
A-P1 CR, PROD deploy, evidence, acceptance
Long pole — A-S1
Credentials and account permissions are the recurring blocker on this project. An integration POC changes no user-facing behaviour, so there is nothing to communicate and nobody to train — one promote item is enough.

## Slide 3
Template B — Lifecycle Process Flow
Applies to 1640805 Server Build Lifecycle · 1640819 Server Decommission Lifecycle
PPL CMDB-CSDM | Template B — Lifecycle Process Flow | Oct 15, 2026
Spike / requirements
3 items
B-S1 Current-state process map
B-S2 Target-state flow and CI state model
B-S3 Class Manager confirmation
Build & test
5 items
B-B1 Configure lifecycle states and flow
B-B2 Triggers and state automation
B-B3 Notifications and approvals
B-B4 User entry point (catalog item)
B-B5 Test with representative records
Promote to prod
3 items · fat
B-P1 OCM comms and training materials
B-P2 Change request and PROD deploy
B-P3 Evidence packaged, acceptance received
Long pole — B-S3
Class Manager sign-off is an external dependency, not team capacity. A lifecycle flow changes how people actually work, so communication and training are delivery work, not an afterthought.