## Slide 1
Implementation Structure — Pilot Features
Recommend the server lifecycle pair · run the structure once, adjust, run it again · both gate Feb 2, the lowest-value invoice month in the PI
PPL CMDB-CSDM | Feature Implementation Structure — Pilot | Oct 15, 2026
Pilot feature
4.1
Oct 28
4.2
Nov 11
4.3
Nov 25
4.4
Dec 9
4.5
Dec 23
4.6
Jan 6
4.7 IP
Jan 20
D10 1640805
Server Build Lifecycle Process Flow
D11 1640819
Server Decommission Lifecycle Flow
handoff — D10 spike closes, D11 spike opens
Spike
Build & test
Validate & release
Owned by you
Both features are M. Vazquez's. No new process imposed on A. Griffis, who is at 50% allocation and already carries 6 of 12 features.
Stage 3 gets a real test
Lifecycle process flows change how server builds and decommissions actually happen — genuine OCM, training and Class Manager sign-off, not a thin POC release.
Two runs, not two pilots
D10's spike closes Nov 24; D11's opens Nov 25. Fix what is awkward after the first run and apply it to the second, inside the same PI.
Watch
D11 finishes on its gate date with no validation margin, and its validate-and-release window falls in the IP iteration where capacity goes to I&A and PI-5 Planning — so the clean read on Stage 3 will come from D10's January window. Confirm Ray Reuter's availability for D10 requirements sign-off at the end of Sprint 4.2 before Nov 11.