## Slide 1
CMDB-CSDM Delivery Status
Weekly Leadership Report
PI-2 · Iteration 2.4 (Jun 24 - Jul 7)
Week of June 29, 2026
Manuel Vazquez - Scrum Master, CMDB-CSDM

## Slide 2
How to Read This Report
Reframed around the 3 CO5 contractual deliverables per the 6/29 CO5 Deliverable Alignment. Sub-item states from the 6/30 ADO board. Sprint 2.3 velocity derived from the board - committed-vs-accepted was not captured at the ceremony.
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
Three progress lenses, refreshed every week:
PI over PI
Are we delivering more value each Program Increment?
Iteration over Iteration
Is each 2-week sprint building on the last?
Week over Week
What concretely moved since the last report?
Status legend:
GREEN
On track
AMBER
Progressing, with watch items
RED
Blocked / needs intervention

## Slide 3
Executive Summary
Iteration 2.4 (Jun 24 - Jul 7)
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
CO5 FOCUS - ACCEPTANCE TIMELINE AT RISK
Sprint 2.4 was re-pointed entirely at the CO5 contractual deliverables per the 6/29 alignment; Service Mapping, Airlift, NowAssist and Network Discovery were temporarily deprioritized. Delivery is real - Sprint 2.3 closed 11 accepted points with a further 23 points delivered and now in validation - but most CO5 acceptance dates land after the 6/30 contractual deadline (Data Dictionary CCB approval 7/21). The $533,775 June holdback stands unless CO6 is executed. Qualys Part 2 and the 90%-coverage acceptance stories remain open gaps.
Wins this period
+ Sprint 2.3 closed - 11 pts accepted (7 items): NowAssist activation (prereqs/plugin/CI summarization), Data Cert pilot changes, Virtual Computer auto-population, Virtual Location Mgmt, Data Cert KB article.
+ Data Certification dashboard deployed to PROD (6/23); Todd validation 6/24-25 - strongest CO5 acceptance evidence.
+ Sprint 2.4 re-pointed entirely to CO5: 30 items / 45 pts across the 3 contractual deliverables; Data Dictionaries in validation.
+ Qualys Part 1 unblocked - vendor plugin approval landed; plugin install (1428703) now Active.
Needs leadership attention
! CO5 acceptance vs. 6/30 deadline - Confirm CO6 execution (re-baselines the open gaps to Jul 31 - Oct 30) or agree an acceptance / holdback plan.
! Qualys Part 2 unconfirmed - Confirm Part 2 status with Rich Santillo / Stan; close or formally defer to CO6.
! Dev code freeze Jul 4-18 - Awareness; sequence CO5 dev deployments before Jul 4.

## Slide 4
CO5 Deliverables Scorecard
The 3 contractual deliverables · sub-items = moving / in-scope
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
D1 Governance - Data Dictionary, Data Cert, ESS-02, SOX, CCB
8
sub-items in scope
8 moving · 0 stuck
8 acceptance stories under Feature 1480087; Data Dictionaries (Servers/Computers/Biz Apps/DB) in Validation; G1 (Databases) & G5 (CCB) closed at artifact level; DD CCB approval targets 7/21
D2 Automated Data Ingestion - Computers / Servers / Databases
3
sub-items in scope
3 moving · 0 stuck
SCCM/Discovery precedence reported complete (email); 90% coverage is the gap - Computer (G2) & Server (G3) audit-dashboard spikes + inventory/retirement cluster in flight; no formal 90%-measurement acceptance story yet
D3 Other Enhancement - Evaluate Qualys Integration
2
sub-items in scope
1 moving · 1 stuck
Part 1 (1428703) unblocked and Active after vendor-plugin approval; Part 2 (1428704) status unconfirmed (G4); CO5 bar = evaluate + document one integration
Scorecard reframed to CO5 contractual deliverables per the 6/29 alignment. Sub-item states from the 6/30 ADO board. No CO5-relevant story is confirmed Done as of the board; closest to acceptance is the Data Certification dashboard (PROD 6/23).

## Slide 5
Progress: PI over PI
Are we delivering more value each Program Increment?
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
PI-2 ACTIVE
May 13 - Aug 4, 2026
Iteration 2.4 of 6
Sprint 2.4 re-pointed to CO5 acceptance; first PROD deployment landed (Data Certification, 6/23)
PI-3 PLANNING
Aug 5 - Oct 27, 2026
Planning Jul 22 - Aug 4
CO6 gap closure (if signed), NowAssist rollout, Qualys full integration, CI Cert extended scope
PENDING DATA
PI-over-PI comparison metric
Comparison basis (objectives completed / business value delivered / stories accepted per PI) to be fixed before PI-3 begins. Only PI-2 has live data today - not yet ready for relevant data.
Note: Only PI-2 has live data today. PI-over-PI comparison populates once PI-3 begins (planning during the PI-2 IP iteration).

## Slide 6
Progress: Iteration over Iteration
Is each 2-week sprint building on the last?
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
Sprint 2.2
May 27 - Jun 9 · COMPLETED
SCCM precedence & unblocking
- SCCM locked as authoritative for 6 hardware attributes
- Service Mapping credentials resolved (6/9)
- Airlift dev admin access resolved (6/9)
- NowAssist activation stories created & assigned
Sprint 2.3
Jun 10 - 23 · COMPLETED
Deploy & scale
- Data Certification dashboard -> PROD (6/23); Todd validating 6/24-25
- NowAssist accepted: prerequisites, plugin activation, CI summarization
- SCCM server precedence set delivered to validation; approval gate cleared
- 11 pts accepted; 23 pts delivered into validation (see velocity below)
Sprint 2.4
Jun 24 - Jul 7 · ACTIVE
CO5 acceptance push
- Sprint re-pointed entirely to CO5 - 30 items / 45 pts across 3 deliverables
- Data Dictionaries (Servers/Computers/Biz Apps/DB) in validation
- 90%-coverage audit spikes + inventory/retirement cluster in flight
- Qualys Part 1 unblocked; Service Mapping/Airlift/NowAssist paused for CO5
Sprint 2.3 delivery - derived from the 6/30 ADO board
On board
30 items - 44 pts
Accepted / Done
7 items - 11 pts
Delivered, in validation
13 items - 23 pts
In progress / backlog
10 items - 10 pts
Derived from the 6/30 ADO board - a committed-vs-accepted baseline was not captured at the 2.3 ceremony, and this is a post-sprint snapshot, so the 23-pt validation tail is delivered work that carried into 2.4 pending acceptance.

## Slide 7
Progress: Week over Week
What changed in status since the last report?
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
Reporting reframed this edition - from 6 PI objectives to 3 CO5 contractual deliverables. Objective-level week-over-week deltas reset to the CO5 baseline and resume next edition.
Delivered this period (Sprint 2.3 close-out)
On board
30 items - 44 pts
Accepted / Done
7 items - 11 pts
Delivered, in validation
13 items - 23 pts
In progress / backlog
10 items - 10 pts
Key moves
+ Data Certification dashboard -> PROD (Jun 23) - first PROD deployment; delivery tracking now live.
+ NowAssist activation accepted: prerequisites Closed, plugin + CI summarization Resolved.
+ SCCM server precedence set (1403759/760/762/763) delivered to Validation.
+ Sprint 2.4 re-pointed to CO5 - 30 items / 45 pts across the 3 contractual deliverables.
Newly unblocked: Qualys Part 1 (vendor plugin approval landed) · Newly blocked: none

## Slide 8
CO5 Deliverable 1 - Governance
Status and detail by deliverable
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
AMBER
Data Dictionaries (Servers/Computers/Biz Apps/DB)
Four class dictionaries in Validation under Feature 1480087 (1480088/090/097/098). Databases closes gap G1 at artifact level. CCB review 7/7-7/20, approval target 7/21.
GREEN
Data Certification (pilot)
Dashboard deployed to PROD 6/23 (Todd validating 6/24-25) - strongest acceptance evidence. Pilot story 1480099 Ready DoR.
AMBER
ESS-02 / SOX / Monthly CCB
ESS-02 alignment (1480102) validation chain 7/1-7/7 with Jason Dubreuil. SOX BA review (1480105) + Monthly CCB (1480107, closes G5) Ready DoR; PM validation with Sonika 6/30.

## Slide 9
CO5 Deliverables 2 & 3 - Data Ingestion + Qualys
Status and detail by deliverable
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
GREEN
Data Ingestion - SCCM/Discovery precedence
Computers/Servers/Databases SCCM & Discovery precedence reported complete (6/29 email); SCCM server precedence set (1403759/760/762/763) in validation.
AMBER
90% Coverage (Computers G2 / Servers G3 / DB)
Audit-dashboard spikes (1480112/114/113) + inventory & bulk-retirement cluster in flight. Gap: no formal 90%-measurement acceptance story for CCB sign-off.
AMBER
Qualys Integration (Other Enhancement)
Part 1 (1428703) unblocked and Active after vendor approval; Part 2 (1428704) unconfirmed (G4). CO5 bar = evaluate + document one integration.

## Slide 10
Key Milestones & Upcoming Dates
CO5 acceptance critical path
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
Jun 23
Sprint 2.3 end + Data Certification dashboard PROD deployment
Jun 24-25
Todd validates Data Certification in PROD
Jun 29
CO5 Deliverable Alignment; Data Certification pilot start
Jun 30
CO5 contractual deadline; Data Dictionary finalize; SOX + CCB PM validation
Jul 1
Data Dictionary customer validation (Sonika)
Jul 4-18
Dev code freeze
Jul 7
Sprint 2.4 end; data/audit cleanup target (aggressive)
Jul 21
Data Dictionary CCB approval (monthly CCB)

## Slide 11
Risks & Leadership Asks
Where we need help to stay on track
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
Risk | Severity | Detail | Ask of Leadership
CO5 acceptance vs. 6/30 deadline | HIGH | Most CO5 acceptance dates fall after the 6/30 contractual deadline (Data Dictionary CCB approval 7/21). $533,775 of June fees held back until final acceptance. | Confirm CO6 execution (re-baselines the open gaps to Jul 31 - Oct 30) or agree an acceptance / holdback plan.
Qualys Part 2 unconfirmed | MEDIUM | Part 1 (1428703) unblocked and Active; Part 2 (1428704) configure step status unconfirmed (gap G4). | Confirm Part 2 status with Rich Santillo / Stan; close or formally defer to CO6.
Dev code freeze Jul 4-18 | HIGH | Freeze spans the tail of Sprint 2.4; CO5 dev-dependent work must land before Jul 4 or wait until Jul 18. | Awareness; sequence CO5 dev deployments before Jul 4.
90% coverage acceptance gap | MEDIUM | Computers (G2) and Servers (G3) have validation spikes but no formal 90%-measurement acceptance story for CCB sign-off. | Endorse creating coverage-measurement acceptance stories.
Deprioritized streams stranded | LOW | Service Mapping, Airlift, NowAssist and Network Discovery paused for CO5; backlog stranded across prior sprints. | Confirm the resumption plan after CO5 acceptance.

## Slide 12
What's Next
CO5 acceptance, CO6 gap closure, and resuming paused streams
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
Secure CO5 acceptance evidence for the CMDB CCB (Data Dictionary approval target Jul 21).
Confirm CO6 signature to re-baseline the 5 open gaps (Jul 31 -> Oct 30).
Close Qualys Part 2 (1428704) or formally defer to CO6.
Create 90%-coverage acceptance stories for Computers and Servers.
Resume Service Mapping / Airlift / NowAssist after CO5 acceptance; sequence around code freezes (Dev Jul 4-18, Test Jul 18-Aug 15).

## Slide 13
Appendix
Story-level detail
PPL CMDB-CSDM | PI-2 | Week of June 29, 2026
Full traceability is maintained in the team's working notes:
- CO5 deliverable traceability: co5-deliverable-tracking.md
- Objectives -> Features -> Stories: PI-2/pi2-objectives-features-stories.md
- Activity by Iteration (2.1 - 2.4): PI-2/pi2-iteration-activity.md
- Program Backlog Review notes: PI-2/Program-Backlog-Review/
This deck is regenerated weekly from build_status_deck.py.