## CO5 2.4 Alignment
CO5 Deliverable Alignment - Iteration 2.4 (Jun 24 - Jul 7, 2026)
CO5 Deliverable | Lead | Team (2.4) | Pts | Status
GOVERNANCE |  |  | 22
Data Dictionary - Servers | Manuel | Vinay | 2 | In Validation
Data Dictionary - Computers | Manuel | Bhushan | 2 | In Validation
Data Dictionary - Business Apps | Manuel | Kiran, Anthony, Joe | 10 | In Validation
Data Dictionary - Databases | Manuel | Kiran | 2 | In Validation (closes gap)
Data Certification | Joe | Joe | 2 | Ready / pilot starting
ESS-02 Alignment | Joe | Manuel | 1 | Scope to confirm (Jason Dubreuil)
SOX BA Review | Manuel | Uloma | 2 | Ready
Monthly CCB | Manuel | Manuel | 1 | Charter / CMP / sponsorship gaps
AUTOMATED DATA INGESTION |  |  | 22
Servers - 90% Coverage / Cleanup | Tony | Bhushan, Vinay, Anthony, Kiran, Anu | 18 | In Progress
Computers - 90% Coverage | Stan | Anthony | 2 | Thinly staffed (1 spike)
Databases - 90% Coverage | Stan | Stan | 2 | Thinly staffed (1 spike)
Discovery / SOX Indicators / Credentials (Comp/Srv/DB) | Stan / Tony | - | 0 | Complete (per status email)
Computers - Build Lifecycle | Stan | - | 0 | No 2.4 story
OTHER ENHANCEMENT |  |  | 1
Evaluate Qualys Integration | Stan | Stan | 1 | Tech blockers; Part 2 unconfirmed
CO5-ALIGNED TOTAL |  |  | 45 | 74% of iteration
NOT CO5-ALIGNED (upgrade / network / NowAssist) |  | Stan, Vinay, Kiran | 16 | 26% of iteration
ITERATION TOTAL |  |  | 61