## Slide 1
CMDB Governance & Lifecycle Advisory Review
Status Update Aligned to Audit Objectives
Data Completeness & Accuracy - Governance Structure - Stakeholder Engagement (OCM)
August 20, 2026
Corporate Audit Services engagement: CMDB Governance and Lifecycle Advisory Review
Manuel Vazquez - Product Owner, CMDB-CSDM

## Slide 2
Audit Objective 1 - Data Completeness & Accuracy
Corporate Audit Services | CMDB Governance and Lifecycle Advisory Review
PPL CMDB-CSDM | CMDB Governance & Lifecycle Advisory Review - Status Update | Aug 20, 2026
CCB-Ratified Jul 21
Approved Data Dictionary
CMP Stage 1 defines Mandatory / Audited attributes for all 4 core CI classes - the agreed standard for completeness and accuracy.
4 CI Classes
Data Certification Program
End-to-end process, PROD build, dashboards, and training. Computers & Servers gate Sep 30; Databases & Network Devices gate Oct 30.
Computer, Server, Network - Live
Automated Discovery
SCCM/Discovery precedence live for Computer & Server; credentialed discovery validated for Routers, Switches, and Firewalls.
2 Active Blockers
Open Data Gaps
Database discovery credential issue (Active, 8 pts) and network device coverage for 3 of 6 device types plus scheduling automation - both tracked toward their gates.
Objective 1: management has a documented plan - a ratified Data Dictionary and an active Certification Program - and is executing it, with two known data-completeness gaps being tracked to closure.

## Slide 3
Audit Objective 2 - Governance Structure & Ownership
Corporate Audit Services | CMDB Governance and Lifecycle Advisory Review
PPL CMDB-CSDM | CMDB Governance & Lifecycle Advisory Review - Status Update | Aug 20, 2026
Chair: Josh Sterling
Change Control Board (CCB)
Standing governance authority. Ratifies attribute governance, ownership assignments, and audit scope for the CMDB data model.
4 of 4 Core Classes
Class Managers Assigned
Todd Dierksheide (Business App), Monica Green / Paul Becker (Computer), Ray Reuter (Server & Database) - named, accountable owners per class.
Stage 1 of 3 Ratified
Configuration Management Plan (CMP)
Stage 1 (Data Dictionary) ratified July 21. Stage 2 (Lifecycle & Health Targets) and Stage 3 (Governance Process & Controls, gate Sep 30) in progress.
Approval-Gated
CI Retirement Governance Policy
Identify - Notify - Approve - Advance Notice - Implement. A controlled, audit-trailed workflow for every future CI retirement, pending formal CCB approval.
Objective 2: a standing governance body, named class owners, and a staged CMP are in place - periodic data validation formalizes further as CMP Stage 2 and 3 land.

## Slide 4
Audit Objective 3 - Stakeholder Engagement & OCM
Corporate Audit Services | CMDB Governance and Lifecycle Advisory Review
PPL CMDB-CSDM | CMDB Governance & Lifecycle Advisory Review - Status Update | Aug 20, 2026
Recurring - 3rd Thursday
Monthly CMDB Audit Sync
Standing communication cadence with PPL Audit and key stakeholders, confirmed ongoing since July 2026.
Jul 21 Session Held
CCB Ratification Sessions
Formal stakeholder review and approval events for governance artifacts, such as the Data Dictionary ratification.
In Flight
Certification Training & Office Hours
Kick-off, policy execution, monitoring, office hours, and feedback loops built into the certification rollout for each CI class.
Proven in Practice
Staged Communication Model
Used during the July cleanup response - key stakeholders engaged first, broader operational teams as the baseline stabilized.
Objective 3: recurring communication cadences and structured training/feedback loops are operating today, and were stress-tested during the July cleanup response.