## Slide 1
CMDB Audit Sync
PI2 Accomplishments & PI3 Activities
Governance Ratified. Certification and Discovery in Execution.
August 20, 2026
PI2 governance foundation ratified; PI3 certification and discovery execution underway
Manuel Vazquez - Product Owner, CMDB-CSDM

## Slide 2
PI2 - CMDB Audit Foundation
Governance ratified, discovery validated, certification piloted
PPL CMDB-CSDM | CMDB Audit Update - PI2 Accomplishments & PI3 Activities | Aug 20, 2026
15 decisions · 4 classes
Approved Data Dictionary
CCB-ratified July 21, 2026 (CMP Stage 1): Business Application, Computer, Server, Database. Establishes source of truth, mandatory rules, and audit scope for the CMDB.
Closed
ESS-02 Alignment
Validation completed and the story closed. Computer and Server data dictionaries are explicitly scoped to ESS-02 audit requirements.
Live & Validated
Automated Discovery - Computer & Server
SCCM / Discovery source-of-truth precedence established for both classes. Credentials enabling discovery completed.
Deployed to PROD
Data Certification Pilot - Business Application
Pilot group identified; certification dashboard UAT signed off and live in PROD - validating the certification workflow ahead of expansion to all CI classes.
Result: a CCB-ratified governance baseline for Business Application, Computer, Server, and Database data - the foundation PI3 certification and discovery build on.

## Slide 3
PI3 - Building on the PI2 Foundation
CO6 Objectives 3 & 4 - certification and discovery execution against the ratified baseline
PPL CMDB-CSDM | CMDB Audit Update - PI2 Accomplishments & PI3 Activities | Aug 20, 2026
Built on the PI2 baseline: ratified Data Dictionary · validated Discovery · closed ESS-02 alignment
Gate: Sep 30
Certify Computers & Servers
Active in Sprint 3.2 (started Aug 19). Certification criteria are drawn directly from the CCB-ratified data dictionary.
Gate: Oct 30
Certify Databases & Network Devices
Planned for Sprint 3.4 - stories are already pulling forward into Sprint 3.2, ahead of schedule.
Gate: Aug 31
Network Device Auto Discovery
Credentialed discovery live and validated for Routers, Switches, and Firewalls - extending the Computer/Server discovery model to network devices.
Credential Issue - Active
Database Auto-Discovery - PI2 Carryover
Enhanced Database Discovery (MS-SQL/Oracle) continues from PI2 under Feature 1554951. Sprint 3.1 is actively resolving a Linux Discovery credential issue blocking DB host connectivity (8 pts, Active).
CO6 Objectives 3 & 4 - every certification and discovery gate is measured against the PI2-ratified governance baseline.