# PI-3 Data Certification — Proposed Stories

Certify Databases (Feature 1517037) & Certify Network Devices (Feature 1517040)

CMDB-CSDM · PI-3 · CO6 Objective 3 (Expand CI Data Certification) · Prepared 2026-08-05 · Status: proposed, not yet created in ADO

# Certify Databases — Feature 1517037

Oct 30 CO6 gate · build Sprints 3.3–3.5 · training/sign-off in 3.6 (IP) · Owner: M. Vazquez

5 stories, total ≈ 13 points (proposed). Straighter clone of the Computers/Servers certification pattern, using existing audit-spike anchor 1480113.

## DB-1 · Document the Database Data Certification process flow

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517037 | 3.3 | 3 |

As the CMDB Configuration Management Process Owner,

I want the end-to-end Database data-certification process documented — trigger, attestation steps, roles, escalation, and remediation path — built off the 1480113 gap-remediation plan,

So that the certification campaign for the Database Instance class runs on an agreed, repeatable workflow before any PROD configuration is built.

Acceptance criteria:

- Process flow diagram covers the full cycle: campaign trigger → owner attestation → gap identification → remediation → re-attestation → sign-off

- Roles defined at each step (CI Owner, Technical Owner Group, Support Group, Process Owner) using the delivered Data Dictionary field mappings

- Attested attribute set for Database confirmed against the reconciled set (DEP-3) and the 1480113 gap plan — no drift

- Process notes the host-Server dependency and how a hostless DB is handled

- Escalation and non-response handling defined

- Process documented in the agreed location and reviewed with the Database CCB Class Manager, Ray Reuter

- Doc-only — no PROD change required

## DB-2 · Build Database certification policies/rules to PROD

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517037 | 3.4 | 3 |

As the CMDB Configuration Management Process Owner,

I want the ServiceNow data-certification campaign, filters, and attestation rules for cmdb_ci_db_instance configured and deployed to PROD,

So that Database CI owners can be issued attestation tasks against the agreed attribute set on a defined schedule.

Acceptance criteria:

- Certification definition/filter created scoping the active cmdb_ci_db_instance population (~3,113; Oracle + MS SQL child classes inherit additively)

- Attestation rules configured for the reconciled Database managed attribute set (CI Owner, Technical Owner Group, Support Group, Environment, Location)

- Certification schedule configured (frequency + first run window) and documented

- Configuration migrated to PROD via a governed update set / change

- Task routing verified — attestation tasks land with the correct owner group

- Dry-run on a bounded owner group confirms tasks generate and complete without error before full launch

## DB-3 · Stand up the Database certification tracking dashboard

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517037 | 3.4 | 2 |

As the CMDB Configuration Management Process Owner,

I want a live tracking dashboard for the Database certification cycle — coverage, attestation status, and outstanding gaps,

So that certification progress against the Oct 30 gate is visible to the team and stakeholders without manual reporting.

Acceptance criteria:

- Dashboard shows Database certification coverage: % attested, pending, and overdue against the scoped active population

- Outstanding-gap view surfaces the attributes driving non-certification (cross-checks the 1480113 audit gaps)

- Dashboard reads from the live certification records created by DB-2 (not a static export)

- Coordinated with the CMDB Health Completeness (Database) config so the two do not build overlapping scoring

- Dashboard reviewed with PO (Joe Dames) and confirmed as the reporting source for the Oct 30 gate

- Refresh cadence confirmed — scores update on schedule, not stale

## DB-4 · Run the Database certification cycle and monitor completeness

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517037 | 3.5 | 2 |

As the CMDB Configuration Management Process Owner,

I want the first Database certification cycle executed end-to-end with completeness monitored on the dashboard,

So that attestation is actively driven to the target coverage and the process is proven before the Oct 30 gate.

Acceptance criteria:

- First certification cycle launched to Database CI owners via the DB-2 configuration

- Attestation progress tracked on the DB-3 dashboard through the cycle

- Gaps surfaced during attestation routed to remediation per the DB-1 process

- Coverage reaches the agreed acceptance target for Databases; shortfall documented with cause if target not met

- Non-responding owners escalated per the DB-1 escalation path

- Cycle outcome (coverage %, gaps closed, gaps outstanding) recorded and reviewed at Sprint Review

## DB-5 · Deliver Database certification training to CI owners

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517037 | 3.5 → 3.6 (IP) | 3 |

As the CMDB Configuration Management Process Owner,

I want Database CI owners trained on the certification process — how to attest, correct gaps, and use office hours,

So that owners can sustain certification independently and the CO6 “training delivered” artifact is satisfied for the Database class.

Acceptance criteria:

- Training material produced covering the Database certification workflow (attest, remediate, re-attest)

- Training delivered to the Database CI owner / support-group audience; attendance or distribution recorded

- Office-hours / support channel established and communicated

- Quick-reference (job aid) distributed to owners

- Training completion evidenced for the Oct 30 gate (session recording, deck, or sign-off log)

- PO (Joe Dames) confirms the training artifact satisfies the CO6 Database certification acceptance criterion

### Dependencies (6)

- DEP-1 — Database audit spike 1480113 closed: status unconfirmed in ADO (unlike the sibling Computer/Server spikes, which closed) — verify before DB-1 anchors to it.

- DEP-2 — Data Dictionary CCB approval (1480098): Database attribute set not yet CCB-approved; certified list could still change under the team.

- DEP-3 — Reconcile the Database attribute set (BLOCKING): the managed-attribute slide (5 fields) and the audit dashboard overlap on only 3 of 8 fields; the dashboard's two worst gaps (Value Stream, Approval Group) aren't on the slide.

- DEP-4 — Database discovery data quality: Oracle / Kentucky visibility gap (ADO Issue 1520824) risks false certification gaps if not remediated or explicitly scoped out first.

- DEP-5 — Class Manager sign-off (Ray Reuter): attribute set and active-population scope (~3,113) not yet ratified by the Database CCB Class Manager.

- DEP-6 — Coordinate with CMDB Health Completeness CP-3: CP-3 (US 1520425) scores the same population — risk of double-counting the same gap across two dashboards.

# Certify Network Devices — Feature 1517040

Oct 30 CO6 gate · build Sprints 3.4–3.5 · training/sign-off in 3.6 (IP) · Owner: M. Vazquez

6 stories, total ≈ 18 points (proposed). Highest-risk certification feature — no existing audit-spike anchor (hence the extra NW-1), no named Class Manager, and hard-gated by Obj 4 Feature 1517005 finishing attribute population by Sep 30.

## NW-1 · Network audit-dashboard scope + gap-remediation baseline (Spike)

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517040 | 3.3 → 3.4 | 5 |

As the CMDB Configuration Management Process Owner,

I want an audit-dashboard scope and gap-remediation baseline for the six network device classes,

So that the network certification process (NW-2+) has the same gap-plan anchor the other three classes already have.

Acceptance criteria:

- Audit view scoped to the six device classes (Routers, Switches, Firewalls, Load Balancers, WAPs, Network Controllers) with exact sys_class_name values confirmed

- Per-attribute population baseline captured for the mandatory attribute set — % populated / missing per class

- Gap-remediation plan drafted (which gaps are discovery-fixable vs owner-attestable)

- Baseline reconciled against the Obj 4 ≥90% coverage denominator (1356646) so counts agree

- Findings written up as the anchor input to NW-2 / NW-4

## NW-2 · Document the Network Device certification process flow

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517040 | 3.4 | 3 |

As the CMDB Configuration Management Process Owner,

I want the end-to-end Network Device certification process documented — trigger, attestation steps, roles, escalation, and remediation path — built off the NW-1 baseline,

So that the certification campaign runs on an agreed, repeatable workflow before any PROD configuration is built.

Acceptance criteria:

- Process flow covers the full cycle: trigger → owner attestation → gap identification → remediation → re-attestation → sign-off

- Roles defined at each step, with the Network CCB Class Manager / governance owner identified

- Attested attribute set confirmed against the network mandatory-attribute set and the NW-1 baseline

- Process distinguishes discovery-populated attributes from owner-attestable attributes

- Escalation and non-response handling defined

- Reviewed with the network governance owner

- Doc-only — no PROD change required

## NW-3 · Build Network Device certification policies/rules to PROD

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517040 | 3.4 → 3.5 | 3 |

As the CMDB Configuration Management Process Owner,

I want the ServiceNow data-certification campaign, filters, and attestation rules for the network device classes configured and deployed to PROD,

So that network device owners can be issued attestation tasks against the mandatory attribute set on a defined schedule.

Acceptance criteria:

- Certification definition/filter created scoping the active network device population across the six classes

- Attestation rules configured for the network mandatory attribute set

- Attributes confirmed populated by Obj 4 discovery before the cycle runs — certification does not attest empty fields discovery was supposed to fill

- Certification schedule configured (frequency + first run window) and documented

- Configuration migrated to PROD via a governed update set / change

- Task routing verified — attestation tasks land with the correct owner group

- Dry-run on a bounded device set confirms tasks generate and complete without error

## NW-4 · Stand up the Network Device certification tracking dashboard

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517040 | 3.4 → 3.5 | 2 |

As the CMDB Configuration Management Process Owner,

I want a live tracking dashboard for the Network Device certification cycle — coverage, attestation status, and outstanding gaps,

So that certification progress against the Oct 30 gate is visible without manual reporting.

Acceptance criteria:

- Dashboard shows network certification coverage: % attested, pending, and overdue against the scoped active population per device class

- Outstanding-gap view surfaces the attributes driving non-certification (cross-checks the NW-1 baseline)

- Dashboard reads from the live certification records created by NW-3 (not a static export)

- Coverage aligns with the Obj 4 ≥90% network coverage reporting (1356646) so the two objectives tell a consistent story

- Dashboard reviewed with PO (Joe Dames) and confirmed as the reporting source for the Oct 30 gate

- Refresh cadence confirmed — scores update on schedule, not stale

## NW-5 · Run the Network Device certification cycle and monitor completeness

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517040 | 3.5 | 2 |

As the CMDB Configuration Management Process Owner,

I want the first Network Device certification cycle executed end-to-end with completeness monitored on the dashboard,

So that attestation is actively driven to the target coverage and the process is proven before the Oct 30 gate.

Acceptance criteria:

- First certification cycle launched to network device owners via the NW-3 configuration

- Attestation progress tracked on the NW-4 dashboard through the cycle

- Gaps surfaced during attestation routed to remediation per the NW-2 process

- Coverage reaches the agreed acceptance target for network devices; shortfall documented with cause (esp. gaps traceable to Obj 4 discovery not yet populating attributes)

- Non-responding owners escalated per the NW-2 escalation path

- Cycle outcome recorded and reviewed at Sprint Review

## NW-6 · Deliver Network Device certification training to owners

| Parent ID | Sprint | Points (proposed) |
| --- | --- | --- |
| 1517040 | 3.5 → 3.6 (IP) | 3 |

As the CMDB Configuration Management Process Owner,

I want network device owners trained on the certification process — how to attest, correct gaps, and use office hours,

So that owners can sustain certification independently and the CO6 “training delivered” artifact is satisfied for the Network Device class.

Acceptance criteria:

- Training material produced covering the network certification workflow (attest, remediate, re-attest)

- Training delivered to the network device owner audience; attendance or distribution recorded

- Office-hours / support channel established and communicated

- Quick-reference (job aid) distributed to owners

- Training completion evidenced for the Oct 30 gate (session recording, deck, or sign-off log)

- PO (Joe Dames) confirms the training artifact satisfies the CO6 Network Device certification acceptance criterion

### Dependencies (5)

- DEP-1 — Obj 4 mandatory attribute population complete (Feature 1517005) — CRITICAL PATH: gated Sep 30; certification cannot attest attributes discovery hasn't populated yet.

- DEP-2 — Network devices discovered as CIs (Feature 1516993): gated Aug 31; nothing to certify until devices exist as CMDB records.

- DEP-3 — Define the network device mandatory-attribute set: not covered by the delivered Data Dictionary (Computer/Server/Database/BA only).

- DEP-4 — Identify / confirm the Network CCB Class Manager: no governance owner named yet, unlike every other certified class.

- DEP-5 — Data Dictionary CCB approval — Network device attributes: depends on DEP-3 (attribute set) and DEP-4 (owner) both closing first.