## Slide 1
PI-3 Plan - CMDB / CSDM
Objectives & Features · Objective View + Sprint View
4 objectives · 11 features · 6 sprints (Aug 5 - Oct 27, 2026)
CMDB / CSDM team focus area - a subset of CO6
Manuel Vazquez - Scrum Master, CMDB-CSDM
Source: Azure DevOps (A-INFOPS\FY26\PI3), as of Jul 31, 2026. CMDB/CSDM focus area - a subset of CO6 (maps to 4 of the 7 CO6 objectives). Stories column: user stories confirmed created in ADO under that feature.

## Slide 2
PI-3 Objectives - Overview
4 CMDB/CSDM objectives · 11 features · each mapped to CO6
PPL CMDB-CSDM | PI-3 Objectives & Features | ADO A-INFOPS\FY26\PI3 | Jul 31, 2026
# | Objective | ADO ID | Owner | Feat | CO6 · delivery gates
1 | Automate Network Device Discovery in the CMDB Automated credentialed discovery of all network device types, mandatory attribute population, and ≥90% owner-validated coverage. | 1516954 | M. Vazquez | 3 | CO6 Obj 4 Aug 31 · Sep 30 · Oct 30
2 | Build & Validate Service Maps for Priority Business Apps Owner-validated Silver- and Gold-tier service maps, with ≥75% of the business-service inventory represented. | 1516955 | A. Griffis | 3 | CO6 Obj 5 Aug 31 · Sep 30 · Oct 30
3 | Certify CMDB Data Across the Four Major CI Classes End-to-end data certification - process, PROD build, dashboards, training - across Computers, Servers, Databases, Network Devices. | 1516956 | M. Vazquez | 4 | CO6 Obj 3 Sep 30 · Oct 30
4 | Activate the ServiceNow → Qualys Attribute Sync in Production One-way ServiceNow → Qualys sync of owner, support group, and SOX flag, live in production on a defined schedule. | 1516957 | M. Vazquez | 1 | CO6 Obj 2 Sep 30
Source: Azure DevOps (A-INFOPS\FY26\PI3), as of Jul 31, 2026. CMDB/CSDM focus area - a subset of CO6 (maps to 4 of the 7 CO6 objectives). Stories column: user stories confirmed created in ADO under that feature.

## Slide 3
Objective View - Features by Objective
11 features grouped under their 4 parent objectives · with CO6 delivery commitment
PPL CMDB-CSDM | PI-3 Objectives & Features | ADO A-INFOPS\FY26\PI3 | Jul 31, 2026
ADO ID | Feature | Sprint | Start | Stories | Delivery (CO6)
Automate Network Device Discovery in the CMDB · ADO 1516954 · CO6 Obj 4 · Owner: M. Vazquez |  |  |  |  | 
1516993 | Automated Credentialed Discovery Live — All Network Device Types | 3.1 | Aug 5 | 5 in ADO | Aug 31, 2026
1517005 | Mandatory Attribute Population via Discovery — Network Devices | 3.3 | Sep 2 | 5 in ADO | Sep 30, 2026
1356646 | Network Inventory Coverage Reconciliation & Owner Validation (≥90%) | 3.5 | Sep 30 | — | Oct 30, 2026
Build & Validate Service Maps for Priority Business Apps · ADO 1516955 · CO6 Obj 5 · Owner: A. Griffis |  |  |  |  | 
1517650 | Silver-Tier Service Maps (App → Infrastructure) + ≥75% Business-Service Inventory | 3.1 | Aug 5 | — | Aug 31, 2026
1517655 | Gold-Tier Service Maps (Service → App) + Silver Validation Pass | 3.3 | Sep 2 | — | Sep 30, 2026
1518000 | Remaining Contractor-Managed Silver-Tier Maps + All-Silver Service → App Layer | 3.5 | Sep 30 | — | Oct 30, 2026
Certify CMDB Data Across the Four Major CI Classes · ADO 1516956 · CO6 Obj 3 · Owner: M. Vazquez |  |  |  |  | 
1517029 | Certify Computers — CMDB Data Certification | 3.2 | Aug 19 | 5 in ADO | Sep 30, 2026
1517032 | Certify Servers — CMDB Data Certification | 3.2 | Aug 19 | 5 in ADO | Sep 30, 2026
1517037 | Certify Databases — CMDB Data Certification | 3.4 | Sep 16 | — | Oct 30, 2026
1517040 | Certify Network Devices — CMDB Data Certification | 3.4 | Sep 16 | — | Oct 30, 2026
Activate the ServiceNow → Qualys Attribute Sync in Production · ADO 1516957 · CO6 Obj 2 · Owner: M. Vazquez |  |  |  |  | 
1517065 | Activate ServiceNow → Qualys Attribute Sync (PROD) | 3.1 | Aug 5 | — | Sep 30, 2026

## Slide 4
Sprint View - Features by Iteration
Which features land in which PI-3 sprint (by ADO Iteration Path)
PPL CMDB-CSDM | PI-3 Objectives & Features | ADO A-INFOPS\FY26\PI3 | Jul 31, 2026
Sprint | Dates | # | Features (ADO ID · CO6 delivery date · color = objective)
Sprint 3.1 | Aug 5 - Aug 18 | 3 | 1516993 · Automated Credentialed Discovery Live — All Network Device Types — CO6 due Aug 31 1517650 · Silver-Tier Service Maps (App → Infrastructure) + ≥75% Business-Service Inventory — CO6 due Aug 31 1517065 · Activate ServiceNow → Qualys Attribute Sync (PROD) — CO6 due Sep 30
Sprint 3.2 | Aug 19 - Sep 1 | 2 | 1517029 · Certify Computers — CMDB Data Certification — CO6 due Sep 30 1517032 · Certify Servers — CMDB Data Certification — CO6 due Sep 30
Sprint 3.3 | Sep 2 - Sep 15 | 2 | 1517005 · Mandatory Attribute Population via Discovery — Network Devices — CO6 due Sep 30 1517655 · Gold-Tier Service Maps (Service → App) + Silver Validation Pass — CO6 due Sep 30
Sprint 3.4 | Sep 16 - Sep 29 | 2 | 1517037 · Certify Databases — CMDB Data Certification — CO6 due Oct 30 1517040 · Certify Network Devices — CMDB Data Certification — CO6 due Oct 30
Sprint 3.5 | Sep 30 - Oct 13 | 2 | 1356646 · Network Inventory Coverage Reconciliation & Owner Validation (≥90%) — CO6 due Oct 30 1518000 · Remaining Contractor-Managed Silver-Tier Maps + All-Silver Service → App Layer — CO6 due Oct 30
Sprint 3.6 IP | Oct 14 - Oct 27 | 0 | — no features planned —
Features span Sprints 3.1 - 3.5 (2-3 each); the 3.6 IP iteration holds none. Every feature completes in a sprint ending before its CO6 delivery date.

## Slide 5
Delivery Commitments - CO6 Gates
Every feature delivers a CO6 acceptance criterion; its completion date is the delivery commitment
PPL CMDB-CSDM | PI-3 Objectives & Features | ADO A-INFOPS\FY26\PI3 | Jul 31, 2026
ADO ID | Feature | Objective | Scheduled sprint
Aug 31, 2026 · 2 features · delivered in Sprint 3.1 (ends Aug 18) · ahead of the commitment |  |  | 
1516993 | Automated Credentialed Discovery Live — All Network Device Types | Network Discovery | Sprint 3.1
1517650 | Silver-Tier Service Maps (App → Infrastructure) + ≥75% Business-Service Inventory | Service Maps | Sprint 3.1
Sep 30, 2026 · 5 features · delivered in Sprints 3.1 - 3.3 (end by Sep 15) · ahead of the commitment |  |  | 
1517005 | Mandatory Attribute Population via Discovery — Network Devices | Network Discovery | Sprint 3.3
1517655 | Gold-Tier Service Maps (Service → App) + Silver Validation Pass | Service Maps | Sprint 3.3
1517029 | Certify Computers — CMDB Data Certification | Data Certification | Sprint 3.2
1517032 | Certify Servers — CMDB Data Certification | Data Certification | Sprint 3.2
1517065 | Activate ServiceNow → Qualys Attribute Sync (PROD) | Qualys Sync | Sprint 3.1
Oct 30, 2026 · 4 features · delivered in Sprints 3.4 - 3.5 (end by Oct 13) · ahead of the Oct 30 date (after PI-3 close, Oct 27) |  |  | 
1356646 | Network Inventory Coverage Reconciliation & Owner Validation (≥90%) | Network Discovery | Sprint 3.5
1518000 | Remaining Contractor-Managed Silver-Tier Maps + All-Silver Service → App Layer | Service Maps | Sprint 3.5
1517037 | Certify Databases — CMDB Data Certification | Data Certification | Sprint 3.4
1517040 | Certify Network Devices — CMDB Data Certification | Data Certification | Sprint 3.4
CO6 check: every feature is scheduled in a sprint that ends before its delivery date - the ADO plan fits within CO6.
Oct 30 gates fall after PI-3 close (Oct 27); those features complete by Sprint 3.5 (Oct 13), leaving the 3.6 IP iteration as validation buffer.

## Slide 6
PI-3 Program Board
Features across the 6 sprints · color-coded by objective
PPL CMDB-CSDM | PI-3 Objectives & Features | ADO A-INFOPS\FY26\PI3 | Jul 31, 2026
Sprint 3.1
Aug 5 - Aug 18
Discovery Live — all device types
ADO 1516993
CO6 due Aug 31
Silver-Tier Maps + ≥75% Inventory
ADO 1517650
CO6 due Aug 31
Activate SN→Qualys Sync (PROD)
ADO 1517065
CO6 due Sep 30
Sprint 3.2
Aug 19 - Sep 1
Certify Computers
ADO 1517029
CO6 due Sep 30
Certify Servers
ADO 1517032
CO6 due Sep 30
Sprint 3.3
Sep 2 - Sep 15
Mandatory Attribute Population
ADO 1517005
CO6 due Sep 30
Gold-Tier Maps + Silver Validation
ADO 1517655
CO6 due Sep 30
Sprint 3.4
Sep 16 - Sep 29
Certify Databases
ADO 1517037
CO6 due Oct 30
Certify Network Devices
ADO 1517040
CO6 due Oct 30
Sprint 3.5
Sep 30 - Oct 13
Coverage Reconciliation ≥90%
ADO 1356646
CO6 due Oct 30
Remaining Silver + Svc→App
ADO 1518000
CO6 due Oct 30
Sprint 3.6 IP
Oct 14 - Oct 27
— none —
Objective:
Network Discovery
Service Maps
Data Certification
Qualys Sync