## Slide 1
PI-3 Sprint & Story Plan — CMDB / CSDM
6 Sprints · Features & Stories · Aug 5 – Oct 27, 2026
4 objectives · 11 features · ~40 stories · 6 sprints
CMDB / CSDM team focus area — a subset of CO6
Manuel Vazquez — Scrum Master, CMDB-CSDM
Stories: REFERENCE / DRAFT — ADO is authoritative. Story IDs filled in as items are created in ADO.

## Slide 2
PI-3 Program Board — Features Across 6 Sprints
11 features · color-coded by objective · click sprint tabs for story detail
PPL CMDB-CSDM | PI-3 Sprint & Story Plan | ADO A-INFOPS\FY26\PI3 | Jul 29, 2026
Sprint 3.1
Aug 5–18
Discovery Live — all device types
ADO 1516993
CO6 Aug 31
Silver-Tier Maps + ≥75% Inventory
ADO 1517650
CO6 Aug 31
Activate SN→Qualys Sync (PROD)
ADO 1517065
CO6 Sep 30
Sprint 3.2
Aug 19–Sep 1
Certify Computers
ADO 1517029
CO6 Sep 30
Certify Servers
ADO 1517032
CO6 Sep 30
Sprint 3.3
Sep 2–15
Mandatory Attribute Population
ADO 1517005
CO6 Sep 30
Gold-Tier Maps + Silver Validation
ADO 1517655
CO6 Sep 30
Sprint 3.4
Sep 16–29
Certify Databases
ADO 1517037
CO6 Oct 30
Certify Network Devices
ADO 1517040
CO6 Oct 30
Sprint 3.5
Sep 30–Oct 13
Coverage Reconciliation ≥90%
ADO 1356646
CO6 Oct 30
Remaining Silver + Svc→App
ADO 1518000
CO6 Oct 30
Sprint 3.6 IP
Oct 14–27
— none —
Objective:
Network Discovery
Service Maps
Data Certification
Qualys Sync

## Slide 3
Sprint 3.1 — Aug 5 – Aug 18
No CO6 gate — delivery enablement sprint | test code freeze Aug 5–15 (no PROD deploys)
PPL CMDB-CSDM | PI-3 Sprint & Story Plan | ADO A-INFOPS\FY26\PI3 | Jul 29, 2026
ID | Type | Story / Enabler Description | Owner
ADO 1516993 · Automated Credentialed Discovery Live — All Network Device Types · CO6 Aug 31 · Network Discovery |  |  | 
ND-1 | Enabler | Configure SNMP/SSH credential records for all 6 device types (Routers, Switches, Firewalls, LBs, WAPs, Controllers) | Stan Tomberg
ND-2 | Enabler | Adjust discovery config + device config; re-parent 1402572, 1402574, 1459721 (SNMP/MID pilot) to this feature | Stan Tomberg
ADO 1517650 · Silver-Tier Service Maps (App→Infra) + ≥75% Business-Service Inventory · CO6 Aug 31 · Service Maps |  |  | 
SM-E | Enabler | Lock before PI: secure app-owner list, finalize Silver/Gold tier app lists, confirm discovery method | Tanzeel Rehman
SM-1 | Story | Gather + Build committed Silver batch (app→infra, discovery-side; feasible under test freeze Aug 5–15) | Tanzeel / Vinay
ADO 1517065 · Activate ServiceNow → Qualys Attribute Sync (PROD) · CO6 Sep 30 · Qualys Sync |  |  | 
Q-E | Enabler | Confirm Qualys plug-in landed (1465952); re-scope 1428704 to SN→Qualys direction; rename parent feature | Stan Tomberg
Q-1 | Story | Install Qualys plugin Dev/Test/Prod (1428703); design field-mapping & sync schedule for owner, support group, SOX flag | Stan Tomberg
ADO 1517029 · Certify Computers [doc-only prep — build starts Sprint 3.2] · CO6 Sep 30 · Data Certification |  |  | 
CC-1 | Story | Document Computer certification process flow off 1480114 gap plan — doc-only; no PROD deploy during freeze | Bhushan Salsekar
ADO 1517032 · Certify Servers [doc-only prep — build starts Sprint 3.2] · CO6 Sep 30 · Data Certification |  |  | 
SV-1 | Story | Document Server certification process flow off 1480112 gap plan — doc-only; resolve `environment` Mandatory ruling (DEP-7) | Bhushan Salsekar
Stories: REFERENCE / DRAFT — ADO is authoritative. Story IDs filled in as items are created in ADO.

## Slide 4
Sprint 3.2 — Aug 19 – Sep 1
CO6 gate Aug 31 — Automated Credentialed Discovery Live + Silver Service Maps + ≥75% Business-Service Inventory
PPL CMDB-CSDM | PI-3 Sprint & Story Plan | ADO A-INFOPS\FY26\PI3 | Jul 29, 2026
ID | Type | Story / Enabler Description | Owner
ADO 1516993 · Automated Credentialed Discovery Live — All Network Device Types · ✅ CO6 Aug 31 · Network Discovery |  |  | 
ND-3 | Story | Deploy + validate discovery at scale across all 6 device types; zero failed authentications confirmed | Stan Tomberg
ND-4 | Enabler | Configure discovery schedules on defined intervals; confirm CMDB auto-updates each cycle with no manual intervention | Stan Tomberg
ADO 1517650 · Silver-Tier Service Maps (App→Infra) + ≥75% Business-Service Inventory · ✅ CO6 Aug 31 · Service Maps |  |  | 
SM-2 | Story | Validate + Publish Silver batch; owner sign-off; inventory reconciliation to ≥75% business-service inventory | Tanzeel / Vinay
ADO 1517065 · Activate ServiceNow → Qualys Attribute Sync (PROD) · CO6 Sep 30 · Qualys Sync |  |  | 
Q-2 | Enabler | Build SN→Qualys config: field-mapping for CI owner, support group, SOX flag; transform maps; scheduled sync job | Stan Tomberg
ADO 1517029 · Certify Computers — CMDB Data Certification · CO6 Sep 30 · Data Certification |  |  | 
CC-2 | Enabler | Build Computer certification policies/rules to PROD (post-freeze, on/after Aug 15); configure attestation rules + task routing | Bhushan Salsekar
CC-3 | Enabler | Stand up Computer certification tracking dashboard (coverage %, outstanding gaps, live refresh) | Kiran Dhobale
ADO 1517032 · Certify Servers — CMDB Data Certification · CO6 Sep 30 · Data Certification |  |  | 
SV-2 | Enabler | Build Server certification policies/rules to PROD (resolve `environment` Mandatory ruling before build — DEP-7) | Bhushan Salsekar
SV-3 | Enabler | Stand up Server certification tracking dashboard (reconcile 3,917 vs 15,218 active count — DEP-5) | Kiran Dhobale
Stories: REFERENCE / DRAFT — ADO is authoritative. Story IDs filled in as items are created in ADO.

## Slide 5
Sprint 3.3 — Sep 2 – Sep 15
No CO6 gate this sprint — builds toward Sep 30 | test freeze lifted; all PROD deployments now unblocked
PPL CMDB-CSDM | PI-3 Sprint & Story Plan | ADO A-INFOPS\FY26\PI3 | Jul 29, 2026
ID | Type | Story / Enabler Description | Owner
ADO 1517005 · Mandatory Attribute Population via Discovery — Network Devices · CO6 Sep 30 · Network Discovery |  |  | 
ND-5 | Story | Define mandatory attribute set for Network Devices with governance (Josh Sterling / Adam Gross, CCB Network Class Manager) | Stan Tomberg
ND-6 | Enabler | Map discovery output → mandatory attributes per device type; remediate blank mandatory fields; validate none-blank | Stan Tomberg
ADO 1517655 · Gold-Tier Service Maps (Service→App) + Silver Validation Pass · CO6 Sep 30 · Service Maps |  |  | 
SM-3 | Story | Build Gold-tier service maps (service→app layer) per app; owner-validated; teams enabled | Tanzeel / Vinay
ADO 1517065 · Activate ServiceNow → Qualys Attribute Sync (PROD) · CO6 Sep 30 · Qualys Sync |  |  | 
Q-3 | Story | End-to-end test of SN→Qualys sync in non-prod; all 3 fields sync correctly; zero manual handoffs confirmed | Stan Tomberg
ADO 1517029 · Certify Computers — CMDB Data Certification · CO6 Sep 30 · Data Certification |  |  | 
CC-4 | Story | Run Computer certification cycle; monitor completeness on dashboard; drive to 90% coverage target; escalate non-responses | Bhushan Salsekar
ADO 1517032 · Certify Servers — CMDB Data Certification · CO6 Sep 30 · Data Certification |  |  | 
SV-4 | Story | Run Server certification cycle; monitor completeness on dashboard; drive to 90% coverage target; escalate non-responses | Bhushan Salsekar
ADO 1517037 · Certify Databases [process doc starts 3.3; build in 3.4] · CO6 Oct 30 · Data Certification |  |  | 
DB-1 | Story | Document Database certification process flow (resolve attribute-set discrepancy: slide vs. dashboard — CP-3 blocker — DEP-3) | Bhushan Salsekar
Stories: REFERENCE / DRAFT — ADO is authoritative. Story IDs filled in as items are created in ADO.

## Slide 6
Sprint 3.4 — Sep 16 – Sep 29
CO6 gate Sep 30 — Qualys Sync PROD · Certify Computers · Certify Servers · Gold Service Maps + Silver Validation
PPL CMDB-CSDM | PI-3 Sprint & Story Plan | ADO A-INFOPS\FY26\PI3 | Jul 29, 2026
ID | Type | Story / Enabler Description | Owner
ADO 1517037 · Certify Databases — CMDB Data Certification · CO6 Oct 30 · Data Certification |  |  | 
DB-2 | Enabler | Build Database certification policies/rules to PROD (scoped to reconciled active DB instance count) | Bhushan Salsekar
DB-3 | Enabler | Stand up Database certification tracking dashboard (watch Oracle/KY visibility gap — DEP-4) | Kiran Dhobale
ADO 1517040 · Certify Network Devices — CMDB Data Certification · CO6 Oct 30 · Data Certification |  |  | 
NW-1 | Story | ⚠ Net-new audit spike: define Network Device audit scope + gap baseline (no prior spike exists for this class) | Stan Tomberg
NW-2 | Story | Document Network Device certification process flow (after NW-1; depends on Obj 4 mandatory attributes) | Bhushan Salsekar
ADO 1517029 · Certify Computers — final: training · ✅ CO6 Sep 30 done by Sep 29 · Data Certification |  |  | 
CC-5 | Story | Deliver Computer certification training to CI owners; office hours; quick-reference job aid — CO6 training artifact | Joe Dames / M. Vazquez
ADO 1517032 · Certify Servers — final: training · ✅ CO6 Sep 30 done by Sep 29 · Data Certification |  |  | 
SV-5 | Story | Deliver Server certification training to CI owners; office hours; quick-reference job aid — CO6 training artifact | Joe Dames / M. Vazquez
ADO 1517655 · Gold-Tier Maps + Silver Validation Pass — final · ✅ CO6 Sep 30 done by Sep 29 · Service Maps |  |  | 
SM-4 | Story | Gold-tier owner sign-off + Silver re-validation pass; 15 Silver + Gold complete; teams enabled — CO6 Sep 30 gate | Tanzeel
ADO 1517065 · SN → Qualys Attribute Sync — final: PROD cutover · ✅ CO6 Sep 30 done by Sep 29 · Qualys Sync |  |  | 
Q-4 | Enabler | PROD cutover + go-live validation; confirm sync active on schedule, all 3 fields, zero manual handoffs — CO6 Sep 30 | Stan Tomberg
Stories: REFERENCE / DRAFT — ADO is authoritative. Story IDs filled in as items are created in ADO.

## Slide 7
Sprint 3.5 — Sep 30 – Oct 13
No new CO6 gate this sprint — builds toward Oct 30 gates
PPL CMDB-CSDM | PI-3 Sprint & Story Plan | ADO A-INFOPS\FY26\PI3 | Jul 29, 2026
ID | Type | Story / Enabler Description | Owner
ADO 1356646 · Network Inventory Coverage Reconciliation & Owner Validation (≥90%) · CO6 Oct 30 · Network Discovery |  |  | 
ND-7 | Story | Gap analysis: discovered network inventory vs. authoritative business-owner device list; quantify shortfall per type | Stan Tomberg
ND-8 | Enabler | Close coverage gaps (credential remediation / subnet scope expansion); build ≥90% coverage metric dashboard | Stan Tomberg
ADO 1518000 · Remaining Contractor-Managed Silver Maps + All-Silver Service→App Layer · CO6 Oct 30 · Service Maps |  |  | 
SM-5 | Story | Complete remaining Contractor-managed Silver apps (app→infra layer); owner-validated per app | Vinay / Tanzeel
SM-6 | Story | Build service→app layer for all Silver-tier apps; owner-validated; teams enabled | Tanzeel
ADO 1517037 · Certify Databases — CMDB Data Certification · CO6 Oct 30 · Data Certification |  |  | 
DB-4 | Story | Run Database certification cycle; monitor completeness; drive to 90% target; escalate non-responses per process | Bhushan Salsekar
ADO 1517040 · Certify Network Devices — CMDB Data Certification · CO6 Oct 30 · Data Certification |  |  | 
NW-3 | Enabler | Build Network Device certification policies to PROD (depends on Obj 4 mandatory attributes populated — Sep 30 prerequisite) | Bhushan Salsekar
NW-4 | Enabler | Stand up Network Device certification tracking dashboard | Kiran Dhobale
NW-5 | Story | Run Network Device certification cycle; monitor completeness on dashboard; drive to 90% target | Bhushan Salsekar
Stories: REFERENCE / DRAFT — ADO is authoritative. Story IDs filled in as items are created in ADO.

## Slide 8
Sprint 3.6 IP — Oct 14 – Oct 27
CO6 gate Oct 30 — Certify Databases · Certify Network Devices · Coverage ≥90% · Remaining Silver Maps
PPL CMDB-CSDM | PI-3 Sprint & Story Plan | ADO A-INFOPS\FY26\PI3 | Jul 29, 2026
ID | Type | Story / Enabler Description | Owner
ADO 1517037 · Certify Databases — final: training + sign-off · ✅ CO6 Oct 30 · Data Certification |  |  | 
DB-5 | Story | Deliver Database certification training to CI owners; training artifact satisfies CO6 Oct 30 Databases gate | Joe Dames / M. Vazquez
ADO 1517040 · Certify Network Devices — final: training + sign-off · ✅ CO6 Oct 30 · Data Certification |  |  | 
NW-6 | Story | Deliver Network Device certification training to CI owners; training artifact satisfies CO6 Oct 30 Network Devices gate | Joe Dames / M. Vazquez
ADO 1356646 · Network Inventory Coverage Reconciliation — final: owner sign-off · ✅ CO6 Oct 30 · Network Discovery |  |  | 
ND-9 | Story | Business-owner validation + sign-off confirming ≥90% network device coverage against authoritative inventory — CO6 Oct 30 | Stan Tomberg
ADO 1518000 · Remaining Silver + All-Silver Service→App Layer — final: sign-off · ✅ CO6 Oct 30 · Service Maps |  |  | 
SM-7 | Story | Owner validation sign-off for remaining Contractor-managed Silver + service→app layer for all Silver — CO6 Oct 30 | Tanzeel
Stories: REFERENCE / DRAFT — ADO is authoritative. Story IDs filled in as items are created in ADO.