## Slide 1
PI-3 Work Scheduled — CMDB / CSDM
5 Objectives · 15 Features · 213 Story Points · Aug 5 – Oct 27, 2026
All 4 certification classes fully reconciled in ADO — Computers, Servers, Databases, Network Devices
CMDB / CSDM team focus area — a subset of CO6
Manuel Vazquez — Product Owner, CMDB-CSDM
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 2
PI-3 Program Board — 15 Features Across 6 Sprints
Color-coded by objective · all features are parented to one of 5 PI-3 objectives
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
Sprint 3.1
Aug 5–18
Discovery Live — all device types
ADO 1516993 · CO6 Aug 31
Silver-Tier Maps + ≥75% Inventory
ADO 1517650 · CO6 Aug 31
Migrate BA → Service Instances (DQ)
ADO 1537867 · CO6 n/a
Activate SN→Qualys Sync (PROD)
ADO 1517065 · CO6 Sep 30
Database Class Clean-up (PI-2)
ADO 1554951 · CO6 n/a
Air Lift CMDB Support (PI-2)
ADO 1557616 · CO6 n/a
New BA Governance Model (PI-2)
ADO 1553982 · CO6 n/a
Sprint 3.2
Aug 19–Sep 1
Certify Computers
ADO 1517029 · CO6 Sep 30
Certify Servers
ADO 1517032 · CO6 Sep 30
Sprint 3.3
Sep 2–15
Mandatory Attribute Population
ADO 1517005 · CO6 Sep 30
Gold-Tier Maps + Silver Validation
ADO 1517655 · CO6 Sep 30
Sprint 3.4
Sep 16–29
Certify Databases
ADO 1517037 · CO6 Oct 30
Certify Network Devices
ADO 1517040 · CO6 Oct 30
Sprint 3.5
Sep 30–Oct 13
Coverage Reconciliation ≥90%
ADO 1356646 · CO6 Oct 30
Remaining Silver + Svc→App
ADO 1518000 · CO6 Oct 30
Sprint 3.6 IP
Oct 14–27
— sign-off buffer —
Objective:
Network Discovery
Service Maps / BA Migr.
Data Certification
Qualys Sync
PI-2 Carryover / Gov.

## Slide 3
Sprint Load Overview — Story Points by Workstream
213 known points across 25 features/sprints · Sprint 3.4 is the heaviest at 53 points
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
Chart: 
| 3.1 | 3.2 | 3.3 | 3.4 | 3.5 | 3.6 IP
Network Discovery | 13 | 0 | 5 | 11 | 14 | 5
Data Certification | 4 | 9 | 2 | 34 | 0 | 0
Service Maps / BA Migr. | 34 | 38 | 29 | 8 | 0 | 0
Qualys Sync | 1 | 0 | 0 | 0 | 0 | 0
PI-2 Carryover / Gov. | 4 | 0 | 0 | 0 | 0 | 0
⚠ 45 additional points from PI-2 carryover stories with no point value yet visible in ADO are not shown (4 database clean-up stories, 2 Airlift stories, 1537638).

## Slide 4
Sprint 3.1 — Aug 5 – Aug 18
No CO6 gate this sprint — delivery enablement | test code freeze Aug 5–15 (no PROD deploys)
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
ADO ID | Feature | Story / spike detail (id, ADO id, description, points) | Total pts
1516993 | Automated Credentialed Discovery Live — All Network Device Types | ND-1 1526911 Configure credentials (5) · ND-2 1526947 Discovery defs/IP ranges (1) · ND-3 1526951 Credentialed discovery live, all 6 device types (2) · ND-6 1557701 Analysis of network ranges (2) | 10
1356646 | Network Inventory Coverage Reconciliation (≥90%) — prep | 1402555 Identify CI classes for group 1 (3, spike) | 3
1517029 | Certify Computers | CC-1 1535486 Document cert process flow (2, spike) | 2
1517032 | Certify Servers | SV-1 1535496 Document cert process flow (2, spike) | 2
1517065 | Activate ServiceNow → Qualys Sync (PROD) | 1428703 Install x_qual5_itam_nwapp plugin, Dev/Test/Prod (1) | 1
1537867 | Migration of Business Apps to Application Services | S01 1553645 Inventory / reference-map (8) · S07 1553653 Stakeholder comms & enablement (8) | 16
1517650 | Silver-Tier Service Maps + ≥75% Inventory | 3 spikes + 15 stories — data-source discovery batch (11 named apps + 4 placeholder) | 18
— | PI-2 Carryover / Governance stories | 1512084 Populate Assigned-to, Computer Class (2, ⚠ misplaced under DB feature) · 1553978/1553980 Service Catalog + SOX-flag governance (1 each) | 4
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 5
Sprint 3.2 — Aug 19 – Sep 1
CO6 gate Aug 31 — Automated Credentialed Discovery Live + Silver Service Maps + ≥75% Inventory
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
ADO ID | Feature | Story / spike detail (id, ADO id, description, points) | Total pts
1517029 | Certify Computers ⚠ sequencing | CC-2 1535488 Build cert policies to PROD (2) · CC-3 1535489 Stand up dashboard (1) · CC-5 1535491 Deliver training (3, ⚠ lands ahead of CC-4) | 6
1517032 | Certify Servers | SV-2 1535499 Build cert policies to PROD (2) · SV-3 1535500 Stand up dashboard (1) | 3
1537867 | Migration of Business Apps to Application Services | S02 1553646 Copy BA → Application Service, retire original (8) · S09 1553656 Recurrence-guardrail spike (1) | 9
1517650 | Silver-Tier Service Maps + ≥75% Inventory | 13 spikes + 16 stories — data-source discovery + build batch | 29
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 6
Sprint 3.3 — Sep 2 – Sep 15
No CO6 gate this sprint — builds toward Sep 30 | test freeze lifted
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
ADO ID | Feature | Story / spike detail (id, ADO id, description, points) | Total pts
1517029 | Certify Computers | CC-4 1535490 Run cert cycle & monitor completeness (1) | 1
1517032 | Certify Servers | SV-4 1535502 Run cert cycle & monitor completeness (1) | 1
1517005 | Mandatory Attribute Population via Discovery — Network Devices | 1537633 Define mandatory candidates (2) · 1537635 Baseline population & gap analysis (3) | 5
1537867 | Migration of Business Apps to Application Services | S04 1553648 Enable migrated services (3) · S10 1553649 Validate migration end state (5) · S05 1553651 Retarget platform config off retired class (8) | 16
1517650 | Silver-Tier Service Maps + ≥75% Inventory ⚠ data quality | 5 spikes + 8 stories — all placeholder-titled, not yet filled in with real app names | 13
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 7
Sprint 3.4 — Sep 16 – Sep 29
CO6 gate Sep 30 (prior sprint's work lands) — ⚠ heaviest sprint: 53 pts, driven by Databases + Network Devices landing together
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
ADO ID | Feature | Story / spike detail (id, ADO id, description, points) | Total pts
1517037 | Certify Databases ⚠ clustering | DB-1 1560066 Document process flow (3, spike) · DB-2 1560067 Build to PROD (3) · DB-3 1560068 Dashboard (2) · DB-4 1560069 Run cycle (2) · DB-5 1560071 Training (3) | 13
1517040 | Certify Network Devices ⚠ clustering | NW-1 1560087 Audit-baseline spike (5) · NW-2 1560089 Process flow (3) · NW-3 1560091 Build to PROD (3) · NW-4 1560093 Dashboard (2) · NW-5 1560094 Run cycle (2) · NW-6 1560096 Training (3) | 18
1517032 | Certify Servers | SV-5 1535504 Deliver training (3) | 3
1517005 | Mandatory Attribute Population via Discovery — Network Devices | 1537637 Populate non-discoverable attrs, CI owner (2) · 1537638 Validate no blanks (TBD) · 1560305 …Support Group (2) · 1560306 …Technical Group Owner (2) · 1560308 …Environment (2) | 8 + TBD
1356646 | Network Inventory Coverage Reconciliation (≥90%) — prep | 1402559 Compare CI class sources (3, spike) | 3
1537867 | Migration of Business Apps to Application Services | S06 1553652 Route operational CIs to App Service (3) · S08 1553654 Post-migration hypercare & close-out (5) | 8
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 8
Sprint 3.5 — Sep 30 – Oct 13
No new CO6 gate this sprint — builds toward Oct 30
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
ADO ID | Feature | Story / spike detail (id, ADO id, description, points) | Total pts
1356646 | Network Inventory Coverage Reconciliation (≥90%) | CR-1 1559163 Define authoritative inventory / denominator (3) · CR-2 1559166 Gap analysis (3) · CR-3 1559175 Gap closure (5) · CR-4 1559183 Coverage dashboard (3) | 14
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 9
Sprint 3.6 IP — Oct 14 – Oct 27
CO6 gate Oct 30 — Certify Databases · Certify Network Devices · Coverage ≥90% | sign-off / validation buffer, not new build
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
ADO ID | Feature | Story / spike detail (id, ADO id, description, points) | Total pts
1356646 | Network Inventory Coverage Reconciliation (≥90%) — final | CR-5 1559193 Business-owner validation & sign-off on ≥90% coverage (5) | 5
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 10
Certification Reconciliation — Computers & Servers
CO6 Obj 3 · Sep 30 gate · all 10 stories created in ADO, IDs reconciled
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
Local | ADO ID | Story | Points | Sprint | State
ADO 1517029 · Certify Computers |  |  |  |  | 
CC-1 | 1535486 | Document the Computer Data Certification process flow | 2 | 3.1 | Ready DoR
CC-2 | 1535488 | Build Computer certification policies/rules to PROD | 2 | 3.2 | Ready DoR
CC-3 | 1535489 | Stand up the Computer certification tracking dashboard | 1 | 3.2 | Ready DoR
CC-4 | 1535490 | Run the Computer certification cycle and monitor completeness | 1 | 3.3 | New
CC-5 | 1535491 | Deliver Computer certification training to CI owners | 3 | 3.2 | Ready DoR
ADO 1517032 · Certify Servers |  |  |  |  | 
SV-1 | 1535496 | Document the Server Data Certification process flow | 2 | 3.1 | Active
SV-2 | 1535499 | Build Server certification policies/rules to PROD | 2 | 3.2 | Ready DoR
SV-3 | 1535500 | Stand up the Server certification tracking dashboard | 1 | 3.2 | Ready DoR
SV-4 | 1535502 | Run the Server certification cycle and monitor completeness | 1 | 3.3 | New
SV-5 | 1535504 | Deliver Server certification training to CI owners | 3 | 3.4 | New
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 11
Certification Reconciliation — Databases & Network Devices
CO6 Obj 3 · Oct 30 gate · all 11 stories created in ADO, IDs reconciled — ⚠ all landed in Sprint 3.4
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
Local | ADO ID | Story | Points | Sprint | State
ADO 1517037 · Certify Databases |  |  |  |  | 
DB-1 | 1560066 | Document the Database Data Certification process flow | 3 | 3.4 | New (spike)
DB-2 | 1560067 | Build Database certification policies/rules to PROD | 3 | 3.4 | New
DB-3 | 1560068 | Stand up the Database certification tracking dashboard | 2 | 3.4 | New
DB-4 | 1560069 | Run the Database certification cycle and monitor completeness | 2 | 3.4 | New
DB-5 | 1560071 | Deliver Database certification training to CI owners | 3 | 3.4 | New
ADO 1517040 · Certify Network Devices |  |  |  |  | 
NW-1 | 1560087 | Network audit-dashboard scope + gap-remediation baseline | 5 | 3.4 | New (spike)
NW-2 | 1560089 | Document the Network Device certification process flow | 3 | 3.4 | New
NW-3 | 1560091 | Build Network Device certification policies/rules to PROD | 3 | 3.4 | New
NW-4 | 1560093 | Stand up the Network Device certification tracking dashboard | 2 | 3.4 | New
NW-5 | 1560094 | Run the Network Device certification cycle and monitor completeness | 2 | 3.4 | New
NW-6 | 1560096 | Deliver Network Device certification training to owners | 3 | 3.4 | New
Reconciled against ADO board export (Iteration Path), Aug 6, 2026. Points marked TBD are not yet visible in ADO.

## Slide 12
Open Items & Data Quality Flags
Surfaced while reconciling the Aug 6 ADO export — none of these block PI-3, all need an owner
PPL CMDB-CSDM | PI-3 Work Scheduled | ADO A-INFOPS\FY26\PI3 | Aug 6, 2026
Sprint 3.4 clustering
All 5 Databases stories and all 6 Network Devices stories landed in Iteration 3.4 in ADO, rather than phased across 3.4→3.6 IP as drafted — 31 of 53 points in that sprint from these two features alone. Same pattern as CC-5 landing ahead of CC-4.
Service Mapping placeholder titles
17 of the 39 “Gather/Build/Validate/Publish” stories under Feature 1517650 are still titled [PLACEHOLDER] — bulk-created template rows not yet filled in with a real app / data-source name. Flag to Adam Griffis.
Possible duplicate stories
1508982 / 1513944 (no parent, no sprint assigned) look like duplicates of 1553978 / 1553980 (parented to Feature 1553982, Sprint 3.1, same titles). Not resolved — confirm in ADO.
1512084 still misplaced
“Populate Assigned-to field in Computer Class” is parented to the Database Class Clean-up feature (1554951), not a Computer-class feature. Needs reparenting in ADO.
Unparented / no-sprint item
1393089 “Requirement Gathering for Non-OT devices” (0 pts) has no parent feature and no sprint — ownership unclear.
Points not yet visible in ADO
1537638 (Mandatory Attribute Population, Sprint 3.4), plus 4 PI-2 database clean-up stories and 2 Airlift stories — real load, but not counted in the 213-point total above.