Change Order #6

For ServiceNow Release 2 and 3 Deployment

This Change Order #6 (“Change Order #6”) is made by and between Accenture International Limited (“Contractor” or “Accenture”) and PPL Services Corporation (“Company” or “’PPL”) as of June 30, 2026 (the “Change Order #6 Effective Date”)  and hereby amends the Statement of Work for ServiceNow Release 2 and 3 Deployment (“the Project”) dated October 14, 2024, and its Change Orders, and is subject to the terms and conditions of the Enterprise Services Agreement (the “Agreement”) dated November 29, 2024. In case of a conflict in terms between this Change Order and the Statement of Work or the Agreement, the terms of the Change Order shall prevail.

Except as specifically provided herein, the terms and conditions of the Statement of Work and Agreement shall remain unchanged and in full force and effect. Capitalized terms not defined herein shall have the meaning described in the Statement of Work and Agreement. Company and Contractor amend the Agreement as set forth herein and the Parties agree to the following:

Purpose:

The purpose of Change Order #6 is to extend the Term through October 30, 2026, incorporate Deliverables and update Fees.

The following details changes to the original SOW titled, ServiceNow Release 2 and 3 Deployment:

- Article 1 (Services), Assumptions and/or Dependencies shall be amended to add the following:

- The Services are limited to the activities expressly described in the SOW and applicable Change Orders.

- Any additional services, deliverables, integrations, environments, or requirements not explicitly stated shall be considered out of scope.

- Changes to scope, including but not limited to additional requirements, expanded environments, or increased volumes, shall be subject to formal change control procedures.

- Timely delivery of Services is supported by Company’s collaboration and participation throughout the engagement, including: service mapping; network discovery; CI coverage; providing access to required systems, environments, and data; ensuring availability of appropriate personnel, including product owners, subject matter advisors, and service/application owners, to support ongoing activities, validation, and decision-making; and providing timely review and feedback on deliverables.

- In support of the agreed delivery timelines, Company shall use commercially reasonable efforts to respond to Contractor’s questions and approvals requests, or other Company’s dependencies within three (3) business days, unless otherwise agreed by the Parties.

- The Parties acknowledge that any delays related to these dependencies may require reasonable adjustments to the project schedule and associated milestones.

- Article 1 (Services), Deliverables shall be amended to add the following:

Deliverables. The following Deliverables shall be provided under this Change Order 6:

| # | Workstream | Description | AC # | Acceptance Criteria | Due Date |
| --- | --- | --- | --- | --- | --- |
|  | Network Gear Discovery | Establishes automated, real-time discovery of network devices to populate and maintain the CMDB. This capability eliminates manual data collection, reduces configuration drift, and provides the foundation for impact analysis during incidents — directly improving response times and reducing outage risk across PPL’s network infrastructure. |  | Network device types (i.e. Routers, Switches, Firewalls, Load Balancers, Wireless Access Points, and Network Controllers) are actively discovered using validated credentials, with no failed authentications on target devices. | August 31, 2026 |
|  |  |  |  | Network discovery schedules are running on defined intervals, and CMDB records for network devices are automatically updated without manual intervention within each scheduled cycle. | August 31, 2026 |
|  |  |  |  | All discoverable, mandatory CMDB attributes for network device (as defined in CMDB governance) are fully populated via discovery, with no mandatory fields left blank. | September 30, 2026 |
|  |  |  |  | 90% or more of the expected network device inventory is represented in the CMDB, validated against authoritative data provided by business owners. | October 30, 2026 |
|  | Service Mapping | Builds end-to-end visibility of business services and their underlying infrastructure dependencies within ServiceNow. Accurate service maps enable faster incident triage, more reliable change impact assessments, and informed prioritization during outages — reducing MTTR (Mean Time to Resolve) and minimizing the risk of unintended service disruptions. |  | Service maps for fifteen (15) priority (i.e. Silver-tier) business applications are built in ServiceNow, showing full dependencies from business application to infrastructure CIs, validated by service/application owners, and operational teams communicated and provided materials for how to use. | August 31, 2026 |
|  |  |  |  | 75% or more of the identified business service inventory is represented in the CMDB, validated by the business service owners (i.e. source providers) *Assumes business services have been defined prior to start | August 31, 2026 |
|  |  |  |  | Service maps for fifteen (15) priority (i.e. Silver-tier) business applications are built in ServiceNow, showing full dependencies from business application to infrastructure CIs, validated by service/application owners, and operational teams communicated and provided materials for how to use. | September 30, 2026 |
|  |  |  |  | Service maps for gold-tier business apps are built in ServiceNow, showing full dependencies from business service to business application, validated by service/application owners, and operational teams communicated and provided materials for how to use. | September 30, 2026 |
|  |  |  |  | Service maps for the remainder of the Silver-tier business applications managed by Contractor are built in ServiceNow, showing full dependencies from business application to infrastructure CIs, validated by | October 30, 2026 |
|  |  |  |  | Service maps for silver tier business applications are built in ServiceNow, showing full dependencies from business service to business application, validated by service/application owners, and operational teams communicated and provided materials for how to use. | October 30, 2026 |
|  | Qualys Integration | Automates the synchronization of key CMDB attributes (asset owners, support groups, and SOX(Sarbanes-Oxley Act of 2002)-related flags) from ServiceNow to Qualys, eliminating manual data reconciliation between systems. This integration enables vulnerability scan data is consistently tied to the right owners and compliance context, accelerating remediation workflows and strengthening audit readiness. |  | A one-way integration from ServiceNow to Qualys is fully configured, tested, and live in production, with owner, support group, and SOX flag data automatically synchronized to Qualys on a defined schedule with no manual handoffs. *Assumes the required plug-in from Qualys is available. | September 30, 2026 |
|  | CMDB Governance | Establishes the data standards, certification processes, and compliance alignment needed to maintain a trustworthy CMDB over time. Strong governance enables configuration data remains accurate and current, enabling confident decision-making in change management, incident response, and regulatory compliance. |  | A data certification process for computers is defined and implemented, with end-to-end process flow documented, technical build released to production, dashboards available for tracking data certification completion, and training provided.. | September 30, 2026 |
|  |  |  |  | A data certification process for servers is defined and implemented, with end-to-end process flow documented, technical build released to production, dashboards available for tracking data certification completion, and training provided.. | September 30, 2026 |
|  |  |  |  | A data certification process for databases is defined and implemented , with end-to-end process flow documented, technical build released to production, dashboards available for tracking data certification completion, and training provided.. | October 30, 2026 |
|  |  |  |  | A data certification process for network devices is defined and implemented, with end-to-end process flow documented, technical build released to production, dashboards available for tracking data certification completion, and training provided.. | October 30, 2026 |
|  | Legacy Platform Rationalization | Drives a deliberate, structured transition from legacy platforms (iTeam, DISCO, Cherwell, AIM) to ServiceNow, reducing tool sprawl and operational risk. Consolidating capabilities into ServiceNow lowers long-term maintenance costs, reduces data silos, and positions PPL to retire redundant tooling with a clear, validated migration roadmap. |  | Gap analysis of functionality in iTeam, DISCO, Cherwell, and AIM compared to ServiceNow existing capabilities. The existing PPL documentation shall be reviewed and validated as part of the analysis. | August 31, 2026 |
|  |  |  |  | Migration plan delivered, including a prioritized list of functionality to be migrated and an actionable roadmap with timelines for completion. | September 30, 2026 |
|  |  |  |  | Execution of October efforts outlined in the migration plan delivered in 5.2. | October 30, 2026 |
|  | ITSM Product Management | Provides dedicated product ownership to enable PPL’s ServiceNow ITSM capabilities are strategically guided, backlog-prioritized, and continuously improved. Consistent product management accelerates value delivery, aligns ITSM development to business needs, and enables governance and cross-functional coordination keep pace with platform growth. |  | Product owner activities are fully executed for the period, including stakeholder engagements, active backlog prioritization in agile ceremonies, cross-functional coordination, and participation in governance and process improvement forums. | July 31, 2026 |
|  |  |  |  | Product owner activities are fully executed for the period, including stakeholder engagements, active backlog prioritization in agile ceremonies, cross-functional coordination, and participation in governance and process improvement forums. | August 31, 2026 |
|  |  |  |  | Product owner activities are fully executed for the period, including stakeholder engagements, active backlog prioritization in agile ceremonies, cross-functional coordination, and participation in governance and process improvement forums. | September 30, 2026 |
|  |  |  |  | Product owner activities are fully executed for the period, including stakeholder engagements, active backlog prioritization in agile ceremonies, cross-functional coordination, and participation in governance and process improvement forums. | October 30, 2026 |
|  | ATF Strategy | Defines a scalable, structured approach for adopting Automated Test Framework (ATF) across PPL’s ServiceNow platform. A clear ATF strategy reduces regression risk in future releases, improves deployment confidence, and lays the groundwork for faster, higher-quality platform changes as ServiceNow capabilities expand. |  | A published ATF implementation plan covers all production ServiceNow capabilities in use as of July 31st, including defined criteria for which capabilities require ATF coverage, a sequenced rollout timeline, and a reusable implementation approach that teams can apply consistently across capabilities. | October 30, 2026 |
|  | Platform Support | Provides a dedicated team of two (2) developers for BAU (Business as Usual) support and DevOps pipeline management for ServiceNow ITSM and CMDB modules, enabling the platform remains stable, current, and responsive to operational needs. Provides a dedicated team of four (4) developers for managing major enhancements for primarily focused on ITSM major enhancements (i.e. more than 40 hours of required effort). Resources may be leveraged for other platform major enhancements, so long as the priority level of the other enhancements are higher as determined by product ownership. Scope of enhancements to be defined during agile ceremonies (i.e. Sprint Planning). Reliable platform support protects service continuity, sustains team velocity, and allows production changes to be delivered with quality and predictability. |  | A time- and effort-tracking mechanism is operational, with all team members logging 40 hours of completed stories per week (adjusted for holidays/PTO), and sprint allocation reports available to stakeholders. | July 31, 2026 |
|  |  |  |  | Each team member delivers 40 hours of completed stories per sprint, with ongoing tracking confirming consistent allocation to BAU scope throughout the period. | August 31, 2026 |
|  |  |  |  | Each team member delivers 40 hours of completed stories per sprint, with ongoing tracking confirming consistent allocation to BAU scope throughout the period. | September 30, 2026 |
|  |  |  |  | Each team member delivers 40 hours of completed stories per sprint, with ongoing tracking confirming consistent allocation to BAU scope throughout the period. | October 30, 2026 |
| 9 | NERC-CIP ServiceNow Platform Strategy | Provides a leadership-ready strategy package evaluating the approach of a separate ServiceNow environment for managing NERC-CIP assets. Enable PPL to determine the go-forward solution for managing NERC-CIP assets in ServiceNow. | 9.1 | Evaluation completed of NERC-CIP ServiceNow Platform strategy of dual-instances with documented high-level considerations, pros and cons, risks, and dependencies. | September 30, 2026 |
|  |  |  | 9.2 | Executive-level NERC-CIP Platform Strategy package (e.g. PowerPoint, Word) that describes go-forward solution options, tradeoffs, and high-level implementation steps. | October 30, 2026 |

- Article 2 (Schedule), shall be deleted in its entirety and replaced with the following:

The targeted start date for this Change Order #6 is June 30, 2026 and be completed by October 30, 2026. Late start dates will retrospectively impact the scheduled end date of this assignment.

For all backlog / BAU related tasks, the capacity team (see 10. Platform Support in Article 1)  shall deliver against story points that the PPL ServiceNow Product team assigns and prioritizes, in accordance with the ServiceNow Governance procedures, from both PPL generated requirements and Accenture Managed Services requirements for ITSM features (i.e. workflow, catalog, etc.).

- Article 6 (Fees), first paragraph and invoicing table are hereby deleted and replaced with the following:

Contractor professional fees for the Services performed under this Change Order #6 are estimated to be $2,724,109 excluding travel and expenses (not to exceed $68,103 in expenses), based on a Change Order #6 start date of June 30, 2026, and a completion date of October 30, 2026.  The total Accenture professional fees for the Services performed will be $12,173,596 excluding travel and expenses (not to exceed $445,641.75 in expenses), based on a project start date of October 14, 2024, and a completion date of October 30, 2026.

Contractor will submit invoices, in accordance with the updated table below:

| Invoicing Month | Net Fees |
| --- | --- |
| October 2024 SOW | $113,077 |
| November 2024 SOW | $363,373 |
| December 2024 SOW | $305,729 |
| January 2025 SOW | $383,125 |
| January 2025 CO1 | $114,941 |
| February 2025 SOW | $381,327 |
| February 2025 CO1 | $114,941 |
| March 2025 SOW | $384,766 |
| March 2025 CO1 | $120,688 |
| April 2025 SOW | $306,165 |
| April 2025 CO1 | $126,435 |
| May 2025 SOW | $306,165 |
| May 2025 CO1 | $11,494 |
| May 2025 CO2 | $367,542 |
| June 2025 SOW | $305,566 |
| June 2025 CO2 | $140,196 |
| July 2025 SOW | $306,765 |
| July 2025 CO2 | $104,328 |
| August 2025 SOW | $301,937 |
| August 2025 CO2 | $95,256 |
| September 2025 SOW | $306,165 |
| September 2025 CO2 | $99,792 |
| October 2025 SOW | $304,368 |
| October 2025 CO2 | $104,328 |
| November 2025 SOW | $288,411 |
| November 2025 CO2 | $90,720 |
| November 2025 CO3 | $128,440 |
| December 2025 SOW | $246,971 |
| December 2025 CO2 | $104,328 |
| December 2025 CO3 | $193,200 |
| January 2026 CO4 | $464,707 |
| February 2026 CO4 | $422,461 |
| March 2026 CO4 | $464,707 |
| April 2026 CO5 | $533,780 |
| May 2026 CO5 | $509,517 |
| June 2026 CO5 | $533,775 |
| July 2026 CO6 | $448,900 |
| August 2026 CO6 | $726,037 |
| September 2026 CO6 | $774,586 |
| October 2026 CO6 | $774,586 |
| SOW Total Professional Fees | $4,603,910 |
| CO1 Total Professional Fees | $488,500 |
| CO2 Total Professional Fees | $1,106,490 |
| CO3 Total Professional Fees | $321,640 |
| CO4 Total Professional Fees | $1,351,875 |
| CO5 Total Professional Fees | $1,577,072 |
| CO6 Total Professional Fees | $2,724,109 |
| Total Professional Fees (inclusive of all COs) | $12,173,596 |

| Statement of Work |  |
| --- | --- |
| Statement of Work Professional Fees | $4,603,910 |
| SOW Not to Exceed Expenses | $230,196 |
| SOW Total (Fees + Estimated Expenses) | $4,834,106 |
| Change Order #1 |  |
| CO #1 Professional Fees | $488,500 |
| CO #1 Not to Exceed Expenses | $24,425 |
| CO #1 Total (Fees + Estimated Expenses) | $512,925 |
| Change Order #2 |  |
| CO #2 Professional Fees | $1,106,490 |
| CO #2 Not to Exceed Expenses | $55,324 |
| CO #2 Total (Fees + Estimated Expenses) | $1,161,814 |
| Change Order #3 |  |
| CO #3 Professional Fees | $321,640 |
| CO #3 Not to Exceed Expenses | $0 |
| CO #3 Total (Fees + Estimated Expenses) | $321,640 |
| Change Order #4 |  |
| CO #4 Professional Fees | $1,351,875 |
| CO #4 Not to Exceed Expenses | $67,593.75 |
| CO #4 Total (Fees + Estimated Expenses) | $1,419,468.75 |
| Change Order #5 |  |
| CO #5 Professional Fees | $1,577,072 |
| CO #5 Not to Exceed Expenses | $0 |
| CO #5 Total (Fees + Estimated Expenses) | $1,577,577 |
| Change Order #6 |  |
| CO #6 Professional Fees | $2,724,109 |
| CO #6 Not to Exceed Expenses | $68,103 |
| CO #6 Total (Fees + Estimated Expenses) | $2,792,212 |
| Total Fees (including all Change Orders) | $12,173,596 |
| Total Not to Exceed Expenses (including all Change Orders) | $445,641.75 |
| Total Fees + Expenses (including all Change Orders) | $12,619,237.75 |

IN WITNESS WHEREOF, the Parties hereto have executed this Change Order #6 as of the date first written above.

ACCENTURE INTERNATIONAL LIMITED		PPL SERVICES CORPORATION

by: 							by:

name: 							name: 	____________________

title: 	______________				title:    	____________________

date:						 	date: