## Slide 1
CO6 Deliverables - Team Focus
Deliverables, dates & where to focus · for Development + supporting roles
What we deliver, by when, and where to focus
Delivery window: Jul 1 - Oct 30, 2026 (tail of PI-2 + all of PI-3)
Manuel Vazquez - Scrum Master, CMDB-CSDM
Planning view - dates & scope firm up at PI-3 planning.

## Slide 2
Deliverables & Dates
Ordered by due date - soonest first
PPL CMDB-CSDM | CO6 Deliverables | Team Focus - Jul 10, 2026
Deliverable | Due | PI | What we focus on
CMDB Governance | Jul 31 | PI-2 | Data dictionary incl. Databases; Data Certification for ALL CI classes + KB articles; ESS-02; SOX BA review
CI Coverage - Computers | Jul 31 -> Sep 30 | PI-2/3 | SCCM/Discovery precedence + bulk life-cycle; 90% of devices managed
CI Coverage - Servers | Jul 31 -> Oct 30 | PI-2/3 | SCCM/Discovery precedence; enhanced DB Discovery (MS-SQL/Oracle); 90% of non-NERC-CIP servers
Network Gear Discovery | Aug 31 -> Oct 30 | PI-3 | Credentials / SNMP (excl. OT); discovery schedules; mandatory attributes; 90% coverage, owner-validated
Service Mapping | Aug 31 -> Oct 30 | PI-3 | End-to-end maps for 10 priority apps down to infra CIs; owner-validated; consumable in ServiceNow
Legacy Platform Rationalization | Aug 31 -> Oct 30 | PI-3 | Analysis + migration plan: iTeam -> DISCO / Cherwell -> AIM
Qualys Integration | Oct 27 | PI-3 | One-way Qualys -> ServiceNow feed; configured, tested, deployed to PROD
ATF Strategy | Oct 31 | PI-3 | Plan for Automated Test Framework rollout across in-prod ServiceNow capabilities
ITSM Product Management | Monthly | PI-2/3 | Separate ITSM lane (Product Owner role) - outside core CMDB delivery
Platform Support | Monthly | PI-3 | Standing BAU / DevOps support - ongoing capacity, not a finite deliverable
Ordered by due date. Bottom two are standing PO / BAU lanes - separate from core CMDB delivery. Planning view - dates & scope firm up at PI-3 planning.

## Slide 3
Deliverable Detail
Acceptance criteria (with target dates) and scope · 1 of 4
PPL CMDB-CSDM | CO6 Deliverables | Team Focus - Jul 10, 2026
CMDB Governance Jul 31
Done when (acceptance)
By Jul 31
• Data dictionary for all CI classes, incl. Databases
• Data Certification live for ALL CI classes + KB articles
• ESS-02 alignment with Cyber Security & Compliance
• SOX Business Apps identified with update-rights controls
Scope
In scope
• Servers, Computers, Business Apps, Databases data dictionary
• Data Cert: process, intake, pilot, KB articles
• ESS-02 alignment; SOX BA identification + access governance
Out of scope
• NERC / CIP compliance indicators (separate stream)
CI Coverage - Computers Jul 31 -> Sep 30
Done when (acceptance)
By Jul 31
• SCCM/Discovery precedence reconciled & applied
• Bulk Life Cycle Stage & Status updates applied
By Sep 30
• 90% of computer devices managed (validated)
Scope
In scope
• Physical + virtual computers
• Precedence; bulk life-cycle; coverage measurement
Out of scope
• Life-cycle process definition (owned by Asset Management)

## Slide 4
Deliverable Detail
Acceptance criteria (with target dates) and scope · 2 of 4
PPL CMDB-CSDM | CO6 Deliverables | Team Focus - Jul 10, 2026
CI Coverage - Servers Jul 31 -> Oct 30
Done when (acceptance)
By Jul 31
• SCCM/Discovery precedence reconciled & applied
• Enhanced Discovery for MS-SQL & Oracle databases
By Oct 30
• 90% of non-NERC-CIP servers discovered
Scope
In scope
• Server precedence; MS-SQL / Oracle discovery; coverage measurement
Out of scope
• SOX indicators (manually maintained - excluded)
• NERC / CIP servers (excluded from the 90% target)
Network Gear Discovery Aug 31 -> Oct 30
Done when (acceptance)
By Aug 31
• Credentials configured & validated (excl. OT)
• Discovery schedules active
By Sep 30
• Mandatory attributes populated
By Oct 30
• 90% coverage, business-owner validated
Scope
In scope
• Network gear: credentials / SNMP, schedules, attributes, coverage
Out of scope
• OT (operational technology) devices

## Slide 5
Deliverable Detail
Acceptance criteria (with target dates) and scope · 3 of 4
PPL CMDB-CSDM | CO6 Deliverables | Team Focus - Jul 10, 2026
Service Mapping Aug 31 -> Oct 30
Done when (acceptance)
By Aug 31
• Initial maps for priority business apps
By Oct 30
• All 10 priority apps mapped down to infra CIs
• Owner-validated & consumable in ServiceNow
Scope
In scope
• The 10 priority apps; app -> infra mapping; owner validation
Out of scope
• Apps beyond the 10 priority set
Legacy Platform Rationalization Aug 31 -> Oct 30
Done when (acceptance)
By Aug 31
• Analysis: iTeam -> DISCO / Cherwell -> AIM
By Oct 30
• Migration plan (Cherwell / AIM if applicable)
Scope
In scope
• iTeam import / migration; analysis of DISCO / Cherwell / AIM
Out of scope
• Cherwell / AIM execution unless confirmed at PI-3 planning

## Slide 6
Deliverable Detail
Acceptance criteria (with target dates) and scope · 4 of 4
PPL CMDB-CSDM | CO6 Deliverables | Team Focus - Jul 10, 2026
Qualys Integration Oct 27
Done when (acceptance)
By Oct 27
• One-way Qualys -> ServiceNow configured & tested
• Deployed to PROD
• Vulnerability data ingests on schedule, no data loss
Scope
In scope
• One-way Qualys -> ServiceNow feed: config, test, PROD deploy
Out of scope
• Two-way sync; other integrations (Tanium was the alternative)
ATF Strategy Oct 31
Done when (acceptance)
By Oct 31
• Rollout plan: selection criteria, timeline, and approach
Scope
In scope
• Strategy / plan for ATF rollout (analysis deliverable)
Out of scope
• Building / implementing ATF (this is the plan, not the rollout)

## Slide 7
Supporting Lanes
PO / BAU capacity - separate from core CMDB delivery
PPL CMDB-CSDM | CO6 Deliverables | Team Focus - Jul 10, 2026
ITSM Product Management
Monthly · PI-2 / PI-3
• ITSM Product Owner role: stakeholder management, backlog prioritization, agile ceremonies, governance
• Separate ITSM lane - outside core CMDB delivery
• No stories; owner TBD
Platform Support
Monthly · PI-3
• Dedicated BAU / DevOps team; ~40 hrs of stories per week per member; per-sprint time tracking
• Ongoing capacity, not a finite deliverable
• Team size TBD
These are staffing / capacity decisions, not backlog - flagged so they stay on the radar.

## Slide 8
Timeline - Where It Lands
Tail of PI-2 + all of PI-3 · staged monthly acceptance
PPL CMDB-CSDM | CO6 Deliverables | Team Focus - Jul 10, 2026
Jun
Jul
Aug
Sep
Oct
Nov
Windows
Delivery window Jul 1 - Oct 30
PI-2 (-> Aug 4)
PI-3 Aug 5 - Oct 27
When | What's due | Lands in
Jul 31 | CMDB Governance (data dictionary incl. Databases; Data Cert all CI classes; ESS-02; SOX) · CI Coverage foundation (Computers & Servers precedence) | PI-2 Iter 2.5 / 2.6 (IP)
Aug 31 | Network Gear (creds & schedules) · Service Mapping (initial maps) · Legacy Platform (analysis) - staged | PI-3
Sep 30 | CI Coverage - Computers 90% managed · Network Gear mandatory attributes | PI-3
Oct 27 | Qualys -> ServiceNow live in PROD | PI-3
Oct 30 | CI Coverage - Servers 90% · Network Gear 90% · Service Mapping (10 apps) · Legacy Platform (migration plan) | PI-3
Oct 31 | ATF Strategy (rollout plan) | PI-3
Ongoing | ITSM Product Management & Platform Support - monthly | PI-2 tail -> PI-3

## Slide 9
Where to Focus
Priorities for Development + supporting roles
PPL CMDB-CSDM | CO6 Deliverables | Team Focus - Jul 10, 2026
Focus first: the Jul 31 items.
CMDB Governance and CI Coverage foundation (Computers & Servers precedence) are due first and land in PI-2 - keep these moving now.
Biggest PI-3 build: Discovery + Mapping.
Network Gear, Service Mapping and the 90% coverage targets (Sep 30 / Oct 30) are the bulk of the work - discovery, credentials, and app-owner validation.
Unblock Qualys early.
One-way feed to PROD by Oct 27 - the plugin blocker needs clearing before the build can finish.
New to plan at PI-3 planning.
Legacy Platform Rationalization and ATF Strategy are greenfield - no stories yet; we scope and staff these at planning.
Supporting lanes stand up separately.
ITSM Product Management and Platform Support are PO / BAU capacity, not core CMDB dev - flagged so they're on the radar.
Questions?
Jordan Yung is the CO6 SME; Joe Dames owns governance scope. Flag anything unclear to Manny.