## Slide 1
CO6 Deliverables - Team Focus
Per-SOW deliverables: description, acceptance criteria & target dates
9 deliverables, straight from the CO6 SOW
Delivery window: Jul 1 - Oct 30, 2026 (tail of PI-2 + all of PI-3)
Manuel Vazquez - Scrum Master, CMDB-CSDM
Sourced from the authoritative CO6 v3. Dates align to CO6 gates (PI-3 ends Oct 27; final gates Oct 30).

## Slide 2
Deliverables & Dates
At-a-glance - ordered by due date (SOW detail follows)
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Deliverable | Due | PI | What we focus on
Network Gear Discovery | Aug 31 -> Oct 30 | PI-3 | Automated network-device discovery into the CMDB; 90% coverage, business-owner validated
Service Mapping | Aug 31 -> Oct 30 | PI-3 | 15 Silver-tier + Gold-tier maps; >=75% business-service inventory; app->infra and service->app layers
Legacy Platform Rationalization | Aug 31 -> Oct 30 | PI-3 | Gap analysis of iTeam / DISCO / Cherwell / AIM; migration plan; October execution
CMDB Governance | Sep 30 -> Oct 30 | PI-3 | Data certification (process + PROD + dashboards + training) for Computers, Servers, Databases, Network Devices
Qualys Integration | Sep 30 | PI-3 | One-way ServiceNow -> Qualys sync of owner, support group & SOX flag, live in PROD
NERC-CIP Platform Strategy | Sep 30 -> Oct 30 | PI-3 | Dual-instance evaluation + executive strategy package
ATF Strategy | Oct 30 | PI-3 | Plan for Automated Test Framework rollout across in-prod ServiceNow capabilities
ITSM Product Management | Monthly | PI-2/3 | Dedicated ITSM Product Owner - backlog prioritization, ceremonies, governance
Platform Support | Monthly | PI-2/3 | 2 BAU / DevOps + 4 major-enhancement developers; 40 hrs of stories per week
At-a-glance summary (date-ordered). Per-deliverable SOW detail follows. Bottom two are standing PO / BAU lanes. Sourced from the authoritative CO6 v3. Dates align to CO6 gates (PI-3 ends Oct 27; final gates Oct 30).

## Slide 3
Deliverable Detail
SOW: description, acceptance criteria & target dates
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Deliverable 1 - Network Gear Discovery Aug 31 - Oct 30, 2026
Description Automated, real-time discovery of network devices to populate and maintain the CMDB. Eliminates manual data collection, reduces configuration drift, and provides the foundation for incident impact analysis - improving response times and reducing outage risk across PPL's network.
Acceptance criteria | Targeted due date
• Network device types (routers, switches, firewalls, load balancers, WAPs, network controllers) actively discovered using validated credentials - no failed authentications on target devices • Discovery schedules running on defined intervals; CMDB records auto-updated without manual intervention within each cycle | Aug 31, 2026
All discoverable mandatory CMDB attributes for network devices (per CMDB governance) fully populated via discovery - no mandatory fields blank | Sep 30, 2026
90%+ of expected network-device inventory represented in the CMDB, validated against authoritative data from business owners | Oct 30, 2026

## Slide 4
Deliverable Detail
SOW: description, acceptance criteria & target dates
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Deliverable 2 - Service Mapping Aug 31 - Oct 30, 2026 (phased)
Description End-to-end visibility of business services and their infrastructure dependencies in ServiceNow. Accurate maps enable faster incident triage, reliable change-impact assessment, and better outage prioritization - reducing MTTR and unintended disruptions.
Acceptance criteria | Targeted due date
• 15 priority (Silver-tier) business-app maps built - full dependencies from business application to infrastructure CIs; owner-validated; ops teams enabled • >=75% of identified business-service inventory represented in the CMDB, owner-validated (*assumes business services defined prior to start) | Aug 31, 2026
• 15 Silver-tier maps (business application -> infrastructure): additional validation pass • Gold-tier maps (business service -> business application) built, owner-validated, teams enabled | Sep 30, 2026
• Remaining Contractor-managed Silver-tier maps (business application -> infrastructure) built and validated • Silver-tier maps (business service -> business application) built, owner-validated, teams enabled | Oct 30, 2026

## Slide 5
Deliverable Detail
SOW: description, acceptance criteria & target dates
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Deliverable 4 - CMDB Governance Sep 30 - Oct 30, 2026
Description Establishes the data standards, certification processes, and compliance alignment to keep the CMDB trustworthy - accurate, current configuration data for change, incident, and regulatory decisions.
Acceptance criteria | Targeted due date
• Data certification for Computers - process flow documented, technical build released to PROD, tracking dashboards live, training delivered • Data certification for Servers - same (process, PROD, dashboards, training) | Sep 30, 2026
• Data certification for Databases - same (process, PROD, dashboards, training) • Data certification for Network Devices - same (process, PROD, dashboards, training) | Oct 30, 2026

## Slide 6
Deliverable Detail
SOW: description, acceptance criteria & target dates
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Deliverable 5 - Legacy Platform Rationalization Aug 31 - Oct 30, 2026
Description A deliberate, structured transition from legacy platforms (iTeam, DISCO, Cherwell, AIM) into ServiceNow - reducing tool sprawl and maintenance cost and enabling retirement of redundant tooling with a validated roadmap.
Acceptance criteria | Targeted due date
Gap analysis of functionality in iTeam, DISCO, Cherwell, and AIM vs. ServiceNow existing capabilities; existing PPL documentation reviewed and validated | Aug 31, 2026
Migration plan delivered - prioritized list of functionality to migrate + an actionable roadmap with timelines | Sep 30, 2026
Execution of the October efforts outlined in the migration plan (per 5.2) | Oct 30, 2026

## Slide 7
Deliverable Detail
SOW: description, acceptance criteria & target dates
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Deliverable 9 - NERC-CIP ServiceNow Platform Strategy Sep 30 - Oct 30, 2026
Description A leadership-ready strategy package evaluating a separate ServiceNow environment for NERC-CIP assets - enabling PPL to decide the go-forward solution for managing NERC-CIP assets in ServiceNow.
Acceptance criteria | Targeted due date
Evaluation of the dual-instance NERC-CIP platform strategy completed - documented high-level considerations, pros and cons, risks, and dependencies | Sep 30, 2026
Executive-level NERC-CIP Platform Strategy package (e.g. PowerPoint / Word) describing go-forward solution options, tradeoffs, and high-level implementation steps | Oct 30, 2026

## Slide 8
Deliverable Detail
SOW: description, acceptance criteria & target dates
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Deliverable 3 - Qualys Integration Sep 30, 2026
Description Automates synchronization of key CMDB attributes (asset owners, support groups, SOX flags) from ServiceNow to Qualys, eliminating manual reconciliation - so vulnerability scan data stays tied to the right owners and compliance context.
Acceptance criteria | Targeted due date
One-way ServiceNow -> Qualys integration fully configured, tested, and live in production - owner, support group & SOX flag data auto-synchronized to Qualys on a defined schedule, no manual handoffs (*assumes the required Qualys plug-in is available) | Sep 30, 2026
Deliverable 7 - ATF Strategy Oct 30, 2026
Description A scalable, structured approach for adopting the Automated Test Framework (ATF) across PPL's ServiceNow platform - reducing regression risk and improving deployment confidence as capabilities expand.
Acceptance criteria | Targeted due date
Published ATF implementation plan covering all production ServiceNow capabilities in use as of Jul 31 - defined criteria for which capabilities require ATF coverage, a sequenced rollout timeline, and a reusable implementation approach applied consistently across capabilities | Oct 30, 2026

## Slide 9
Deliverable Detail
SOW: description, acceptance criteria & target dates
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Deliverable 6 - ITSM Product Management Monthly, Jul 31 - Oct 30, 2026
Description Dedicated product ownership so PPL's ServiceNow ITSM capabilities are strategically guided, backlog-prioritized, and continuously improved - keeping governance and cross-functional coordination in step with platform growth.
Acceptance criteria | Targeted due date
Product owner activities fully executed for the period - stakeholder engagements, active backlog prioritization in agile ceremonies, cross-functional coordination, and participation in governance / process-improvement forums | Monthly: Jul 31 -> Oct 30, 2026
Deliverable 8 - Platform Support Monthly, Jul 31 - Oct 30, 2026
Description A dedicated team of 2 developers for BAU support and DevOps pipeline management (ServiceNow ITSM & CMDB), plus 4 developers for major enhancements (primarily ITSM, >40 hrs effort). Enhancement priority set by product ownership, scoped in agile ceremonies.
Acceptance criteria | Targeted due date
Time- and effort-tracking mechanism operational - all team members logging 40 hours of completed stories per week (holiday/PTO-adjusted); sprint allocation reports available to stakeholders | Jul 31, 2026
Each team member delivers 40 hours of completed stories per sprint, with ongoing tracking confirming consistent allocation to BAU scope throughout the period | Monthly: Aug 31 -> Oct 30, 2026

## Slide 10
Timeline - Where It Lands
Tail of PI-2 + all of PI-3 · staged monthly acceptance
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Jun
Jul
Aug
Sep
Oct
Nov
Windows
Delivery window Jul 1 - Oct 30
PI-2 (-> Aug 4)
PI-3 Aug 5 - Oct 27
When | What's due | Lands in
Jul 31 | ITSM Product Management & Platform Support monthly lanes begin; Platform time/effort tracking operational | PI-2 tail
Aug 31 | Network Gear (creds + schedules) · Service Mapping (15 Silver + >=75% inventory) · Legacy (4-platform gap analysis) | PI-3
Sep 30 | Qualys live in PROD · Governance data cert (Computers, Servers) · Network attrs · Service Mapping (Gold + Silver pass) · NERC-CIP evaluation · Legacy (migration plan) | PI-3
Oct 27 | PI-3 ends | -
Oct 30 | Governance data cert (Databases, Network) · Network 90% · Service Mapping (remaining Silver + service->app) · ATF plan · NERC-CIP exec package · Legacy (Oct execution) | IP / post-PI-3

## Slide 11
Where to Focus
Priorities for Development + supporting roles
PPL CMDB-CSDM | CO6 Deliverables (per SOW v3) | Team Focus - Jul 12, 2026
Two lanes start Jul 31.
ITSM Product Management and Platform Support (2 BAU + 4 enhancement devs) begin monthly - stand up tracking and capacity first.
Aug 31 is the first big gate.
Network Gear discovery live, 15 Silver-tier service maps + >=75% inventory, and the 4-platform Legacy gap analysis all land Aug 31.
Sep 30 is the heaviest gate.
Qualys live in PROD, data certification for Computers & Servers, network attributes, Gold-tier maps, and the NERC-CIP evaluation.
Qualys is ServiceNow -> Qualys.
It syncs owner, support group and SOX flag TO Qualys (not vulnerability ingestion) - confirm the required Qualys plug-in is available.
Service Mapping is the biggest build.
15 Silver + Gold tiers, >=75% inventory, two mapping layers - app-owner validation gates it; assumes business services are pre-defined.
Questions?
Jordan Yung is the CO6 SME; Joe Dames owns governance scope. Flag anything unclear to Manny.