## Slide 1
CMDB-CSDM Delivery Status
Weekly Leadership Report
PI-2 · Iteration 2.5 (Jul 8 - Jul 21)
Week of July 6, 2026
Manuel Vazquez - Scrum Master, CMDB-CSDM

## Slide 2
How to Read This Report
Sprint 2.4 close-out (Jul 7). Board state: Jul 8 ADO snapshot. Sprint 2.5 scope TBD — work items to be added once planning is confirmed. CO6 pending execution as of Jul 8.
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
Three progress lenses, refreshed every week:
PI over PI
Are we delivering more value each Program Increment?
Iteration over Iteration
Is each 2-week sprint building on the last?
Week over Week
What concretely moved since the last report?
Status legend:
GREEN
On track
AMBER
Progressing, with watch items
RED
Blocked / needs intervention

## Slide 3
Executive Summary
Iteration 2.5 (Jul 8 - Jul 21)
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
CO5 FOCUS - CO6 PENDING; DEV FREEZE ACTIVE
Delivery momentum is real - SOX BA review done, Airlift exports complete, CI retirement executed - but the CO5 acceptance gate (Data Dictionary CCB approval Jul 21) is 13 days out. Dev code freeze (Jul 4-18) is now active, constraining Sprint 2.5 delivery capacity.
Wins this period
+ Sprint 2.4 closed (Jul 7); SOX BA review, Airlift exports (PA/KY VMware + PA Physical), bulk CI retirement, NowAssist Duplicate CIs skill, IRE behaviour review spike.
+ SOX Business Apps (1480105) Closed - CO5 D1 acceptance evidence confirmed; Airlift inventory export cluster complete.
+ Data Dictionaries (Servers/Computers/Biz Apps/DB) delivered to Validation - CCB review Jul 7-20, approval target Jul 21.
Needs leadership attention
! CO6 pending execution - Execute CO6 this week. Confirm with Christian / Aaron Simeon — effective date is already Jun 30; delay only extends holdback exposure.
! Dev code freeze Jul 4-18 - Awareness; prioritize validation and documentation work in 2.5 through Jul 18.
! 3 audit dashboard spikes incomplete - Prioritize spike completion in 2.5; required before 90%-coverage acceptance stories can be created.

## Slide 4
CO5 Deliverables Scorecard
The 3 contractual deliverables · sub-items = moving / in-scope
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
D1 Governance - Data Dictionary, Data Cert, ESS-02, SOX, CCB
8
sub-items in scope
8 moving · 0 stuck
SOX BA review (1480105) Closed - D1 acceptance evidence confirmed; 4 Data Dictionaries in Validation (CCB review Jul 7-20, approval Jul 21); ESS-02 (1480102) and Monthly CCB (1480107) Ready DoR; Data Cert pilot (1480099) Ready DoR; code freeze gates ESS-02/CCB until Jul 18
D2 Automated Data Ingestion - Computers / Servers / Databases
3
sub-items in scope
3 moving · 0 stuck
Airlift exports (PA/KY VMware + PA Physical) Closed; imports in Validation; 3 audit-dashboard spikes (Servers/DB/Computer) carried from 2.4 Active - did not close; no formal 90%-measurement acceptance story
D3 Other Enhancement - Evaluate Qualys Integration
2
sub-items in scope
1 moving · 1 stuck
Part 1 (1428703) still Active - did not close in 2.4; dev freeze further delays; Part 2 (1428704) status unconfirmed (G4); CO5 bar = evaluate + document; CO6 (Sep 30) delivers full one-way PROD integration (ServiceNow → Qualys)

## Slide 5
Progress: PI over PI
Are we delivering more value each Program Increment?
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
PI-2 ACTIVE
May 13 - Aug 4, 2026
Iteration 2.5 of 6
Sprint 2.4 closed Jul 7; CO5 acceptance gate = Data Dictionary CCB approval Jul 21
PI-3 PLANNING
Aug 5 - Oct 27, 2026
Planning Jul 22 - Aug 4
CO6 gap closure (if signed), NowAssist rollout, Qualys full integration, CI Cert extended scope
PENDING DATA
PI-over-PI comparison metric
Comparison basis (objectives completed / business value delivered / stories accepted per PI) to be fixed before PI-3 begins. Only PI-2 has live data today - not yet ready for relevant data.
Note: Only PI-2 has live data today. PI-over-PI comparison populates once PI-3 begins (planning during the PI-2 IP iteration, Jul 22 - Aug 4).

## Slide 6
Progress: Iteration over Iteration
Is each 2-week sprint building on the last?
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
Sprint 2.3
Jun 10 - 23 · COMPLETED
Deploy & scale
- Data Certification dashboard -> PROD (6/23)
- NowAssist accepted: prerequisites, plugin activation, CI summarization
- 11 pts accepted; 23 pts delivered into validation
Sprint 2.4
Jun 24 - Jul 7 · COMPLETED
CO5 acceptance push
- 9 items / 10 pts accepted: SOX BA review, Airlift exports, CI retirement, NowAssist Duplicate CIs
- Data Dictionaries (Servers/Computers/Biz Apps/DB) delivered to Validation
- 12 items / 18 pts in validation - largest carry-over pipeline of PI-2
- 3 audit dashboard spikes carried to 2.5 Active (Servers/DB/Computer)
Sprint 2.5
Jul 8 - Jul 21 · ACTIVE
CO5 acceptance gate + code freeze navigation
- Scope TBD - 2.5 work items to be confirmed; planning in progress
- Dev code freeze Jul 4-18 constrains first 10 days of sprint
- Data Dictionary CCB approval target Jul 21 (sprint end)
- 3 audit spikes (Servers/DB/Computer) carried from 2.4
Sprint 2.4 delivery - derived from the Jul 8 ADO board (sprint close-out)
On board
~38 items / ~48 pts
Accepted / Done
9 items - 10 pts
Delivered, in validation
12 items - 18 pts
Active / not started
~17 items
Derived from the Jul 8 ADO board (Sprint 2.4 close-out). Board grew during sprint with retirement cluster and Airlift imports added mid-sprint. 18 pts in validation carry into Sprint 2.5 pending acceptance.

## Slide 7
Progress: Week over Week
What changed in status since the last report?
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
Sprint 2.4 closed Jul 7. Reporting continues on the CO5 contractual deliverable frame. Week-over-week deltas reflect movement since the Jun 29 report.
Delivered this period (Sprint 2.4 close-out)
On board
~38 items / ~48 pts
Accepted / Done
9 items - 10 pts
Delivered, in validation
12 items - 18 pts
Active / not started
~17 items
Key moves
+ Sprint 2.4 closed (Jul 7: SOX BA review, Airlift exports (PA/KY VMware + PA Physical), bulk CI retirement, NowAssist Duplicate CIs, IRE review spike.
+ SOX Business Apps (1480105) Closed - CO5 D1 acceptance evidence confirmed.
+ Data Dictionaries (Servers/Computers/Biz Apps/DB) delivered to Validation - CCB review Jul 7-20, approval target Jul 21.
+ 12 items / 18 pts in validation entering Sprint 2.5 - largest carry-over pipeline of PI-2.
Newly closed: SOX BA review · Airlift exports · CI retirement execution · Newly carried to 2.5: 3 audit spikes (Servers/DB/Computer)

## Slide 8
CO5 Deliverable 1 - Governance
Status and detail by deliverable
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
AMBER
Data Dictionaries (Servers/Computers/Biz Apps/DB)
All 4 dictionaries in Validation (1480088/090/097/098) - CCB customer review Jul 7-20, approval target Jul 21 (monthly CCB). Databases closes G1 at artifact level.
GREEN
SOX + Data Certification
SOX BA review (1480105) Closed - CO5 D1 acceptance evidence confirmed. Data Cert pilot (1480099) Ready DoR; dashboard in PROD since 6/23.
AMBER
ESS-02 / Monthly CCB
ESS-02 alignment (1480102) and Monthly CCB (1480107) remain Ready DoR - not started; dev-dependent work gated by code freeze (lifts Jul 18). CCB story closes G5.

## Slide 9
CO5 Deliverables 2 & 3 - Data Ingestion + Qualys
Status and detail by deliverable
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
AMBER
Data Ingestion - Airlift inventory + SCCM/Discovery precedence
Airlift exports (PA/KY VMware + PA Physical) Closed; imports (1487867/868/869) in Validation. Retirement: execute Closed (1487878), validate Active (1487872). SCCM/Discovery precedence reported complete.
AMBER
90% Coverage (Computers G2 / Servers G3 / DB)
3 audit-dashboard spikes (1480112 Servers, 1480113 DB, 1480114 Computer) carried from 2.4 Active - did not close in sprint. BA spike (1480111) in Validation. No formal 90%-measurement acceptance story yet.
AMBER
Qualys Integration (Other Enhancement)
Part 1 (1428703) still Active - did not close in 2.4; dev freeze (Jul 4-18) further delays. Part 2 (1428704) status unconfirmed (G4). CO5 bar = evaluate + document. CO6 (pending signature) delivers full one-way PROD integration (ServiceNow → Qualys) by Sep 30.

## Slide 10
Key Milestones & Upcoming Dates
CO5 acceptance critical path
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
Jul 4-18
Dev code freeze — ACTIVE NOW; constrains Sprint 2.5 delivery through Jul 18
Jul 7
Sprint 2.4 end ✓ — 9 items / 10 pts accepted; 12 items / 18 pts to validation
Jul 8
Sprint 2.5 start — CO5 acceptance gate; Data Dictionary CCB push
Jul 18
Dev code freeze lifts — ESS-02 / CCB / Qualys work can resume
Jul 18-Aug 15
Test code freeze — overlaps Sprint 2.5 tail and IP iteration
Jul 21
Data Dictionary CCB approval (monthly CCB) — critical CO5 D1 gate; Sprint 2.5 end
Jul 22-Aug 4
IP Iteration — PI-3 planning begins
Aug 5
PI-3 begins

## Slide 11
Risks & Leadership Asks
Where we need help to stay on track
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
Risk | Severity | Detail | Ask of Leadership
CO6 pending execution | HIGH | CO6 unsigned as of Jul 8; signature expected this week. Effective Jun 30 retroactively when signed. $2.7M, 9 workstreams through Oct 30: Network Discovery, Service Mapping, Qualys PROD (Sep 30), CMDB Governance (Data Cert expanded), Legacy Rationalization, ITSM PO, ATF Strategy, Platform Support, NERC-CIP Strategy. $533,775 June holdback stands until signed. | Execute CO6 this week. Confirm with Christian / Aaron Simeon — effective date is already Jun 30; delay only extends holdback exposure.
Dev code freeze Jul 4-18 | HIGH | Freeze is currently active - spans first 10 days of Sprint 2.5. Dev-dependent CO5 items (ESS-02, CCB story, Qualys Part 1) cannot land until Jul 18. | Awareness; prioritize validation and documentation work in 2.5 through Jul 18.
3 audit dashboard spikes incomplete | MEDIUM | Servers (1480112), Database (1480113), Computer (1480114) audit spikes carried into 2.5 Active - did not close in 2.4. G2/G3 coverage measurement evidence incomplete. | Prioritize spike completion in 2.5; required before 90%-coverage acceptance stories can be created.
90% coverage acceptance gap | MEDIUM | No formal 90%-measurement acceptance story for Computers (G2) or Servers (G3). Audit spikes must complete first; stories must then be created and accepted. | Endorse creating coverage-measurement acceptance stories once spikes close.
Deprioritized streams stranded | LOW | Service Mapping, Network Discovery, and NowAssist phases 2-5 remain paused. Test freeze (Jul 18-Aug 15) further limits resumption window. | Confirm resumption plan after CO5 acceptance; sequence around test freeze.

## Slide 12
What's Next
CO5 acceptance, CO6 gap closure, and resuming paused streams
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
Execute CO6 this week (effective Jun 30 retroactively)
Secure Data Dictionary CCB approval Jul 21 — critical CO5 D1 gate; validation window Jul 7-20.
Complete 3 audit dashboard spikes (Servers/DB/Computer) in 2.5 — prerequisite for G2/G3 acceptance stories.
Progress ESS-02 (1480102) and Monthly CCB (1480107) off Ready DoR — code freeze lifts Jul 18.
Confirm Qualys Part 1 (1428703) path to completion; CO6 delivers full PROD integration by Sep 30.
Begin CO6 workstream onboarding: Network Discovery, Service Mapping, ITSM PO, Platform Support, Legacy Rationalization.

## Slide 13
Appendix
Story-level detail
PPL CMDB-CSDM | PI-2 | Week of July 8, 2026
Full traceability is maintained in the team's working notes:
- CO5 deliverable traceability: co5-deliverable-tracking.md
- Objectives -> Features -> Stories: PI-2/pi2-objectives-features-stories.md
- Activity by Iteration (2.1 - 2.4): PI-2/pi2-iteration-activity.md
- Program Backlog Review notes: PI-2/Program-Backlog-Review/
This deck is regenerated weekly from build_status_deck.py.