PPL CMDB-CSDM — PI-3 Data Certification

Feature 1517029 — Certify Computers — CMDB Data Certification

DRAFT · 2026-07-27  ·  CO6 Obj 3 — Expand CI Data Certification Across All Major Classes  ·  Sprint 3.2 (build start); process-flow doc 3.1  ·  CO6 due 2026-09-30

Feature 1517029 — Stories & Dependencies

Certify Computers — CMDB Data Certification

Sprint 3.2 (build) · process-flow doc starts 3.1 · CO6 due Sep 30 · Owner: M. Vazquez

Status: REFERENCE / DRAFT — Manuel creates the real items in ADO under Feature 1517029 and reconciles IDs back here (ADO authoritative). Per definition-of-ready, create stories from the Feature "+" link, never standalone.  See PI-3/pi3-data-certification-feature-breakdown for the full feature-level breakdown and the PI-2 BA pilot pattern these stories clone.

Sprint reconciliation note (raise at Sprint Planning)

ADO records Feature 1517029's start as Sprint 3.2 (Aug 19); the PI-3/pi3-data-certification-feature-breakdown shapes the feature as 3.1 → 3.4. The reconciliation: the test code freeze runs through Aug 15 (mid-3.1), so no PROD deployment is possible early — the feature's *build* work correctly starts in 3.2. The only 3.1 work is doc-only process-flow definition (CC-1) off the 1480114 gap plan, which needs no deployment. Everything requiring a PROD change is sequenced 3.2+.

CO6 Acceptance Criteria this feature delivers (Sep 30)

From PI-3/pi3-objectives — Obj 3 (CO6 §4), Sep 30 gate:

*Data certification process for Computers: end-to-end process documented, technical build to PROD, dashboards live, training delivered.*

"Certified" = all four artifacts present for the Computer class:

| Artifact | Delivered by |
| --- | --- |
| Documented process flow | CC-1 |
| Technical build in PROD | CC-2 |
| Tracking dashboard live | CC-3 |
| Certification cycle executed + monitored | CC-4 |
| Training delivered | CC-5 |

ADO item reconciliation note

This feature clones the PI-2 Business-Application certification pilot pattern; no net-new *process* is invented. Reusable story shapes to clone per class (from the feature breakdown):

| PI-2 pilot item | Shape it provides | Clones to |
| --- | --- | --- |
| 1480114 | Computer audit-dashboard scope + gap-remediation plan (anchor) | Input to CC-1 (see DEP-1) |
| 1402962 | Kick-off / training | CC-5 |
| 1402976 | Execute certification policies | CC-2 / CC-4 |
| 1402980 | Monitor completeness | CC-4 |
| 1402984 | Office hours | CC-5 |
| 1402985 | Process feedback | optional CC-6 |
| 1402727 | Dashboard | CC-3 |

Stories CC-1 through CC-5 are net-new for the Computer class — created from the pilot shapes above, re-scoped from Business Application to cmdb_ci_computer.

Stories (5)

CC-1 · [User Story] Document the Computer Data Certification process flow

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517029 |
| Sprint | 3.1 (doc-only — no PROD dependency) |
| Owner | Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones the BA pilot process definition, re-scoped to Computer |
| Depends on | DEP-1 (1480114 gap plan), DEP-5 (Class Manager) |
| Tags | Data-Certification Computer CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the end-to-end Computer data-certification process documented — trigger, attestation steps, roles, escalation, and remediation path — built off the 1480114 gap-remediation plan,

So that the certification campaign for the Computer class runs on an agreed, repeatable workflow before any PROD configuration is built.

Acceptance criteria:

☐  Process flow diagram covers the full cycle: campaign trigger → owner attestation → gap identification → remediation → re-attestation → sign-off

☐  Roles defined at each step (CI Owner, Technical Owner Group, Support Group, Process Owner) using the delivered Data Dictionary field mappings (managed_by, managed_by_group, support_group)

☐  Attested attribute set for Computer confirmed against the delivered dictionary (9 managed attributes) and the 1480114 gap plan — no attribute drift between the two

☐  Escalation and non-response handling defined (what happens when an owner does not attest within the cycle)

☐  Process documented in the agreed location and reviewed with the Computer CCB Class Manager (DEP-5)

☐  Doc-only — no PROD change required; deliverable is demonstrable during the Aug 5–15 test freeze

Dependencies: DEP-1 (audit spike 1480114 gap plan), DEP-5 (Class Manager attribute confirmation).

CC-2 · [Enabler – Configuration] Build Computer certification policies/rules to PROD

| Field | Value |
| --- | --- |
| Type | Enabler – Configuration |
| Parent feature | 1517029 |
| Sprint | 3.2 |
| Owner | Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402976 (execute policies), re-scoped to Computer |
| Depends on | CC-1, DEP-3 (Data Dictionary CCB), DEP-4 (test freeze lifts) |
| Tags | Data-Certification Computer Configuration CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the ServiceNow data-certification campaign, filters, and attestation rules for cmdb_ci_computer configured and deployed to PROD,

So that Computer CI owners can be issued attestation tasks against the agreed attribute set on a defined schedule.

Acceptance criteria:

☐  Certification definition/filter created scoping the active cmdb_ci_computer population (≈19,901 — reconcile to the "active" lifecycle definition, DEP-5)

☐  Attestation rules configured for the Computer managed attribute set per CC-1 (Assigned To, CI Owner, Technical Owner Group, Support Group, Asset Tag, OS, Location, IP Address, Serial Number)

☐  Certification schedule configured (frequency + first run window) and documented

☐  Configuration migrated to PROD via a governed update set / change (post-freeze, on/after Aug 15 — DEP-4)

☐  Task routing verified — attestation tasks land with the correct owner group (managed_by_group / support_group)

☐  Dry-run on a bounded owner group confirms tasks generate and complete without error before full launch

Dependencies: CC-1, DEP-3 (attribute set locked by CCB), DEP-4 (test freeze), DEP-5 (active-population definition).

CC-3 · [Enabler – Configuration] Stand up the Computer certification tracking dashboard

| Field | Value |
| --- | --- |
| Type | Enabler – Configuration |
| Parent feature | 1517029 |
| Sprint | 3.2 → 3.3 |
| Owner | Kiran (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402727 (dashboard), re-scoped to Computer |
| Depends on | CC-2 |
| Tags | Data-Certification Computer Dashboard CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want a live tracking dashboard for the Computer certification cycle — coverage, attestation status, and outstanding gaps,

So that certification progress against the Sep 30 gate is visible to the team and stakeholders without manual reporting.

Acceptance criteria:

☐  Dashboard shows Computer certification coverage: % attested, pending, and overdue against the scoped active population

☐  Outstanding-gap view surfaces the attributes driving non-certification (cross-checks the 1480114 audit gaps so remediation is not double-counted — DEP-1)

☐  Dashboard reads from the live certification records created by CC-2 (not a static export)

☐  Coordinated with the CMDB Health Completeness (Computer) config so the two do not build overlapping scoring — see CP-1 (DEP-6)

☐  Dashboard reviewed with PO (Joe Dames) and confirmed as the reporting source for the Sep 30 gate

☐  Refresh cadence confirmed — scores update on schedule, not stale

Dependencies: CC-2 (records must exist to report on), DEP-1 (audit-gap alignment), DEP-6 (CP-1 coordination).

CC-4 · [User Story] Run the Computer certification cycle and monitor completeness

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517029 |
| Sprint | 3.3 |
| Owner | Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402980 (monitor completeness), re-scoped to Computer |
| Depends on | CC-2, CC-3 |
| Tags | Data-Certification Computer CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the first Computer certification cycle executed end-to-end with completeness monitored on the dashboard,

So that attestation is actively driven to the target coverage and the process is proven before the Sep 30 gate.

Acceptance criteria:

☐  First certification cycle launched to Computer CI owners via the CC-2 configuration

☐  Attestation progress tracked on the CC-3 dashboard through the cycle

☐  Gaps surfaced during attestation routed to remediation per the CC-1 process (owner correction / support-group action)

☐  Coverage reaches the agreed acceptance target for Computers (ties the 90%-coverage acceptance — DEP-2); shortfall documented with cause if target not met

☐  Non-responding owners escalated per the CC-1 escalation path

☐  Cycle outcome (coverage %, gaps closed, gaps outstanding) recorded and reviewed at Sprint Review

Dependencies: CC-2 (PROD build), CC-3 (dashboard), DEP-2 (90%-coverage acceptance target).

CC-5 · [User Story] Deliver Computer certification training to CI owners

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517029 |
| Sprint | 3.4 |
| Owner | Joe Dames (PO) / Manuel Vazquez |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402962 (kick-off/training) + 1402984 (office hours), re-scoped to Computer |
| Depends on | CC-2, CC-4 |
| Tags | Data-Certification Computer Training CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want Computer CI owners trained on the certification process — how to attest, correct gaps, and use office hours,

So that owners can sustain certification independently and the CO6 "training delivered" artifact is satisfied for the Computer class.

Acceptance criteria:

☐  Training material produced covering the Computer certification workflow (attest, remediate, re-attest) per CC-1

☐  Training delivered to the Computer CI owner / support-group audience; attendance or distribution recorded

☐  Office-hours / support channel established and communicated for attestation questions

☐  Quick-reference (job aid) distributed to owners

☐  Training completion evidenced for the Sep 30 gate (session recording, deck, or sign-off log)

☐  PO (Joe Dames) confirms the training artifact satisfies the CO6 Computer certification acceptance criterion

Dependencies: CC-2 (process live to train against), CC-4 (real cycle to reference in training).

Gate note: CO6 due Sep 30 lands on the 3.4/3.5 boundary → this story is the tight item; it must be done by end of Sprint 3.4 (Sep 29).

Dependencies (6)

Work item type: Dependency · Linked to: Feature 1517029 (Blocked By) · Area path: A-INFOPS\FY26\PI3

Each dependency is stated as Problem (why it blocks) + Acceptance criteria (what "resolved" looks like), per SAFe.

DEP-1 · Computer audit-dashboard scope + gap-remediation spike (1480114) closed

| Field | Value |
| --- | --- |
| Title | [Dependency] Close Computer audit spike 1480114 — Feature 1517029 |
| Assigned To | Stan (confirm) |
| Priority | 1 |
| State | ✅ CLOSED — 1480114 completed (confirmed 2026-07-28) |
| Due Date | 2026-08-05 (met early) |

RESOLVED (2026-07-28): Spike 1480114 is closed. CC-1 (process-flow doc) is no longer blocked by this dependency — it may proceed on the published gap plan once DEP-5 (Class Manager attribute confirmation) also clears. Confirm the two sub-criteria below (gap plan published + reviewed with Class Manager) are satisfied by the closed spike; if the review with the Computer Class Manager did not happen inside 1480114, it rolls into DEP-5.

Problem: CC-1 documents the certification process *off the 1480114 gap-remediation plan*, and CC-3's dashboard cross-checks the same audit gaps. If 1480114 has not closed, the Computer attribute gap picture is undefined and CC-1 cannot anchor to it — blocking the whole feature at story 1.

Acceptance criteria:

☐  Spike 1480114 completed and its Computer gap-remediation plan published

☐  The audited Computer attribute gaps (Missing CI Owner, Assigned To empty, Location empty, Missing IP) quantified and available as CC-1/CC-3 input

☐  Gap plan reviewed with the Computer CCB Class Manager (links DEP-5)

DEP-2 · Computers 90%-coverage acceptance story (G2) created and accepted

| Field | Value |
| --- | --- |
| Title | [Dependency] Create + accept Computers 90%-coverage story (G2) — Feature 1517029 |
| Assigned To | Manuel Vazquez |
| Priority | 1 |
| State | Open (net-new — no formal story exists) |
| Due Date | 2026-08-19 |

Problem: The CO6 Computer certification acceptance is evidenced by a 90%-coverage acceptance story (gate G2). No formal ADO story exists yet. Without an agreed coverage target and acceptance vehicle, CC-4's completeness cycle has no defined "done" and the feature cannot be signed off at the Sep 30 gate.

Acceptance criteria:

☐  90%-coverage acceptance story for Computers (G2) created in ADO and linked to Feature 1517029

☐  Coverage target and measurement basis (which attributes, which active population) agreed with PO (Joe Dames) and PM (Sonika Das)

☐  Story referenced as the acceptance target in CC-4

☐  Accepted at the appropriate Sprint Review as the Computer certification evidence

DEP-3 · Data Dictionary CCB approval — Computer attribute set (1480097/1480098)

| Field | Value |
| --- | --- |
| Title | [Dependency] Data Dictionary CCB approval covering Computer attributes — Feature 1517029 |
| Assigned To | Manuel Vazquez / Josh Sterling (CCB Chair) |
| Priority | 1 |
| State | Open (target Jul 21 — PI-2 carryover) |
| Due Date | 2026-08-19 |

Problem: CC-2 configures attestation rules against the Computer managed-attribute set. If the Data Dictionary is not CCB-approved, the certified attribute list can still change under the team, forcing rework of the PROD build and invalidating early attestations.

Acceptance criteria:

☐  Data Dictionary CCB approval recorded covering the 9 Computer managed attributes and their field mappings (managed_by, managed_by_group, support_group, etc.)

☐  Approved attribute set matches the set configured in CC-2 — no drift

☐  Approval date and CCB decision referenced in CC-1 / CC-2

DEP-4 · Test code freeze lifts (no PROD deploy before Aug 15)

| Field | Value |
| --- | --- |
| Title | [Dependency] Test code freeze through Aug 15 — Feature 1517029 |
| Assigned To | Manuel Vazquez |
| Priority | 2 |
| State | Open |
| Due Date | 2026-08-15 |

Problem: CC-2 requires a governed PROD deployment of the certification configuration. The test code freeze (PI-3 Risk #1, CHG70100865) runs through Aug 15 — the first 10 days of PI-3 — so no deployment can occur in early Sprint 3.1. This is why the feature's build start is Sprint 3.2, not 3.1.

Acceptance criteria:

☐  Freeze end date (Aug 15) confirmed unchanged; if extended, CC-2 sprint placement re-planned

☐  Deployment window for the certification update set secured on/after Aug 15

☐  CC-1 (doc-only) confirmed as the only 1517029 work scheduled during the freeze

DEP-5 · Computer CCB Class Manager confirms attribute set + active-population definition

| Field | Value |
| --- | --- |
| Title | [Dependency] Class Manager sign-off — Computer attribute set + active scope — Feature 1517029 |
| Assigned To | Manuel Vazquez |
| Priority | 2 |
| State | Open |
| Due Date | 2026-08-19 |

Problem: CC-2's scoped population (≈19,901 active cmdb_ci_computer) and the attested attribute set must be ratified by the Computer CCB Class Manager (Monica Green / Paul Becker). Without confirmation, the certification may score the wrong population (e.g. include retired CIs) or attest attributes owners cannot control.

Acceptance criteria:

☐  Monica Green / Paul Becker confirm the Computer managed-attribute set to be certified

☐  "Active" population definition (install_status / operational_status values) confirmed so the scored count reconciles to the dictionary figure (19,901)

☐  Any attribute an owner cannot reasonably attest to flagged and dispositioned before CC-2 build

DEP-6 · Coordinate with CMDB Health Completeness (Computer) config — CP-1

| Field | Value |
| --- | --- |
| Title | [Dependency] Align cert dashboard with CMDB Health Completeness CP-1 — Feature 1517029 |
| Assigned To | Manuel Vazquez |
| Priority | 3 |
| State | Open — CP-1 exists in ADO as US 1520415 (Ready DoR); ⚠️ possible duplicate 1526839 (New) to resolve |
| Due Date | 2026-08-19 |

Problem: The CMDB Health Completeness (Computer) KPI (CP-1 = ADO 1520415, parent "Governance Validation & Acceptance") scores the same Computer attribute population that CC-3's certification dashboard reports on. Building the two independently risks overlapping/contradictory scoring of the same gaps.

Acceptance criteria:

☐  CC-3 and CP-1 owners agree which artifact is authoritative for "attribute populated" scoring vs "owner attested"

☐  No double-counting of the same Computer gap across the certification dashboard and the CMDB Health completeness score

☐  Coordination decision recorded (ADO comment) and reflected in CC-3 acceptance

Sequence summary

DEP-1 (Aug 5, 1480114 gap plan) ─┐
DEP-5 (Class Manager) ───────────┼─► CC-1 (process flow, 3.1 doc-only)
                                  │        │
DEP-3 (Data Dictionary CCB) ──────┘        │
DEP-4 (freeze lifts Aug 15) ───────────────┼─► CC-2 (PROD build, 3.2)
                                            │        │
                                            │        ├─► CC-3 (dashboard, 3.2→3.3) ◄── DEP-6 (CP-1 align)
                                            │        │        │
DEP-2 (90% acceptance G2) ──────────────────┘        └────────┼─► CC-4 (run cycle + monitor, 3.3)
                                                              │        │
                                                              └────────┴─► CC-5 (training, 3.4) ── done by Sep 29

Freeze-window rule: only CC-1 (doc-only) runs during the Aug 5–15 test freeze. All PROD work (CC-2 onward) starts Sprint 3.2.

Gate: CO6 Sep 30 lands on the 3.4/3.5 boundary → the feature must be done by end of Sprint 3.4 (Sep 29); CC-5 training is the tight item. Raise DEP-1/DEP-2/DEP-3 (all PI-2 carryover) at PI Planning (IP Iteration, Jul 22–Aug 4).