PPL CMDB-CSDM — PI-3 Data Certification

Feature 1517040 — Certify Network Devices — CMDB Data Certification

DRAFT · 2026-07-27  ·  CO6 Obj 3 — Expand CI Data Certification Across All Major Classes  ·  Sprint 3.4 (ADO start); build 3.4–3.5, sign-off 3.6 IP  ·  CO6 due 2026-10-30

Feature 1517040 — Stories & Dependencies

Certify Network Devices — CMDB Data Certification

ADO start Sprint 3.4 · build 3.4–3.5 · sign-off 3.6 IP · CO6 due Oct 30 · Owner: M. Vazquez

Status: REFERENCE / DRAFT — Manuel creates the real items in ADO under Feature 1517040 and reconciles IDs back here (ADO authoritative). Per definition-of-ready, create stories from the Feature "+" link, never standalone.  Fourth and last certification feature. Same PI-2 BA pilot pattern as the other three, but the most back-loaded and most dependent — see below. See PI-3/pi3-data-certification-feature-breakdown for the full feature-level breakdown.

Sprint reconciliation & gate note (raise at Sprint Planning)

•  Sprint: ADO records Feature 1517040's start as 3.4 (Sep 16); the PI-3/pi3-data-certification-feature-breakdown shapes it 3.4 → 3.5 with sign-off in 3.6 IP. It cannot start earlier because it depends on Obj 4 populating network mandatory attributes first (DEP-1, Sep 30).

•  Gate date open item: pi3-objectives and CO6 show Oct 30; the objectives deck says Oct 27. Build done by end of Sprint 3.5 (Oct 13); 3.6 IP (Oct 14–27) is validation/training buffer. Confirm at planning.

Why this feature is the riskiest of the four (surface at planning)

1. No audit spike exists yet. Computers/Servers/Databases each have a completed audit-dashboard scope + gap spike (1480114 / 1480112 / 1480113) as their anchor. Network has none — one must be created as the first story (NW-1). That is why this feature has 6 stories, not 5.

2. No Network CCB Class Manager is named. Computers (Monica Green / Paul Becker), Servers & Databases (Ray Reuter), BA (Todd Dierksheide) all have Class Managers. Network devices have no named governance owner — required for attribute sign-off and attestation routing (DEP-4).

3. The certified attribute set isn't in the delivered dictionary. The 2026-07-21 Data Dictionary covered Computer / Server / Database / BA — not network devices. The set is "all mandatory CMDB attributes for network devices per CMDB governance," which must be defined (DEP-3) and approved (DEP-5).

4. Certification depends on Obj 4 finishing first. You cannot certify attributes that discovery has not populated. Obj 4 Feature 1517005 (Mandatory Attribute Population via Discovery) gates Sep 30 — the same window this feature must start. If Obj 4 slips, this feature slips with it (DEP-1). This is the critical path.

CO6 Acceptance Criteria this feature delivers (Oct 30)

From PI-3/pi3-objectives — Obj 3 (CO6 §4), Oct 30 gate:

*Data certification process for Network Devices: end-to-end process documented, technical build to PROD, dashboards live, training delivered.*

Device types in scope (CO6 §1, via Obj 4): Routers · Switches · Firewalls · Load Balancers · Wireless Access Points · Network Controllers

"Certified" = all four artifacts present for the Network Device classes:

| Artifact | Delivered by |
| --- | --- |
| Audit scope + gap baseline (net-new anchor) | NW-1 |
| Documented process flow | NW-2 |
| Technical build in PROD | NW-3 |
| Tracking dashboard live | NW-4 |
| Certification cycle executed + monitored | NW-5 |
| Training delivered | NW-6 |

ADO item reconciliation note

Clones the PI-2 BA certification pilot pattern, plus a net-new audit spike (no existing anchor). Reusable story shapes:

| PI-2 pilot item | Shape it provides | Clones to |
| --- | --- | --- |
| *(none — no network audit spike exists)* | Audit-dashboard scope + gap plan | NW-1 (create net-new) |
| 1402976 | Execute certification policies | NW-3 / NW-5 |
| 1402980 | Monitor completeness | NW-5 |
| 1402962 / 1402984 | Kick-off / training / office hours | NW-6 |
| 1402727 | Dashboard | NW-4 |

Cross-objective anchor: Obj 4 Feature 1517005 (mandatory attribute population) must complete before NW-3 build is meaningful — see DEP-1. Discovery of the devices themselves is Obj 4 Feature 1516993 — see DEP-2.

Prefix note: these certification stories use NW-; the Obj 4 network *discovery* stories use ND- (PI-3/pi3-nd-1516993-stories-dependencies). Different features, different work.

Stories (6)

NW-1 · [Enabler – Exploration (Spike)] Network audit-dashboard scope + gap-remediation baseline

| Field | Value |
| --- | --- |
| Type | Enabler – Exploration (Spike) |
| Parent feature | 1517040 |
| Sprint | 3.3 → 3.4 |
| Owner | Stan Tomberg (confirm) |
| Points | TBD (hard timebox) |
| ADO note | Net-new — the network equivalent of 1480112/113/114, which do not exist yet |
| Depends on | DEP-2 (discovery live), DEP-3 (attribute set) |
| Tags | Data-Certification Network Spike CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want an audit-dashboard scope and gap-remediation baseline for the six network device classes,

So that the network certification process (NW-2+) has the same gap-plan anchor the other three classes already have.

Acceptance criteria:

☐  Audit view scoped to the six device classes (Routers, Switches, Firewalls, Load Balancers, WAPs, Network Controllers) with exact sys_class_name values confirmed

☐  Per-attribute population baseline captured for the mandatory attribute set (DEP-3) — % populated / missing per class

☐  Gap-remediation plan drafted (which gaps are discovery-fixable vs owner-attestable)

☐  Baseline reconciled against the Obj 4 ≥90% coverage denominator (1356646) so counts agree

☐  Findings written up as the anchor input to NW-2 / NW-4

Dependencies: DEP-2 (devices discovered as CIs), DEP-3 (attribute set defined).

NW-2 · [User Story] Document the Network Device certification process flow

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517040 |
| Sprint | 3.4 |
| Owner | Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones the BA pilot process definition, re-scoped to Network |
| Depends on | NW-1, DEP-3 (attribute set), DEP-4 (Class Manager) |
| Tags | Data-Certification Network CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the end-to-end Network Device certification process documented — trigger, attestation steps, roles, escalation, and remediation path — built off the NW-1 baseline,

So that the certification campaign runs on an agreed, repeatable workflow before any PROD configuration is built.

Acceptance criteria:

☐  Process flow covers the full cycle: trigger → owner attestation → gap identification → remediation → re-attestation → sign-off

☐  Roles defined at each step, with the Network CCB Class Manager / governance owner identified (DEP-4)

☐  Attested attribute set confirmed against the network mandatory-attribute set (DEP-3) and the NW-1 baseline

☐  Process distinguishes discovery-populated attributes (fixed via Obj 4) from owner-attestable attributes

☐  Escalation and non-response handling defined

☐  Reviewed with the network governance owner (DEP-4)

☐  Doc-only — no PROD change required

Dependencies: NW-1 (baseline), DEP-3 (attribute set), DEP-4 (governance owner).

NW-3 · [Enabler – Configuration] Build Network Device certification policies/rules to PROD

| Field | Value |
| --- | --- |
| Type | Enabler – Configuration |
| Parent feature | 1517040 |
| Sprint | 3.4 → 3.5 |
| Owner | Stan Tomberg / Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402976 (execute policies), re-scoped to Network |
| Depends on | NW-2, DEP-1 (Obj 4 attributes populated), DEP-5 (Data Dictionary CCB) |
| Tags | Data-Certification Network Configuration CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the ServiceNow data-certification campaign, filters, and attestation rules for the network device classes configured and deployed to PROD,

So that network device owners can be issued attestation tasks against the mandatory attribute set on a defined schedule.

Acceptance criteria:

☐  Certification definition/filter created scoping the active network device population across the six classes (baseline per NW-1)

☐  Attestation rules configured for the network mandatory attribute set (DEP-3 / DEP-5)

☐  Attributes confirmed populated by Obj 4 discovery (DEP-1) before the cycle runs — certification does not attest empty fields discovery was supposed to fill

☐  Certification schedule configured (frequency + first run window) and documented

☐  Configuration migrated to PROD via a governed update set / change

☐  Task routing verified — attestation tasks land with the correct owner group

☐  Dry-run on a bounded device set confirms tasks generate and complete without error

Dependencies: NW-2, DEP-1 (Obj 4 mandatory attributes populated — critical), DEP-5 (attribute set CCB-approved).

NW-4 · [Enabler – Configuration] Stand up the Network Device certification tracking dashboard

| Field | Value |
| --- | --- |
| Type | Enabler – Configuration |
| Parent feature | 1517040 |
| Sprint | 3.4 → 3.5 |
| Owner | Kiran (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402727 (dashboard), re-scoped to Network |
| Depends on | NW-3 |
| Tags | Data-Certification Network Dashboard CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want a live tracking dashboard for the Network Device certification cycle — coverage, attestation status, and outstanding gaps,

So that certification progress against the Oct 30 gate is visible without manual reporting.

Acceptance criteria:

☐  Dashboard shows network certification coverage: % attested, pending, and overdue against the scoped active population per device class

☐  Outstanding-gap view surfaces the attributes driving non-certification (cross-checks the NW-1 baseline so remediation is not double-counted)

☐  Dashboard reads from the live certification records created by NW-3 (not a static export)

☐  Coverage aligns with the Obj 4 ≥90% network coverage reporting (1356646) so the two objectives tell a consistent story

☐  Dashboard reviewed with PO (Joe Dames) and confirmed as the reporting source for the Oct 30 gate

☐  Refresh cadence confirmed — scores update on schedule, not stale

Dependencies: NW-3 (records must exist to report on).

NW-5 · [User Story] Run the Network Device certification cycle and monitor completeness

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517040 |
| Sprint | 3.5 |
| Owner | Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402980 (monitor completeness), re-scoped to Network |
| Depends on | NW-3, NW-4, DEP-1 |
| Tags | Data-Certification Network CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the first Network Device certification cycle executed end-to-end with completeness monitored on the dashboard,

So that attestation is actively driven to the target coverage and the process is proven before the Oct 30 gate.

Acceptance criteria:

☐  First certification cycle launched to network device owners via the NW-3 configuration

☐  Attestation progress tracked on the NW-4 dashboard through the cycle

☐  Gaps surfaced during attestation routed to remediation per the NW-2 process

☐  Coverage reaches the agreed acceptance target for network devices; shortfall documented with cause (esp. gaps traceable to Obj 4 discovery not yet populating attributes — DEP-1)

☐  Non-responding owners escalated per the NW-2 escalation path

☐  Cycle outcome recorded and reviewed at Sprint Review

Dependencies: NW-3 (PROD build), NW-4 (dashboard), DEP-1 (attributes populated — gaps from unpopulated discovery are not owner-attestable).

NW-6 · [User Story] Deliver Network Device certification training to owners

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517040 |
| Sprint | 3.5 → 3.6 IP (sign-off) |
| Owner | Joe Dames (PO) / Manuel Vazquez |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402962 (kick-off/training) + 1402984 (office hours), re-scoped to Network |
| Depends on | NW-3, NW-5 |
| Tags | Data-Certification Network Training CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want network device owners trained on the certification process — how to attest, correct gaps, and use office hours,

So that owners can sustain certification independently and the CO6 "training delivered" artifact is satisfied for the Network Device class.

Acceptance criteria:

☐  Training material produced covering the network certification workflow (attest, remediate, re-attest) per NW-2

☐  Training delivered to the network device owner audience; attendance or distribution recorded

☐  Office-hours / support channel established and communicated

☐  Quick-reference (job aid) distributed to owners

☐  Training completion evidenced for the Oct 30 gate (session recording, deck, or sign-off log)

☐  PO (Joe Dames) confirms the training artifact satisfies the CO6 Network Device certification acceptance criterion

Gate note: build done by end of Sprint 3.5 (Oct 13); training/validation sign-off completes in 3.6 IP (Oct 14–27) ahead of the Oct 30 external date.

Dependencies (5)

Work item type: Dependency · Linked to: Feature 1517040 (Blocked By) · Area path: A-INFOPS\FY26\PI3

Each dependency is stated as Problem (why it blocks) + Acceptance criteria (what "resolved" looks like), per SAFe.

DEP-1 · Obj 4 mandatory attribute population complete (Feature 1517005) — CRITICAL PATH

| Field | Value |
| --- | --- |
| Title | [Dependency] Obj 4 network mandatory attributes populated (1517005) — Feature 1517040 |
| Assigned To | Manuel Vazquez (Obj 4 owner) |
| Priority | 1 |
| State | Open (Obj 4 Feature 1517005, gated Sep 30) |
| Due Date | 2026-09-30 |

Problem: Certification attests that mandatory CMDB attributes are populated and correct. For network devices those attributes are populated by Obj 4 Feature 1517005 (Mandatory Attribute Population via Discovery), which gates Sep 30. If 1517005 has not completed, NW-3/NW-5 would certify empty fields discovery was supposed to fill — producing false gaps and an invalid certification. This is the single hardest constraint on the feature.

Acceptance criteria:

☐  Obj 4 Feature 1517005 confirmed complete — mandatory network attributes populated via discovery, no mandatory fields blank

☐  Populated attribute set matches the certification attribute set (DEP-3) — no field certified that discovery does not populate

☐  If 1517005 slips: certification scope re-planned (subset of device types where attributes are populated) with PO (Joe Dames) sign-off

DEP-2 · Network devices discovered as CIs (Feature 1516993)

| Field | Value |
| --- | --- |
| Title | [Dependency] Network discovery live — devices exist as CIs (1516993) — Feature 1517040 |
| Assigned To | Manuel Vazquez (Obj 4 owner) |
| Priority | 1 |
| State | Open (Obj 4 Feature 1516993, gated Aug 31) |
| Due Date | 2026-08-31 |

Problem: There is nothing to certify until the network devices exist as CMDB records. Obj 4 Feature 1516993 (Automated Credentialed Discovery Live) creates those records and gates Aug 31. NW-1's audit baseline needs the discovered population in place.

Acceptance criteria:

☐  Obj 4 Feature 1516993 confirmed live — network device CIs created/updated by discovery across the six classes

☐  CI population per class available and plausible against the Obj 4 baseline (ties DEP-5 baseline counts)

☐  Discovered population is the scope basis for NW-1

DEP-3 · Define the network device mandatory-attribute set (per CMDB governance)

| Field | Value |
| --- | --- |
| Title | [Dependency] Define network device certification attribute set — Feature 1517040 |
| Assigned To | Manuel Vazquez / Josh Sterling (CCB Chair) |
| Priority | 1 |
| State | Open (not in the delivered 2026-07-21 Data Dictionary) |
| Due Date | 2026-09-16 |

Problem: The delivered Data Dictionary (2026-07-21) covered Computer / Server / Database / Business Application — not network devices. There is no agreed managed/mandatory attribute set for the six network classes to certify against. Without it, NW-1's baseline and NW-3's attestation rules have nothing to measure.

Acceptance criteria:

☐  Mandatory + recommended attribute set defined for each of the six network device classes, aligned with the Obj 4 "mandatory attributes per CMDB governance" definition

☐  Field names confirmed in the live instance per class

☐  Set documented as the certification basis and fed into NW-1, NW-2, NW-3, and DEP-5

DEP-4 · Identify / confirm the Network CCB Class Manager (governance owner)

| Field | Value |
| --- | --- |
| Title | [Dependency] Name the Network device CCB Class Manager — Feature 1517040 |
| Assigned To | Joe Dames (PO) / Josh Sterling (CCB Chair) |
| Priority | 2 |
| State | Open (no Class Manager named for network devices) |
| Due Date | 2026-09-16 |

Problem: Every other certified class has a named CCB Class Manager (Computers: Monica Green / Paul Becker; Servers & Databases: Ray Reuter; BA: Todd Dierksheide). Network devices have none. Without a governance owner there is no one to ratify the attribute set (DEP-3), approve targets, or own attestation routing and escalation in NW-2.

Acceptance criteria:

☐  Network device CCB Class Manager / governance owner identified and confirmed

☐  Owner engaged to ratify the attribute set (DEP-3) and the certification process (NW-2)

☐  Attestation routing and escalation path confirmed with that owner

DEP-5 · Data Dictionary CCB approval — Network device attributes

| Field | Value |
| --- | --- |
| Title | [Dependency] CCB approval of network device attribute set — Feature 1517040 |
| Assigned To | Manuel Vazquez / Josh Sterling (CCB Chair) |
| Priority | 2 |
| State | Open (depends on DEP-3, DEP-4) |
| Due Date | 2026-09-23 |

Problem: NW-3 configures attestation rules against the network attribute set. Until that set is CCB-approved (which itself needs DEP-3 defined and DEP-4's owner in place), the certified attribute list can change under the team, forcing rework of the PROD build.

Acceptance criteria:

☐  Network device attribute set (DEP-3) ratified by the Network Class Manager (DEP-4) and approved at CCB

☐  Approved set matches the set configured in NW-3 — no drift

☐  Approval date and CCB decision referenced in NW-2 / NW-3

Sequence summary

Obj 4 upstream
DEP-2 (1516993 discovery live, Aug 31) ───────────┐
DEP-1 (1517005 attributes populated, Sep 30) ─────┼── CRITICAL PATH
                                                   │
DEP-3 (define attr set) ─┐                         │
DEP-4 (name Class Mgr) ──┼─► DEP-5 (CCB approve)   │
                         │        │                │
DEP-2 ───────────────────┴─► NW-1 (audit baseline spike, 3.3→3.4)
                                   │
                                   └─► NW-2 (process flow, 3.4)
                                          │
                          DEP-1 ──────────┼─► NW-3 (PROD build, 3.4→3.5)
                          DEP-5 ──────────┘        │
                                                   ├─► NW-4 (dashboard, 3.4→3.5)
                                                   │        │
                                                   └────────┼─► NW-5 (run cycle + monitor, 3.5) ◄── DEP-1
                                                            │
                                                            └─► NW-6 (training, 3.5 → 3.6 IP)

Gate: CO6 Oct 30 falls after PI-3 ends (Oct 27). Build done by end of Sprint 3.5 (Oct 13); training/validation completes in 3.6 IP (Oct 14–27).

Critical path: DEP-1 (Obj 4 attribute population, Sep 30) is the binding constraint — this feature has the least buffer of the four. If Obj 4 slips, Network certification slips. DEP-3/DEP-4 (attribute set + Class Manager) are net-new governance gaps that must close before the build. Raise all five dependencies at PI Planning; flag Network certification as the highest-risk item in the objective.