PPL CMDB-CSDM — PI-3 Data Certification

Feature 1517032 — Certify Servers — CMDB Data Certification

DRAFT · 2026-07-27  ·  CO6 Obj 3 — Expand CI Data Certification Across All Major Classes  ·  Sprint 3.2 (build start); process-flow doc 3.1  ·  CO6 due 2026-09-30

Feature 1517032 — Stories & Dependencies

Certify Servers — CMDB Data Certification

Sprint 3.2 (build) · process-flow doc starts 3.1 · CO6 due Sep 30 · Owner: M. Vazquez

Status: REFERENCE / DRAFT — Manuel creates the real items in ADO under Feature 1517032 and reconciles IDs back here (ADO authoritative). Per definition-of-ready, create stories from the Feature "+" link, never standalone.  Parallel to PI-3/pi3-cert-1517029-certify-computers-stories-dependencies (Computers). Both certify a CI class off the PI-2 BA pilot pattern to the same Sep 30 gate. See PI-3/pi3-data-certification-feature-breakdown for the full feature-level breakdown.

Sprint reconciliation note (raise at Sprint Planning)

ADO records Feature 1517032's start as Sprint 3.2 (Aug 19); the PI-3/pi3-data-certification-feature-breakdown shapes it 3.1 → 3.4. The reconciliation: the test code freeze runs through Aug 15 (mid-3.1), so no PROD deployment is possible early — the feature's *build* work correctly starts in 3.2. The only 3.1 work is doc-only process-flow definition (SV-1) off the 1480112 gap plan, which needs no deployment.

Server starting position vs Computers (why this feature is not a straight clone)

Servers run in parallel with Computers, but the class is in a stronger and messier position:

•  Ahead on remediation: recent work took Server Location 44%→100% and IP 43%→91% — the ownership/location gaps that dominate Computers are largely closed on Servers.

•  One Mandatory attribute — `environment`: per the delivered Data Dictionary, Server is the only class with a Mandatory managed attribute. Its designation is unresolved — an open spike (server-environment-mandatory-spike) questions whether it is integration-fed (audit shows Missing Environment ≈11,665) and whether "Mandatory" means *scoring weight* or an *enforced save-time constraint*. This directly affects what the certification attests to → DEP-7.

•  Disputed active count: dictionary shows 3,917 active servers; the audit dashboard scopes 15,218. The certification scope must land on one reconciled number → DEP-5.

CO6 Acceptance Criteria this feature delivers (Sep 30)

From PI-3/pi3-objectives — Obj 3 (CO6 §4), Sep 30 gate:

*Data certification process for Servers: end-to-end process documented, technical build to PROD, dashboards live, training delivered.*

"Certified" = all four artifacts present for the Server class:

| Artifact | Delivered by |
| --- | --- |
| Documented process flow | SV-1 |
| Technical build in PROD | SV-2 |
| Tracking dashboard live | SV-3 |
| Certification cycle executed + monitored | SV-4 |
| Training delivered | SV-5 |

ADO item reconciliation note

Clones the PI-2 Business-Application certification pilot pattern; no net-new *process* is invented. Reusable story shapes (from the feature breakdown):

| PI-2 pilot item | Shape it provides | Clones to |
| --- | --- | --- |
| 1480112 | Servers audit-dashboard scope + gap-remediation plan (anchor) | Input to SV-1 (see DEP-1) |
| 1402962 | Kick-off / training | SV-5 |
| 1402976 | Execute certification policies | SV-2 / SV-4 |
| 1402980 | Monitor completeness | SV-4 |
| 1402984 | Office hours | SV-5 |
| 1402985 | Process feedback | optional SV-6 |
| 1402727 | Dashboard | SV-3 |

Stories SV-1 through SV-5 are net-new for the Server class — the pilot shapes re-scoped from Business Application to cmdb_ci_server (Windows + Linux inherit additively from the parent class).

Stories (5)

SV-1 · [User Story] Document the Server Data Certification process flow

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517032 |
| Sprint | 3.1 (doc-only — no PROD dependency) |
| Owner | Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones the BA pilot process definition, re-scoped to Server |
| Depends on | DEP-1 (1480112 gap plan), DEP-5 (Class Manager), DEP-7 (Environment ruling) |
| Tags | Data-Certification Server CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the end-to-end Server data-certification process documented — trigger, attestation steps, roles, escalation, and remediation path — built off the 1480112 gap-remediation plan,

So that the certification campaign for the Server class runs on an agreed, repeatable workflow before any PROD configuration is built.

Acceptance criteria:

☐  Process flow diagram covers the full cycle: campaign trigger → owner attestation → gap identification → remediation → re-attestation → sign-off

☐  Roles defined at each step (CI Owner, Technical Owner Group, Support Group, Process Owner) using the delivered Data Dictionary field mappings (managed_by, managed_by_group, support_group)

☐  Attested attribute set for Server confirmed against the delivered dictionary (10 managed attributes) and the 1480112 gap plan — no attribute drift

☐  `environment` handling explicitly stated — whether it is attested as Mandatory or Recommended, per the DEP-7 ruling; if unresolved, the process documents both branches

☐  Escalation and non-response handling defined

☐  Process documented in the agreed location and reviewed with the Server CCB Class Manager, Ray Reuter (DEP-5)

☐  Doc-only — no PROD change; demonstrable during the Aug 5–15 test freeze

Dependencies: DEP-1 (audit spike 1480112 gap plan), DEP-5 (Class Manager confirmation), DEP-7 (Environment Mandatory ruling).

SV-2 · [Enabler – Configuration] Build Server certification policies/rules to PROD

| Field | Value |
| --- | --- |
| Type | Enabler – Configuration |
| Parent feature | 1517032 |
| Sprint | 3.2 |
| Owner | Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402976 (execute policies), re-scoped to Server |
| Depends on | SV-1, DEP-3 (Data Dictionary CCB), DEP-4 (test freeze lifts), DEP-7 (Environment ruling) |
| Tags | Data-Certification Server Configuration CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the ServiceNow data-certification campaign, filters, and attestation rules for cmdb_ci_server configured and deployed to PROD,

So that Server CI owners can be issued attestation tasks against the agreed attribute set on a defined schedule.

Acceptance criteria:

☐  Certification definition/filter created scoping the reconciled active cmdb_ci_server population (DEP-5 resolves 3,917 vs 15,218); Windows + Linux inherit the parent-class attribute set additively

☐  Attestation rules configured for the Server managed attribute set per SV-1: CI Owner (managed_by), Technical Owner Group (managed_by_group), Support Group (support_group), Asset Tag (asset_tag), Value Stream (business_unit), SOX Type (u_sox_type), Data Classification (classification), Location (location), IP Address (ip_address), Environment (environment)

☐  `environment` configured per the DEP-7 ruling — as a scored Mandatory attribute, or Recommended, or Mandatory-on-manual-create-only — not enforced in a way that breaks Discovery/integration inserts

☐  Certification schedule configured (frequency + first run window) and documented

☐  Configuration migrated to PROD via a governed update set / change (post-freeze, on/after Aug 15 — DEP-4)

☐  Task routing verified — attestation tasks land with the correct owner group (managed_by_group / support_group)

☐  Dry-run on a bounded owner group confirms tasks generate and complete without error before full launch

Dependencies: SV-1, DEP-3 (attribute set locked by CCB), DEP-4 (test freeze), DEP-5 (active population), DEP-7 (Environment ruling).

SV-3 · [Enabler – Configuration] Stand up the Server certification tracking dashboard

| Field | Value |
| --- | --- |
| Type | Enabler – Configuration |
| Parent feature | 1517032 |
| Sprint | 3.2 → 3.3 |
| Owner | Kiran (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402727 (dashboard), re-scoped to Server |
| Depends on | SV-2 |
| Tags | Data-Certification Server Dashboard CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want a live tracking dashboard for the Server certification cycle — coverage, attestation status, and outstanding gaps,

So that certification progress against the Sep 30 gate is visible to the team and stakeholders without manual reporting.

Acceptance criteria:

☐  Dashboard shows Server certification coverage: % attested, pending, and overdue against the scoped active population

☐  Outstanding-gap view surfaces the attributes driving non-certification (cross-checks the 1480112 audit gaps so remediation is not double-counted — DEP-1); reflects the closed Location/IP gaps and highlights Environment

☐  Dashboard reads from the live certification records created by SV-2 (not a static export)

☐  Coordinated with the CMDB Health Completeness (Server) config so the two do not build overlapping scoring — see CP-2 (DEP-6)

☐  Dashboard reviewed with PO (Joe Dames) and confirmed as the reporting source for the Sep 30 gate

☐  Refresh cadence confirmed — scores update on schedule, not stale

Dependencies: SV-2 (records must exist to report on), DEP-1 (audit-gap alignment), DEP-6 (CP-2 coordination).

SV-4 · [User Story] Run the Server certification cycle and monitor completeness

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517032 |
| Sprint | 3.3 |
| Owner | Bhushan Salsekar (confirm) |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402980 (monitor completeness), re-scoped to Server |
| Depends on | SV-2, SV-3 |
| Tags | Data-Certification Server CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want the first Server certification cycle executed end-to-end with completeness monitored on the dashboard,

So that attestation is actively driven to the target coverage and the process is proven before the Sep 30 gate.

Acceptance criteria:

☐  First certification cycle launched to Server CI owners via the SV-2 configuration

☐  Attestation progress tracked on the SV-3 dashboard through the cycle

☐  Gaps surfaced during attestation routed to remediation per the SV-1 process; Environment gaps handled per the DEP-7 ruling

☐  Coverage reaches the agreed acceptance target for Servers (ties the 90%-coverage acceptance G3 — DEP-2); shortfall documented with cause if target not met

☐  Non-responding owners escalated per the SV-1 escalation path

☐  Cycle outcome (coverage %, gaps closed, gaps outstanding) recorded and reviewed at Sprint Review

Dependencies: SV-2 (PROD build), SV-3 (dashboard), DEP-2 (90%-coverage acceptance G3).

SV-5 · [User Story] Deliver Server certification training to CI owners

| Field | Value |
| --- | --- |
| Type | User Story |
| Parent feature | 1517032 |
| Sprint | 3.4 |
| Owner | Joe Dames (PO) / Manuel Vazquez |
| Points | TBD at refinement |
| ADO note | Net-new — clones pilot 1402962 (kick-off/training) + 1402984 (office hours), re-scoped to Server |
| Depends on | SV-2, SV-4 |
| Tags | Data-Certification Server Training CO6-Obj3 |

As the CMDB Configuration Management Process Owner,

I want Server CI owners trained on the certification process — how to attest, correct gaps, and use office hours,

So that owners can sustain certification independently and the CO6 "training delivered" artifact is satisfied for the Server class.

Acceptance criteria:

☐  Training material produced covering the Server certification workflow (attest, remediate, re-attest) per SV-1, including how environment is to be attested

☐  Training delivered to the Server CI owner / support-group audience; attendance or distribution recorded

☐  Office-hours / support channel established and communicated for attestation questions

☐  Quick-reference (job aid) distributed to owners

☐  Training completion evidenced for the Sep 30 gate (session recording, deck, or sign-off log)

☐  PO (Joe Dames) confirms the training artifact satisfies the CO6 Server certification acceptance criterion

Gate note: CO6 due Sep 30 lands on the 3.4/3.5 boundary → this story is the tight item; it must be done by end of Sprint 3.4 (Sep 29).

Dependencies (7)

Work item type: Dependency · Linked to: Feature 1517032 (Blocked By) · Area path: A-INFOPS\FY26\PI3

Each dependency is stated as Problem (why it blocks) + Acceptance criteria (what "resolved" looks like), per SAFe.

DEP-1 · Server audit-dashboard scope + gap-remediation spike (1480112) closed

| Field | Value |
| --- | --- |
| Title | [Dependency] Close Server audit spike 1480112 — Feature 1517032 |
| Assigned To | Anthony (Tony) (confirm) |
| Priority | 1 |
| State | ✅ CLOSED — 1480112 completed (ADO PI2.6, confirmed 2026-07-28) |
| Due Date | 2026-08-05 (met early) |

RESOLVED (2026-07-28): Spike 1480112 is closed (ADO PI2.6 board, parent "Data Certification Rollout (PI2)"). SV-1 (process-flow doc) is no longer blocked by this dependency — the Server gap-remediation plan is available to anchor it. Confirm the "reviewed with Class Manager" sub-criterion below was satisfied inside 1480112; if not, it rolls into DEP-5.

Problem: SV-1 documents the certification process *off the 1480112 gap-remediation plan*, and SV-3's dashboard cross-checks the same audit gaps. If 1480112 has not closed, the Server attribute gap picture is undefined and SV-1 cannot anchor to it — blocking the feature at story 1.

Acceptance criteria:

☐  Spike 1480112 completed and its Server gap-remediation plan published

☐  Server attribute gaps quantified (reflecting closed Location/IP gaps and the outstanding Environment gap) and available as SV-1/SV-3 input

☐  Gap plan reviewed with the Server CCB Class Manager, Ray Reuter (links DEP-5)

DEP-2 · Servers 90%-coverage acceptance story (G3) created and accepted

| Field | Value |
| --- | --- |
| Title | [Dependency] Create + accept Servers 90%-coverage story (G3) — Feature 1517032 |
| Assigned To | Manuel Vazquez |
| Priority | 1 |
| State | Open (net-new — no formal story exists) |
| Due Date | 2026-08-19 |

Problem: The CO6 Server certification acceptance is evidenced by a 90%-coverage acceptance story (gate G3). No formal ADO story exists yet. Without an agreed coverage target and acceptance vehicle, SV-4's completeness cycle has no defined "done" and the feature cannot be signed off at the Sep 30 gate.

Acceptance criteria:

☐  90%-coverage acceptance story for Servers (G3) created in ADO and linked to Feature 1517032

☐  Coverage target and measurement basis (which attributes — and whether Environment is included — which active population) agreed with PO (Joe Dames) and PM (Sonika Das)

☐  Story referenced as the acceptance target in SV-4

☐  Accepted at the appropriate Sprint Review as the Server certification evidence

DEP-3 · Data Dictionary CCB approval — Server attribute set

| Field | Value |
| --- | --- |
| Title | [Dependency] Data Dictionary CCB approval covering Server attributes — Feature 1517032 |
| Assigned To | Manuel Vazquez / Josh Sterling (CCB Chair) |
| Priority | 1 |
| State | Open (delivered to PPL 2026-07-21; CCB vote pending) |
| Due Date | 2026-08-19 |

Problem: SV-2 configures attestation rules against the Server managed-attribute set. If the Data Dictionary is not CCB-approved, the certified attribute list — including the contested Environment designation — can still change under the team, forcing rework of the PROD build and invalidating early attestations.

Acceptance criteria:

☐  Data Dictionary CCB approval recorded covering the 10 Server managed attributes and their field mappings (managed_by, managed_by_group, support_group, business_unit, classification, environment, etc.)

☐  Environment's requirement designation resolved in the approved dictionary (coordinated with DEP-7)

☐  Approved attribute set matches the set configured in SV-2 — no drift

☐  Approval date and CCB decision referenced in SV-1 / SV-2

DEP-4 · Test code freeze lifts (no PROD deploy before Aug 15)

| Field | Value |
| --- | --- |
| Title | [Dependency] Test code freeze through Aug 15 — Feature 1517032 |
| Assigned To | Manuel Vazquez |
| Priority | 2 |
| State | Open |
| Due Date | 2026-08-15 |

Problem: SV-2 requires a governed PROD deployment of the certification configuration. The test code freeze (PI-3 Risk #1, CHG70100865) runs through Aug 15 — the first 10 days of PI-3 — so no deployment can occur in early Sprint 3.1. This is why the feature's build start is Sprint 3.2, not 3.1.

Acceptance criteria:

☐  Freeze end date (Aug 15) confirmed unchanged; if extended, SV-2 sprint placement re-planned

☐  Deployment window for the certification update set secured on/after Aug 15

☐  SV-1 (doc-only) confirmed as the only 1517032 work scheduled during the freeze

DEP-5 · Class Manager confirms attribute set + reconciled active-population count

| Field | Value |
| --- | --- |
| Title | [Dependency] Ray Reuter sign-off — Server attribute set + active scope (3,917 vs 15,218) — Feature 1517032 |
| Assigned To | Manuel Vazquez |
| Priority | 2 |
| State | Open |
| Due Date | 2026-08-19 |

Problem: SV-2's scoped population must be ratified by the Server CCB Class Manager (Ray Reuter). The active-server count is disputed — the delivered dictionary shows 3,917 while the audit dashboard scopes 15,218 (Missing Environment 11,665 is measured against the larger set). Certifying against the wrong population invalidates the coverage %.

Acceptance criteria:

☐  Ray Reuter confirms the Server managed-attribute set to be certified

☐  The 3,917 vs 15,218 discrepancy explained — exact install_status / operational_status filter behind each figure agreed with Ray / Stan, and one scored population fixed for certification

☐  Any attribute an owner cannot reasonably attest to flagged and dispositioned before SV-2 build

DEP-6 · Coordinate with CMDB Health Completeness (Server) config — CP-2

| Field | Value |
| --- | --- |
| Title | [Dependency] Align cert dashboard with CMDB Health Completeness CP-2 — Feature 1517032 |
| Assigned To | Manuel Vazquez |
| Priority | 3 |
| State | Open — CP-2 exists in ADO as US 1520424 (Validation) |
| Due Date | 2026-08-19 |

Problem: The CMDB Health Completeness (Server) KPI (CP-2 = ADO 1520424, parent "Governance Validation & Acceptance"; and the linked environment Spike 1526856) scores the same Server attribute population that SV-3's certification dashboard reports on. Building the two independently risks overlapping/contradictory scoring of the same gaps.

Acceptance criteria:

☐  SV-3 and CP-2 owners agree which artifact is authoritative for "attribute populated" scoring vs "owner attested"

☐  No double-counting of the same Server gap across the certification dashboard and the CMDB Health completeness score

☐  Coordination decision recorded (ADO comment) and reflected in SV-3 acceptance

DEP-7 · Resolve the Server environment Mandatory designation (spike)

| Field | Value |
| --- | --- |
| Title | [Dependency] Resolve Server environment Mandatory ruling — Feature 1517032 |
| Assigned To | Stan Tomberg (technical) w/ Ray Reuter (requestor) (confirm) |
| Priority | 2 |
| State | Open — created in ADO as Spike 1526856 (New; parent "Governance Validation & Acceptance") — server-environment-mandatory-spike |
| Due Date | 2026-08-19 |

Problem: environment is the only Mandatory Server managed attribute, but its designation is unresolved: (a) it is normally non-discoverable, (b) the delivered slide names no source, (c) audit shows ≈11,665 missing — inconsistent with a reliable integration feed. Two open questions block the build: *what is the source* (integration vs manual), and *does "Mandatory" mean scored-weight or an enforced save-time constraint*. If SV-2 configures Environment as enforced-Mandatory and it is not integration-fed, it can break Discovery/integration inserts and block server creation; if it is attested but unpopulated, it drags Server coverage below the DEP-2 target for reasons owners cannot fix.

Acceptance criteria:

☐  Spike server-environment-mandatory-spike completed: source of cmdb_ci_server.environment identified with evidence; SCCM hypothesis confirmed or denied

☐  "Mandatory" interpretation confirmed with Ray / CCB — scoring designation vs enforced field constraint

☐  Enforcement mode decided (scored-only, Recommended, or Mandatory-on-manual-create-only) so SV-2 can configure without breaking inserts

☐  Decision fed into DEP-3 (dictionary) and SV-1/SV-2/SV-4; CP-2 updated to match

Sequence summary

DEP-1 (Aug 5, 1480112 gap plan) ─┐
DEP-5 (Ray — attr set + count) ──┤
DEP-7 (Environment ruling) ──────┼─► SV-1 (process flow, 3.1 doc-only)
DEP-3 (Data Dictionary CCB) ──────┤        │
DEP-4 (freeze lifts Aug 15) ──────┴────────┼─► SV-2 (PROD build, 3.2)
                                            │        │
                                            │        ├─► SV-3 (dashboard, 3.2→3.3) ◄── DEP-6 (CP-2 align)
                                            │        │        │
DEP-2 (90% acceptance G3) ──────────────────┘        └────────┼─► SV-4 (run cycle + monitor, 3.3)
                                                              │        │
                                                              └────────┴─► SV-5 (training, 3.4) ── done by Sep 29

Freeze-window rule: only SV-1 (doc-only) runs during the Aug 5–15 test freeze. All PROD work (SV-2 onward) starts Sprint 3.2.

Gate: CO6 Sep 30 lands on the 3.4/3.5 boundary → the feature must be done by end of Sprint 3.4 (Sep 29); SV-5 training is the tight item.

Server-specific critical path: DEP-7 (Environment ruling) gates SV-1 *and* SV-2 — if the spike is not resolved by ~Aug 19, the build either stalls or proceeds on an assumption that may force rework. Raise DEP-1/DEP-2/DEP-3/DEP-7 (all PI-2 carryover or open spikes) at PI Planning (IP Iteration, Jul 22–Aug 4).