## Slide 1
PI-3 Objectives - CMDB / CSDM
Proposed objectives for PI Planning · SMART, CO6-aligned
7 proposed objectives · SMART · committed & stretch
PI-3 window: Aug 5 - Oct 27, 2026 · for PI Planning (Jul 22 - Aug 4)
Manuel Vazquez - Scrum Master, CMDB-CSDM
Proposed for planning discussion - Business Value set by Business Owners; committed vs. stretch confirmed at PI Planning. Grounded in CO6 v3 (authoritative).

## Slide 2
PI-3 Objectives - Overview
7 objectives · ordered by priority · committed & stretch
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
# | Objective | Measurable target | Gate | Commit | Priority
1 | Sustain ServiceNow Platform Operations | 40 pts/member/sprint · ATF plan | Oct 30 | Committed | P0
2 | Activate Qualys Integration in Production | Live in PROD · scheduled sync | Sep 30 | Committed* | P1
3 | Expand CI Data Certification (all classes) | 4 CI classes certified | Oct 30 | Committed | P1
4 | Automate Network Device Discovery | 0 failed auth · >=90% coverage | Oct 30 | Mixed | P1
5 | Build Service Maps (priority apps) | 15 Silver + Gold · >=75% inventory | Oct 30 | Stretch | P2
6 | Deliver NERC-CIP Platform Strategy | Evaluation + exec package | Oct 30 | Committed | P2
7 | Define & Begin Legacy Rationalization | 4-platform analysis · plan · Oct exec | Oct 30 | Mixed | P3
* Obj 2 committable only if the Qualys plugin is confirmed available. Mixed = the later gate is a stretch (Obj 4 90% coverage; Obj 7 Oct execution). Proposed for planning discussion - Business Value set by Business Owners; committed vs. stretch confirmed at PI Planning. Grounded in CO6 v3 (authoritative).

## Slide 3
Objective 1 - Sustain ServiceNow Platform Operations
Priority P0 · Committed
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
Sustain BAU delivery at 40 completed story points per team member per sprint across every PI-3 sprint, publish monthly sprint-allocation reports, and publish an ATF rollout plan by Oct 30.
S · Specific | BAU support + ITSM PO coverage + ATF plan, scoped to production ITSM / CMDB modules.
M · Measurable | 40 pts/member/sprint (PTO-adjusted); monthly allocation reports; 1 ATF plan (all prod capabilities in use as of Jul 31).
A · Achievable | Achievable if the Platform Support team is staffed at PI start with a PI-2 velocity baseline.
R · Relevant | The delivery engine for the whole PI - if capacity drops, every objective slips. (CO6 Platform Support + ITSM PO + ATF.)
T · Time-bound | Per sprint through PI-3; ATF plan by Oct 30.
Acceptance gates
Per sprint - 40 pts/member · Monthly - allocation reports · Oct 30 - ATF rollout plan
Lock before planning
Pin '40 pts' to your actual estimation unit; lock the team roster + PI-2 velocity baseline before planning.

## Slide 4
Objective 2 - Activate Qualys Integration in Production
Priority P1 · Committed (contingent on Qualys plugin)
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
Configure, test, and deploy the one-way ServiceNow -> Qualys integration to production by Sep 30, syncing CI owner, support group, and SOX flag on a defined schedule with zero manual handoffs.
S · Specific | One integration, explicit direction (ServiceNow -> Qualys) and fields (owner, support group, SOX flag).
M · Measurable | Live in PROD; scheduled sync; 0 manual handoffs; 0 data-loss / transformation errors.
A · Achievable | AT RISK - stories 1428703 / 1428704 are blocked on the Qualys vendor plugin.
R · Relevant | Highest contractual visibility; carries CO5 -> CO6; security / vulnerability posture.
T · Time-bound | Sep 30 - single mid-PI gate, leaving recovery room.
Acceptance gates
Sep 30 - integration live in PROD, scheduled sync, 0 manual handoffs
Lock before planning
Confirm the Qualys plugin is available (Stan / Rich Santillo) before planning. If unconfirmed, split: non-prod build (commit) vs. PROD go-live (stretch). Reconcile direction/data against CO6 v3.

## Slide 5
Objective 3 - Expand CI Data Certification Across All Major CI Classes
Priority P1 · Committed
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
Stand up data certification (process, PROD build, dashboards, training) for Computers and Servers by Sep 30 and Databases and Network Devices by Oct 30, all against the approved data dictionary.
S · Specific | 4 named CI classes; each = process definition + PROD build + dashboard + training.
M · Measurable | 4 classes certified; per-class 4 artifacts; coverage evidenced by the audit dashboards.
A · Achievable | Achievable only if PI-2 carryover closes first (CCB approval, audit spikes, 90% stories).
R · Relevant | Re-baselines CO5 D1; audit-readiness; core CMDB health.
T · Time-bound | Computers & Servers Sep 30; Databases & Network Devices Oct 30.
Acceptance gates
Sep 30 - Computers & Servers · Oct 30 - Databases & Network Devices
Lock before planning
Entry criteria: Data Dictionary CCB approval (Jul 21) + 3 audit-dashboard spikes + 90%-coverage stories. If CCB slips, Sprint-1 is blocked.

## Slide 6
Objective 4 - Automate Network Device Discovery in CMDB
Priority P1 · Committed to Sep 30; 90% coverage is Stretch
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
Discover all in-scope network device types with validated credentials (0 failed auth) and active schedules by Aug 31, populate 100% of mandatory attributes by Sep 30, and reach >=90% coverage validated by business owners by Oct 30.
S · Specific | In-scope device types (routers, switches, firewalls, load balancers, WAPs, controllers).
M · Measurable | 0 failed authentications; 0 blank mandatory attributes; >=90% vs an owner-validated inventory.
A · Achievable | Credential distribution is an unresolved CO6 RISK - 90% by Oct 30 is aggressive.
R · Relevant | CMDB completeness + incident response; foundational.
T · Time-bound | Aug 31 (creds/schedules) -> Sep 30 (attrs) -> Oct 30 (90%).
Acceptance gates
Aug 31 - creds validated + schedules active · Sep 30 - mandatory attrs 100% · Oct 30 - >=90% coverage
Lock before planning
Prove credential distribution on a pilot subnet before committing 90%. Define the coverage denominator (whose authoritative device list?).

## Slide 7
Objective 5 - Build Service Maps for Priority Business Applications
Priority P2 · Stretch (app-owner dependency)
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
Build and owner-validate service maps for 15 Silver-tier apps and >=75% of the business-service inventory by Aug 31, Gold-tier apps by Sep 30, and remaining Accenture-managed Silver-tier apps by Oct 30 - all consumable in ServiceNow.
S · Specific | Tiered app targets; dependencies down to infrastructure CIs; owner validation.
M · Measurable | 15 Silver + >=75% service inventory (Aug 31); Gold-tier (Sep 30); remaining Silver (Oct 30).
A · Achievable | HIGHEST RISK - CO6 assumes business services defined pre-start; app-owner availability is the gate.
R · Relevant | End-to-end service visibility; impact / incident analysis.
T · Time-bound | Aug 31 / Sep 30 / Oct 30.
Acceptance gates
Aug 31 - 15 Silver + >=75% inventory · Sep 30 - Gold-tier · Oct 30 - remaining Silver
Lock before planning
Secure the app-owner list before Aug 5 (hard entry criterion). Consider committing 8-10 Silver as the first gate; full 15 + Gold as stretch.

## Slide 8
Objective 6 - Deliver NERC-CIP ServiceNow Platform Strategy
Priority P2 · Committed
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
Deliver a completed dual-instance NERC-CIP evaluation (considerations, pros/cons, risks, dependencies) by Sep 30 and an executive strategy package accepted by PPL IT leadership by Oct 30.
S · Specific | 2 artifacts - dual-instance evaluation + executive strategy package.
M · Measurable | Evaluation delivered Sep 30; exec package delivered and accepted Oct 30.
A · Achievable | Highly achievable - analysis / strategy work, low technical / infra dependency.
R · Relevant | Regulatory (NERC-CIP); executive visibility.
T · Time-bound | Sep 30 (evaluation) / Oct 30 (package accepted).
Acceptance gates
Sep 30 - dual-instance evaluation · Oct 30 - exec strategy package accepted
Lock before planning
Name the accepting stakeholder (PPL IT Leadership) now - 'accepted' needs a named approver. Scope is in CO6 v3 but not the 3/27 draft - confirm with Joe / Jordan.

## Slide 9
Objective 7 - Define and Begin Legacy Platform Rationalization
Priority P3 · Committed to plan; Oct execution is Stretch
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
Complete a gap analysis of iTeam, DISCO, Cherwell, and AIM vs. ServiceNow by Aug 31, deliver a prioritized migration plan + roadmap by Sep 30, and execute the October-scope items defined in that plan by Oct 30.
S · Specific | 4 platforms (iTeam, DISCO, Cherwell, AIM); analysis -> plan -> limited execution.
M · Measurable | 4-platform gap analysis; 1 prioritized plan; defined Oct-scope items executed.
A · Achievable | Analysis achievable; execution is greenfield (only iTeam import 1452028 today), intentionally limited.
R · Relevant | Retire legacy tooling into ServiceNow.
T · Time-bound | Aug 31 (analysis) / Sep 30 (plan) / Oct 30 (Oct-scope execution).
Acceptance gates
Aug 31 - 4-platform gap analysis · Sep 30 - migration plan + roadmap · Oct 30 - Oct-scope execution
Lock before planning
Oct execution scope is defined only by the Sep 30 plan -> keep it stretch. Decide Cherwell / AIM in-or-out at planning.

## Slide 10
Gate Timeline - PI-3
When each objective's acceptance lands
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
When | What's due | Objectives
Aug 31 | Network Gear (creds + schedules) · Service Mapping (15 Silver + 75% inventory) · Legacy (gap analysis) | Obj 4, 5, 7
Sep 30 | Qualys live in PROD · Data Cert (Computers, Servers) · Network attrs · Service Mapping (Gold) · Legacy (plan) | Obj 2, 3, 4, 5, 7
Oct 27 | PI-3 ends | -
Oct 30 | ATF plan · Data Cert (Databases, Network) · Network 90% · Service Mapping (remaining Silver) · NERC-CIP package · Legacy (Oct exec) | Obj 1, 3, 4, 5, 6, 7
The Oct 30 CO6 gates land ~3 days after PI-3 ends (Oct 27) - plan them into the final sprint / IP iteration.

## Slide 11
Lock These Before PI Planning
Each turns an objective from aspirational to genuinely Achievable
PPL CMDB-CSDM | PI-3 Objectives (proposed) | Jul 11, 2026
Lock before Aug 5 / PI Planning | Threatens | Owner
CO6 executed (signature) | All objectives | Christian / Aaron Simeon
Qualys vendor plugin confirmed available | Obj 2 (blocked stories 1428703/04) | Stan / Rich Santillo
App-owner list secured (Silver / Gold tiers) | Obj 5 | Tanzeel / Joe
Data Dictionary CCB approval (Jul 21) + audit spikes + 90% stories | Obj 3 | Manuel / Josh Sterling
Credential-distribution approach proven on a pilot | Obj 4 (90% coverage) | Stan
Named accepting stakeholder for NERC-CIP | Obj 6 | Joe
These are already in the PI-3 open-actions list - reframed here as entry criteria: a commitment isn't real until its dependency is closed.