## Slide 1
PI-3 Objectives - CMDB / CSDM
Four proposed objectives · SMART, mapped to CO6 v3 deliverables
Network Gear · Service Mapping · CMDB Governance · Qualys Integration
PI-3 window: Aug 5 - Oct 27, 2026 · for PI Planning (Jul 22 - Aug 4)
Manuel Vazquez - Scrum Master, CMDB-CSDM
Proposed for PI Planning - Business Value set by Business Owners. Grounded in the authoritative CO6 v3.

## Slide 2
PI-3 Objectives - Overview
Four objectives, each mapped to a CO6 v3 deliverable
PPL CMDB-CSDM | PI-3 Objectives (proposed) | CO6 v3 - Jul 12, 2026
# | Objective | CO6 v3 deliverable | Measurable target | Gate | Commit
1 | Automate Network Device Discovery | v3 #1 Network Gear | 0 failed auth · >=90% coverage | Oct 30 | Mixed
2 | Build & Validate Service Maps | v3 #2 Service Mapping | 15 Silver + Gold · >=75% inventory | Oct 30 | Stretch
3 | Certify CMDB Data (4 CI classes) | v3 #4 CMDB Governance | 4 CI classes certified | Oct 30 | Committed
4 | Activate ServiceNow->Qualys Sync | v3 #3 Qualys Integration | Live in PROD · scheduled sync | Sep 30 | Committed*
* Obj 4 committable only if the Qualys plug-in is confirmed. Mixed = later gate is a stretch (Obj 1 90% coverage). Proposed for PI Planning - Business Value set by Business Owners. Grounded in the authoritative CO6 v3.

## Slide 3
Objective 1 - Automate Network Device Discovery in the CMDB
Maps to CO6 v3 Deliverable #1 (Network Gear Discovery) · Committed to Sep 30; 90% = Stretch
PPL CMDB-CSDM | PI-3 Objectives (proposed) | CO6 v3 - Jul 12, 2026
Enable automated discovery of all in-scope network device types with validated credentials (0 failed auth) and active schedules by Aug 31, 100% of mandatory attributes by Sep 30, and >=90% of the business-owner-validated device inventory in the CMDB by Oct 30.
S · Specific | Named device types (routers, switches, firewalls, load balancers, WAPs, controllers); creds, schedules, attributes, coverage.
M · Measurable | 0 failed authentications; 0 blank mandatory attributes; >=90% vs an owner-validated inventory.
A · Achievable | At risk - credential distribution is an unsolved CO6 risk; 90% by Oct 30 is aggressive.
R · Relevant | CMDB completeness and incident impact analysis.
T · Time-bound | Aug 31 -> Sep 30 -> Oct 30 (Oct 30 lands just after PI-3 ends Oct 27).
Acceptance criteria (CO6 v3) | Target date
• Device types discovered via validated credentials - no failed authentications • Discovery schedules active on defined intervals; CMDB auto-updated each cycle | Aug 31, 2026
All mandatory CMDB attributes populated via discovery - none blank | Sep 30, 2026
>=90% of expected inventory in the CMDB, validated by business owners | Oct 30, 2026
Lock before planning
Prove credential distribution on a pilot subnet before committing 90%. Define the coverage denominator (authoritative device list).

## Slide 4
Objective 2 - Build & Validate Service Maps for Priority Business Apps
Maps to CO6 v3 Deliverable #2 (Service Mapping) · Stretch (app-owner dependency)
PPL CMDB-CSDM | PI-3 Objectives (proposed) | CO6 v3 - Jul 12, 2026
Deliver owner-validated, ServiceNow-consumable service maps - 15 Silver-tier apps (app->infra) and >=75% of the business-service inventory by Aug 31, Gold-tier (service->app) maps by Sep 30, and the remaining Contractor-managed Silver-tier maps by Oct 30.
S · Specific | Tiered targets; two mapping layers (app->infra, service->app); owner validation; consumable in ServiceNow.
M · Measurable | 15 Silver-tier maps; Gold-tier maps; >=75% business-service inventory.
A · Achievable | Highest risk - depends on app-owner availability and business services being defined before start.
R · Relevant | Faster incident triage and change-impact assessment; lower MTTR.
T · Time-bound | Aug 31 / Sep 30 / Oct 30.
Acceptance criteria (CO6 v3) | Target date
• 15 Silver-tier maps (business app -> infrastructure), owner-validated, teams enabled • >=75% business-service inventory represented, owner-validated (*assumes services defined prior to start) | Aug 31, 2026
• 15 Silver-tier maps: additional validation pass • Gold-tier maps (business service -> business application), owner-validated, teams enabled | Sep 30, 2026
• Remaining Contractor-managed Silver-tier maps (app -> infra) • Silver-tier maps (business service -> business application) | Oct 30, 2026
Lock before planning
Secure the app-owner list before Aug 5. Consider committing 8-10 Silver as the first gate; full 15 + Gold as stretch.

## Slide 5
Objective 3 - Certify CMDB Data Across the Four Major CI Classes
Maps to CO6 v3 Deliverable #4 (CMDB Governance) · Committed
PPL CMDB-CSDM | PI-3 Objectives (proposed) | CO6 v3 - Jul 12, 2026
Stand up an end-to-end data certification process - documented flow, technical build in production, tracking dashboards, and delivered training - for Computers and Servers by Sep 30 and Databases and Network Devices by Oct 30.
S · Specific | 4 CI classes; each = process flow + PROD build + dashboards + training.
M · Measurable | 4 classes fully certified (4 artifacts each).
A · Achievable | Depends on PI-2 carryover: Data Dictionary CCB approval (Jul 21) + audit-dashboard spikes.
R · Relevant | Audit-readiness and a trustworthy CMDB for change / incident / regulatory decisions.
T · Time-bound | Computers & Servers Sep 30; Databases & Network Devices Oct 30.
Acceptance criteria (CO6 v3) | Target date
• Data certification for Computers - process flow, PROD build, dashboards, training • Data certification for Servers - same | Sep 30, 2026
• Data certification for Databases - same • Data certification for Network Devices - same | Oct 30, 2026
Lock before planning
Close the PI-2 carryover gates before PI-3 starts, or Sprint-1 is blocked.

## Slide 6
Objective 4 - Activate the ServiceNow -> Qualys Attribute Sync in Production
Maps to CO6 v3 Deliverable #3 (Qualys Integration) · Committed (contingent on plug-in)
PPL CMDB-CSDM | PI-3 Objectives (proposed) | CO6 v3 - Jul 12, 2026
Configure, test, and deploy to production a one-way ServiceNow -> Qualys integration that automatically synchronizes CI owner, support group, and SOX flag on a defined schedule with zero manual handoffs, by Sep 30.
S · Specific | One integration; direction ServiceNow -> Qualys; three fields (owner, support group, SOX flag).
M · Measurable | Live in production; scheduled sync; 0 manual handoffs.
A · Achievable | Contingent on the Qualys plug-in; stories 1428703/1428704 are blocked and scoped for the old direction.
R · Relevant | Ties vulnerability data to the right owners and compliance context; audit readiness.
T · Time-bound | Sep 30 - single mid-PI gate.
Acceptance criteria (CO6 v3) | Target date
One-way ServiceNow -> Qualys integration configured, tested, live in PROD; owner, support group & SOX flag auto-synchronized on a defined schedule, no manual handoffs (*assumes the required Qualys plug-in is available) | Sep 30, 2026
Lock before planning
Confirm the Qualys plug-in is available; re-scope stories 1428703 / 1428704 to the ServiceNow -> Qualys direction.

## Slide 7
Gate Timeline - PI-3
When each objective's acceptance lands
PPL CMDB-CSDM | PI-3 Objectives (proposed) | CO6 v3 - Jul 12, 2026
When | What's due | Objectives
Aug 31 | Network Gear (creds + schedules) · Service Mapping (15 Silver + >=75% inventory) | Obj 1, 2
Sep 30 | Qualys live in PROD · Data cert (Computers, Servers) · Network attributes · Service Mapping (Gold + Silver pass) | Obj 1, 2, 3, 4
Oct 27 | PI-3 ends | -
Oct 30 | Network 90% · Service Mapping (remaining Silver + service->app) · Data cert (Databases, Network) | Obj 1, 2, 3
The Oct 30 gates land ~3 days after PI-3 ends (Oct 27) - plan them into the final sprint / IP iteration.

## Slide 8
Lock These Before PI Planning
Each turns an objective from aspirational to genuinely Achievable
PPL CMDB-CSDM | PI-3 Objectives (proposed) | CO6 v3 - Jul 12, 2026
Lock before Aug 5 / PI Planning | Threatens | Owner
Qualys plug-in confirmed available | Obj 4 (stories 1428703/04 blocked) | Stan / Rich Santillo
Re-scope Qualys stories to ServiceNow -> Qualys direction | Obj 4 | Stan
App-owner list secured (Silver / Gold tiers) | Obj 2 | Tanzeel / Joe
PI-2 carryover: Data Dictionary CCB approval (Jul 21) + audit spikes | Obj 3 | Manuel / Josh Sterling
Credential-distribution approach proven on a pilot | Obj 1 (90% coverage) | Stan
A commitment isn't real until its dependency is closed - resolve these before committing at PI Planning.