## Slide 1
CO5 Deliverables - Story Validation
Change Order #5 · per-deliverable feature & story mapping
3 deliverables · one slide each · PI-2 features & stories
CO5 · Mar 31 - Jun 30, 2026
Manuel Vazquez - Scrum Master, CMDB-CSDM

## Slide 2
CO5 Deliverables - Overview
3 contractual deliverables, all due Jun 30 · CO6 (draft) is the re-baselining vehicle
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
Deliverable | CO5 Due | Stories | Hard gaps | CO6 (draft) date
1 Governance | Jun 30 | ~17 | G1 Databases · G5 CCB | Jul 31
2 Automated Data Ingestion | Jun 30 | ~9 | G2/G3 90% coverage | Jul 31 / Sep 30 / Oct 30
3 Other Enhancement (Qualys) | Jun 30 | 5 | G4 BLOCKED | Oct 27
Hard gaps (G1-G5) = a CO5 acceptance item with NO story, or fully blocked. CO6 (draft, unsigned) re-baselines all but G5 - contingent on signature before July 1.
Governing constraint
CO5 (signed 2026-05-26) · term Mar 31 - Jun 30, 2026 · $533,775 June holdback released on final acceptance. PI-2 runs to Aug 4 - stories in Iter 2.4/2.5/2.6 land after the 6/30 deadline.

## Slide 3
Deliverable 1 - Governance
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
Due Jun 30 (CO5) · CO6 (draft) re-baselines to Jul 31 · Acceptance: only Data Cert is near acceptance; Databases (G1) & CCB (G5) are hard gaps
CO5 sub-item | PI-2 Feature(s) | Related stories (ID - status) | Status
1.1 Data Dictionary - Servers | 1354797 Server Class Data & Form | 1421790 Gap Analysis (Validation) · 1454371 Extract w/o Support Grp (Active) · 1355167 spike (Active) | In progress
1.1 Data Dictionary - Computers | 1354794 Computer Class Data & Form | 1313400 Asset Tags (Resolved) · 1399547 Shared Devices (Validation) · 1455858 Virtual Location (Active) | In progress
1.1 Data Dictionary - Business Apps | BA data-population cluster (no single feature) | 1475582 Support Grps (Refine Rdy) · 1478286 Classification (Refine Rdy) · 1475584/85 (New, Manuel) · 1474892 (New) | Early
1.1 Data Dictionary - Databases [G1] | - none - | NO STORY IN ADO | GAP
1.2 Data Certification | 1247179 · 1402979 · 1402958 · 1371672 | 1402727 Dashboard (UAT signed, PROD 6/23) · 1435307 Pilot Changes (Validation) · 1402962/76/80/84/85 (Defining) | Near acceptance
1.3 ESS-02 Alignment | under 1406668 (Removed) | 1420244 ESS-02 Policy & CMDB Alignment (Active - spike, analysis only) | Analysis only
1.4 SOX BA Review (SOX only, not NERC/CIP) | 1354797 / governance | 1438967 (Closed/approved) · 1455827 SOX Notify (Refine Rdy, Iter 2.5) · 1399787 Full Access Grp (Validation) | Partial
1.5 Monthly CCB + future-PI backlog [G5] | 1406668 - REMOVED in ADO | 1406672/683/687 May/Jun/Jul CCB (New, under Removed feature) · 1339116 (Refine Rdy) | Gap - broken evidence

## Slide 4
Deliverable 2 - Automated Data Ingestion
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
Due Jun 30 (CO5) · CO6 (draft): precedence/discovery -> Jul 31, 90% coverage -> Sep 30 / Oct 30 · Acceptance: precedence in Validation; both 90% goals (G2/G3) have no story
CO5 sub-item | PI-2 Feature(s) | Related stories (ID - status) | Status
2.1 Computers - SCCM/Discovery precedence | 1354794 / SCCM Computer Class | 1348712/716/717 (Resolved) · 1348715 Last-Seen (Validation) | On track
2.1 Computers - bulk Life Cycle Stage/Status | Computer Class 1354794 | 1402790 Retired Computers Lifecycle (Closed) | Done
2.1 Computers - 90% coverage validation [G2] | - none - | NO MEASUREMENT STORY | GAP
2.2 Servers - SCCM/Discovery precedence | 1356826 SCCM Server Class Precedence | 1403759 / 1403760 / 1403762 / 1403763 (all Validation, approval gate cleared) | Validation
2.2 Servers - credentials (enables discovery) | 1356646 / 1354797 | 1444864 Fix Creds Svr/DB/Net (Validation; 6 child tasks still Active) · 1459721 SNMP/MID (Validation) | In progress
2.2 Servers - 90% non-NERC-CIP coverage [G3] | - none - | NO MEASUREMENT STORY | GAP
2.3 Databases - enhanced Discovery (MS-SQL/Oracle) | 1356646 / credential work | Oracle DB cred tasks under 1444864 (in progress, task-level only) | Task-level only
SOX indicators for Servers & Databases are manually maintained - explicitly EXCLUDED from automated ingestion per CO5. CO5-documented RISK: no scalable credential-distribution solution for target CIs.

## Slide 5
Deliverable 3 - Other Enhancement
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
Due Jun 30 (CO5) · CO6 (draft) ESCALATES evaluate -> full one-way PROD integration, due Oct 27 · Acceptance: BLOCKED (G4)
CO5 sub-item | PI-2 Feature(s) | Related stories (ID - status) | Status
3 Evaluate ONE integration (Tanium OR Qualys) -> team chose Qualys | Integration Qualys & ServiceNow (CMDB Data Read-Only) (PI2) | 1428703 Install Plugin P1 (BLOCKED) · 1428704 Configure Integration P2 (BLOCKED) · 1234585 Data Scope spike (Ready, no parent) · 1465952 Plugin Replacement (Closed - may unblock) · 1383519 Qualys Dev/Support dep (Active) | BLOCKED
Detail:
Blocker: Qualys replaced the plugin version; previous uninstalled, new one requested - pending vendor approval (Issue 1465952).
1465952 now shows Closed in the 6/19 grid - MAY unblock 1428703/1428704, but story states were NOT auto-flipped. Confirm with Rich Santillo / Stan.
CO5 only requires EVALUATE + document requirements for ONE integration - a lighter bar than full implementation.
Tanium is the contractual alternative, but no Tanium stories exist - a pivot this late is unrealistic for 6/30.
CO6 (draft) escalates this to a full one-way Qualys->ServiceNow PROD integration, due Oct 27 (PI-3).

## Slide 6
Governance - Deep Dive
Deliverable 1 broken down per CO5 sub-item (1.1 - 1.5)

## Slide 7
Governance 1.1 - Data Dictionary / Class Attributes
Define class attributes for the four in-scope CI classes
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO5 requires: Data Dictionary / Class Attribute definitions for: Servers (Windows/Linux), Computers (Physical/Virtual), Business Applications, Databases.
CI Class | PI-2 Feature(s) | Related stories (ID - status) | Status
Servers (Win/Linux) | 1354797 Server Class Data & Form | 1421790 Gap Analysis (Validation) · 1454371 Extract Servers w/o Support Grp (Active) · 1355167 Migrate BA to Svc Instance (Active) | In progress
Computers (Phys/Virtual) | 1354794 Computer Class Data & Form | 1313400 Asset Tags (Resolved) · 1399547 Shared Devices (Validation) · 1455858 Virtual Location (Active) · 1407572 Auto-Populate Owner (Validation) | In progress
Business Applications | BA data-population cluster (no single feature) | 1475582 Support Grps (Refine Rdy) · 1478286 Classification (Refine Rdy) · 1475584 Tech Owner Grp (New, Manuel) · 1475585 Approval Grps (New, Manuel) · 1474892 Value Stream (New) | Early
Databases [G1] | - none - | NO STORY IN ADO - hard gap | GAP
CO6 effect: CO6 (draft) 'CMDB Governance' lists Databases explicitly -> re-baselines the full data dictionary to Jul 31. Closes hard gap G1 (if signed).
Notes / actions:
Databases is the only CI class with zero story coverage - the clean contractual gap (G1).
Business App data-population is mostly New / Refinement Ready (Iter 2.4) - lands after the 6/30 deadline.

## Slide 8
Governance 1.2 - Data Certification
Strongest-covered governance sub-item; pilot deploying to PROD 6/23
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO5 requires: Process Definition; Intake for New Data Certifications; End-to-end process flow overview; Pilot Release for the Business Application CI Class; Supporting User Documentation / KB Articles.
CO5 component | PI-2 Feature(s) | Related stories (ID - status) | Status
Process Definition & framework | 1247179 Pilot Functionality · 1402979 Impl Support | 1435307 Data Cert Pilot Changes (Validation) | On track
Intake for new certifications | 1371672 Governance Model (New BA Requests) | 1455827 SOX Notify on Ownership Change (Refine Rdy, Iter 2.5) | Partial
E2E flow + pilot execution | 1402958 Impl Planning | 1402962 Kickoff · 1402976 Execute Policies · 1402980 Monitor · 1402984 Office Hours · 1402985 Feedback (Defining/New) | In progress
Pilot Release - Business App CI Class | 1402979 Impl Support | 1402727 Dashboard (UAT signed 6/10, PROD 6/23) · 1402959 Pilot Group (Closed) | Near acceptance
Supporting KB / User Docs | - none - | NO STORY - owner TBD | Soft gap
CO6 effect: CO6 (draft) expands the pilot from Business App only to ALL CI classes -> Jul 31.
Notes / actions:
Pilot Release (Business App CI class) is the holdback-critical item: PROD deploy 6/23 -> Todd validates 6/24-25 - acceptance evidence just before 6/30.
KB Articles / User Documentation has no story and no owner - confirm before acceptance.

## Slide 9
Governance 1.3 - ESS-02 Alignment
Cyber Security & Compliance alignment - analysis only today
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO5 requires: ESS-02 Alignment with Cyber Security and Compliance.
Area | PI-2 Feature(s) | Related stories (ID - status) | Status
ESS-02 policy & CMDB alignment | under 1406668 (Removed) | 1420244 ESS-02 Policy & CMDB Alignment (Active - spike, 0 pts, Joe Dames) | Analysis only
CO6 effect: CO6 (draft) carries ESS-02 under 'CMDB Governance' -> Jul 31.
Notes / actions:
Single Active spike, no implementation stories - confirm whether alignment = analysis-only (spike sufficient) or requires a deliverable artifact by deadline.
Open actions: engage Jason Dubreuil (Cyber/Compliance CCB member) on ESS-02; document the CMP.
Parent feature 1406668 is Removed in ADO - the same dead feature as the CCB stories (see 1.5).
'ESS-02' is not expanded in the contract - confirm the definition (likely 'Enterprise Security Standard') with Jason Dubreuil.

## Slide 10
Governance 1.4 - SOX Business Application Review
Ensure SOX BAs identified in CMDB + correct update-rights controls
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO5 requires: Support review of SOX Business Applications - ensure properly identified in CMDB and rules in place so the right users can update them. Applies to SOX data ONLY - not NERC/CIP compliance indicators.
Area | PI-2 Feature(s) | Related stories (ID - status) | Status
SOX custom-fields governance | 1354797 / governance | 1438967 PMDB App Service SOX & DR Customization (Closed/approved; edit rights -> Cyber Risk & DR) | Done
SOX ownership-change notification | 1371672 | 1455827 Notification for SOX Team on Ownership Changes (Refine Rdy, Iter 2.5) | At risk - 2.5
CI-owner access governance | (no feature home) | 1399787 Add all CI-Owners to CMDB Full Access Group (Validation) | In progress
CO6 effect: CO6 (draft) carries SOX review under 'CMDB Governance' -> Jul 31. Same SOX-only boundary (NERC/CIP excluded).
Notes / actions:
Contractual boundary: SOX data ONLY. NERC-CIP (Stream B, feature 1370224) is separate and NOT part of this acceptance item.
1455827 sits in Iter 2.5 (post-6/30) with an open Joe decision: PI-2 or PI-3? Resolve to avoid a deadline miss.

## Slide 11
Governance 1.5 - Monthly CCB + Future-PI Backlog
Cadence is running, but the ADO evidence is broken (hard gap G5)
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO5 requires: Facilitate Monthly CCB Meetings and create a backlog for future PIs.
Area | PI-2 Feature(s) | Related stories (ID - status) | Status
Monthly CCB facilitation [G5] | 1406668 CMDB Governance & Monthly CCB - REMOVED in ADO | 1406672 May CCB · 1406683 June CCB · 1406687 July CCB (all New, Joe; under Removed feature) | Gap - broken evidence
CI-owner governance (leavers) | 1355888 Operational Monitoring | 1339116 Monitor / Update CI Owners Who Left PPL (Refine Rdy) | In progress
Backlog for future PIs | - | artifact not yet tracked | TBD
CO6 effect: NOT carried as a CO6 deliverable - only in the CMDB PO role text. Remains a CO5-only obligation.
Notes / actions:
CCB cadence IS happening: CCB meeting 6/16, CMDB Audit Sync 6/18, Manuel attending - but the feature that proves it (1406668) is marked Removed in ADO.
Action (high priority): un-Remove 1406668 OR re-parent the 3 CCB stories to a live feature, so the deliverable is demonstrable for acceptance.
Confirm the 'backlog for future PIs' artifact exists and is tracked.

## Slide 12
Automated Data Ingestion - Deep Dive
Deliverable 2 by sub-item (Computers / Servers / Databases) + a CO6 look-ahead: Network Gear

## Slide 13
Data Ingestion 2.1 - Computers
SCCM/Discovery precedence + bulk life-cycle + 90% coverage
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO5 requires: SCCM/Discovery data precedence reconciliation & updates; bulk updates for Life Cycle Stage & Status (process defined by Asset Mgmt team); coverage validation - goal of 90% devices managed.
CO5 component | PI-2 Feature(s) | Related stories (ID - status) | Status
SCCM/Discovery precedence | 1354794 Computer Class / SCCM Computer Class Precedence | 1348712 Domain&Network (Resolved) · 1348716 HW&SW (Resolved) · 1348717 De-Prioritize SCCM (Resolved) · 1348715 Last-Seen (Validation) | On track
Bulk Life Cycle Stage/Status | Computer Class 1354794 | 1402790 Update Lifecycle for Retired Computers (Closed) | Done
90% coverage validation [G2] | - none - | NO MEASUREMENT STORY | GAP
CO6 effect: CO6 'CI Coverage - Computers' -> precedence & life-cycle Jul 31, 90% coverage validation Sep 30. Closes G2 (if signed).
Notes / actions:
CO5 RISK: no reliable source to compare physical devices; only on-network devices are discovered.
Life Cycle process is an external dependency on the Asset Management team - not a team-owned story.
90% coverage has no measurement story (G2) - CO6 gives it a Sep 30 target.

## Slide 14
Data Ingestion 2.2 - Servers
SCCM/Discovery precedence + credentials + 90% non-NERC-CIP coverage
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO5 requires: SCCM/Discovery data precedence reconciliation & updates; coverage validation - goal of 90% non-NERC-CIP devices discovered; SOX indicators manually maintained (excluded from automation).
CO5 component | PI-2 Feature(s) | Related stories (ID - status) | Status
SCCM/Discovery precedence | 1356826 SCCM Server Class Precedence | 1403763 HW&SW (Validation) · 1403760 Domain&Network (Validation) · 1403762 Last-Seen (Validation) · 1403759 Remove SCCM Attrs (Validation) | Validation
Credentials (enables discovery) | 1356646 / 1354797 | 1444864 Fix Creds Svr/DB/Net (Validation; 6 child tasks still Active) · 1459721 SNMP/MID test (Validation) | In progress
90% non-NERC-CIP coverage [G3] | - none - | NO MEASUREMENT STORY | GAP
SOX indicators | n/a | Manually maintained - EXCLUDED from automation per CO5 | Excluded
CO6 effect: CO6 'CI Coverage - Servers' -> precedence & enhanced DB discovery Jul 31, 90% coverage Oct 30. Closes G3 (if signed).
Notes / actions:
SCCM precedence baseline RISK (Risk #12): no complete field-by-field precedence map - rework risk across stories.
Credential work gates discovery for servers AND databases; 6 tasks still Active in Iter 2.2.
90% non-NERC-CIP coverage has no measurement story (G3).

## Slide 15
Data Ingestion 2.3 - Databases
Enhanced Discovery for MS-SQL & Oracle - credential-bound
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO5 requires: Enhanced Discovery support for MS-SQL and Oracle databases (RISK - no scalable solution for the distribution of credentials to target CIs); SOX indicators manually maintained (excluded).
CO5 component | PI-2 Feature(s) | Related stories (ID - status) | Status
Enhanced Discovery (MS-SQL/Oracle) | 1356646 / credential work | Oracle DB cred tasks under 1444864 (GWIZ_MON_ORACLE_DB cred; PA Oracle DB discovery test) - task-level only | Task-level only
SOX indicators | n/a | Manually maintained - EXCLUDED from automation per CO5 | Excluded
CO6 effect: CO6 'CI Coverage - Servers' carries enhanced DB Discovery (MS-SQL/Oracle) -> Jul 31 (same RISK language).
Notes / actions:
CO5 RISK (verbatim): no scalable solution for the distribution of credentials to target CIs - your active credential/SolarWinds workstream.
No discrete 'enhanced DB Discovery' story - it lives only as credential tasks. Acceptance needs a demonstrable deliverable.
Discovery now surfacing Oracle DBs / listeners (6/9) after credential fixes - momentum is real.

## Slide 16
Look-Ahead: Network Gear Discovery
NOT a CO5 deliverable - PI-2 Objective 1, formalized as a CO6 (draft) deliverable
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
CO6 (draft) requires: Enable & configure Network Gear Discovery; devices discovered & populated in CMDB. Staged acceptance: creds configured/validated (excl. OT) & schedules active Aug 31; mandatory attrs Sep 30; 90% coverage (business-owner validated) Oct 30.
Component | PI-2 Feature(s) | Related stories (ID - status) | Status
Network device coverage | 1356646 Network Device Coverage Reconciliation - Group 1 | 1402555 Identify CI Classes (Active spike) · 1402559 Compare CI Class Sources (New spike) · 1402572/574/575 discovery & device config + rerun (New) | In progress
Credentials / SNMP | 1356646 | 1444864 Fix Creds (Validation) · 1459721 SNMP/MID test (Validation) | In progress
Stakeholder requirements | dependency | 1383487 Network-gear stakeholder requirements to assess (New, Dan Carabelas) | New
Staged acceptance: CO6 (draft) Deliverable #1 - Aug 31 / Sep 30 / Oct 30 (PI-3). 90% coverage business-owner validated by Oct 30. OT explicitly excluded.
Notes / actions:
Network gear is a PI-2 objective (Obj 1) but was NOT a CO5 deliverable - CO6 makes it contractual.
Story scaffolding exists (spikes + config stories under 1356646) but no contractual acceptance is met yet.
Shown here as a precursor/bridge to CO6 - do not report as current CO5 scope.

## Slide 17
CO6 (Draft) - Net-New Scope
TENTATIVE - based on the unsigned 3/27 draft. To be updated once the signed contract is reviewed.

## Slide 18
CO6 Net-New Deliverables
Brand-new scope with no CO5 antecedent - 6 items, mostly PI-3
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
TENTATIVE - DRAFT / UNSIGNED (3/27). Numbers, dates and scope will change once the signed contract is reviewed.
CO6 Deliverable | What it adds | Due (draft) | Story status today | Note
Network Gear Discovery | Discover & populate network devices in CMDB (excl. OT); 90% coverage | Aug 31 - Oct 30 | Scaffolding under 1356646 (spikes + config stories) | See slide 16 look-ahead
Service Mapping | E2E maps for 10 priority business apps down to infra CIs; owner-validated | Aug 31 - Oct 30 | Wave features 1355866/68/71 + per-app stories | Was PI-2 obj; now contractual
Legacy Platform Rationalization | Analysis + migration plan: iTeam, DISCO/Cherwell, AIM | Aug 31 - Oct 30 | Only iTeam import 1452028 | Cherwell/AIM 'if applicable' at PI-3
ITSM Product Management | New ITSM Product Owner role + ITSM workstream | Monthly Jul 31 - Oct 30 | None - owner TBD | Outside CMDB; ties to CR6 role seg
ATF Strategy | Automated Test Framework rollout plan across in-prod capabilities | Oct 31 | None - greenfield | Net-new analysis deliverable
Platform Support | Dedicated BAU/DevOps team; 40 hrs stories/wk per member | Monthly Aug 31 - Oct 30 | None - team size TBD ('XXX') | Ongoing capacity, not finite
Net-new != free: ITSM PM + Platform Support are ongoing-capacity commitments, not finite deliverables. CO6 also RE-BASELINES the CO5 items (Governance, CI Coverage, Qualys) - those live in the gap-closure / timeline-shift maps, not here.

## Slide 19
Sprints vs the 7/31 Date
CO6 re-dates Governance & CI Coverage to Jul 31 - but the sprint calendar tells a tighter story
PPL CMDB-CSDM | CO5 Deliverables | ADO 6/19 snapshot - Jun 20, 2026
Iteration | Window | Relation to CO6 7/31 | Freeze overlay
2.3 | Jun 10 - 23 | Active now - last fully-open sprint | none
2.4 | Jun 24 - Jul 7 | CO5 6/30 deadline here · clean dev window only Jun 24 - Jul 3 | Dev freeze from Jul 4
2.5 | Jul 8 - 21 | Runway to 7/31 - squeezed both ends | Dev freeze <= Jul 18; Test freeze >= Jul 18
2.6 (IP) | Jul 22 - Aug 4 | 7/31 LANDS HERE - IP iteration, not a delivery sprint | Test freeze Jul 18 - Aug 15
Timeline reality
7/31 sits in the IP iteration, bracketed by two freezes. The last realistic window to land a 7/31 deliverable is end of Iter 2.4 (~Jul 3, before the Dev freeze) - so CO6's 7/31 work must be substantially complete in Iter 2.3-2.4, not 'sometime in July.'
The 90% coverage items (Sep 30 / Oct 30) are the ones genuinely given room - PI-3, past the test freeze. Open question: is the IP iteration (2.6) expected to carry CO6 acceptance, or should 7/31 work be pulled into 2.4/2.5 planning?
Freeze source: Dev clone Jun 27 / upgrade Jul 4 (CHG70100870) · Test freeze CHG70100865 - see PI-2/Memory Risks #10/#11